|  | # Request for Tender New Project Building and Annex Refurbishment Tender - Stanwell Power Station Response Schedule 7 – Project Works Programs & Plans RFT # 1221995761 |
| --- | --- |

Contents

1	Project Work Program	3

1.1.	Tender Contract Program	3

2	Example Plans	4

2.1.	Project Execution Plan (PEP)	4

2.2.	Construction Management Plan (CMP)	4

2.3.	Work, Health & Safety Management Plan (WHSP)	4

# Project Work Program

Tenderers are required to review both Scopes of Works and prepare and submit one Contract Program in line with the Scopes of Works for the Project.

For example: Tenderers will have two (2) Practical Completion dates within the one Contract Program for each Scope of Work.

This program is to demonstrate the Tenderer’s proposed methodology, sequencing and resourcing approach for the delivery of the Works, and to confirm the Tenderer’s understanding of the scopes, interfaces, constraints and key milestones associated with the Project.

The submitted program will be used by Stanwell to assess the Tenderer’s ability to plan, resource and manage the Works in a structured and realistic manner, consistent with the requirements of the Contract and the complexity of the Project.

## Tender Contract Program – Scope A & B (New Project Building & Annex Refurbishment)

| No. | Tender Schedule |  |
| --- | --- | --- |
|  | The Tenderer shall submit one proposed Tender Contract Program in relation to both Scopes of Works. Tender contract programs must be developed in an industry recognised software such as P6 or similar. The Contract Program must: - be provided in the native scheduling file format approved by the Principal and in PDF format; - be resource‑loaded, identifying major commodity quantities and all direct hours required to execute the WUC; and - be developed in accordance with the Contract, including the Scope of Work and any Superintendent’s Direction. The Contract Program must reflect the Contractor’s execution methodology and be accompanied by a narrative which must: - describe the construction methodology in a logical and sequential manner; - identify the materials, equipment and labour resources proposed to complete the WUC; - identify all major and intermediate milestones, including interface milestones; - describe the basis of assumptions, qualifications, durations, logic, sequencing and resource loading; and - identify the critical path(s) for the WUC. |  |
|  | Has the Tenderer uploaded the Tender Contract Program and any relevant supporting document(s) named Schedule [X] Item [X.X] Q [X] – [Document Name]? | ☐ YES ☐ NO |

# Plans

Tenderers are required to review the Scope of Works and, in response, provide an example of a previously developed Project Execution Plan (PEP), Construction Management Plan (CMP) and Work, Health & Safety Management Plan (WHSP) from one of the three (3) reference projects submitted in Response Schedule 4: Capability, Section 2 - Project References.

Given the size, complexity and operational environment of the Works, Stanwell considers these plans to be critical delivery documents. The submission of historical examples is requested to demonstrate the Tenderer’s capability, competence and experience in developing and implementing project management, construction and WHS plans of a similar nature.

The examples provided will assist Stanwell in understanding the Tenderer’s approach, level of detail and maturity in planning for projects of this scale and complexity.

## Project Execution Plan (PEP)

| No. | Tender Schedule |  |
| --- | --- | --- |
|  | The Tenderer shall submit an example Project Execution Plan (PEP). |  |
|  | Has the Tenderer uploaded relevant supporting document(s) named Schedule [X] Item [X.X] Q [X] – [Document Name]? | ☐ YES ☐ NO |

## Construction Management Plan (CMP)

| No. | Tender Schedule |  |
| --- | --- | --- |
|  | The Tenderer shall submit an example Construction Management Plan (CMP). |  |
|  | Has the Tenderer uploaded relevant supporting document(s) named Schedule [X] Item [X.X] Q [X] – [Document Name]? | ☐ YES ☐ NO |

## Work, Health & Safety Management Plan (WHSP)

| No. | Tender Schedule |  |
| --- | --- | --- |
|  | The Tenderer shall submit an example Work, Health & Safety Management Plan (WHSP). |  |
|  | Has the Tenderer uploaded relevant supporting document(s) named Schedule [X] Item [X.X] Q [X] – [Document Name]? | ☐ YES ☐ NO |