## Instructions
RFT # 1221995761
SPS New Project Building
TENDERER INSTRUCTIONS
Pay Table, Variation Table & WBS Completion Guide
1. INTRODUCTION
1.1 | This workbook contains the pricing schedules for RFT # 1221995761 - SPS New Project Building.
1.2 | Tenderers must complete all applicable cells in the Pay Table and Variation Table tabs.
1.3 | All pricing must be entered in Australian Dollars (AUD) exclusive of GST unless otherwise stated.
1.4 | Do not modify the structure of the tables, column headings, item numbers, or formulas.
1.5 | Refer to the Scope of Work (SOW), Contract (AS4000-1997 Amended), and Drawings for scope details.
2. WORKBOOK STRUCTURE
Tab Name | Purpose | Tenderer Action | Key Input Columns
Instructions | Guidance for completing the pricing response | READ ONLY - For reference | N/A
Introduction | Tenderer company details and overview | Enter company name and contact | C4, D4
Pay Table | Contract Sum pricing - Lump Sum and Provisional Sum items | Enter RATE for each line item | Column AC (Rate)
Variation Table | Daywork rates for variations per AS4000-1997 Cl 36, 38, 41 | Enter rates in yellow columns | Columns H-S (Rates)
WBS | Work Breakdown Structure with deliverables and references | READ ONLY - For reference | N/A
Numbering | WBS coding structure reference | READ ONLY - For reference | N/A
3. PAY TABLE - COLUMN DEFINITIONS
Column | Header | Description | Data Type | Tenderer Action | Validation | Notes
A-H | N1-N7 | Internal numbering hierarchy codes | Text/Number | DO NOT MODIFY | System generated | Used for sorting/filtering
I | LEVEL | Hierarchy level (1=Section, 2=Category, 3=Sub-cat, 4=Line Item) | Number 1-4 | DO NOT MODIFY | 1, 2, 3, or 4 | Level 4 requires pricing
J | L1 | Level 1 - Major section (e.g., Section A - Lump Sum) | Text | DO NOT MODIFY | Pre-populated | Section identifier
K | L2 | Level 2 - Cost category (e.g., INDIRECT COSTS) | Text | DO NOT MODIFY | Pre-populated | Cost classification
L | L3 | Level 3 - Sub-category (e.g., PROJECT MANAGEMENT) | Text | DO NOT MODIFY | Pre-populated | Work type
M | L4 | Level 4 - Activity/Commodity detail | Text | DO NOT MODIFY | Pre-populated | Specific work item
N | L5 | Level 5 - Additional detail (if required) | Text | DO NOT MODIFY | Pre-populated | Extended detail
O | Item No. | Unique Pay Table item number (e.g., A1.01.01) | Text | DO NOT MODIFY | Alphanumeric | WBS linkage reference
P | SOW Ref# | Scope of Work reference clause(s) | Text | DO NOT MODIFY | Pre-populated | Links to SOW
Q | Contract Ref# | Contract clause reference(s) - AS4000-1997 | Text | DO NOT MODIFY | Pre-populated | Links to Contract
R | Arch Dwg Ref# | Architectural drawing references (A-series) | Text | DO NOT MODIFY | Pre-populated | A-000001 to A-910001
S | Struct Dwg Ref# | Structural drawing references (S-series) | Text | DO NOT MODIFY | Pre-populated | S1.01 to S9.02
T | Civil Dwg Ref# | Civil drawing references (C-series) | Text | DO NOT MODIFY | Pre-populated | C01 to C104
U | Mech Dwg Ref# | Mechanical drawing references (M-series) | Text | DO NOT MODIFY | Pre-populated | M0000 to M2000
V | Elec Dwg Ref# | Electrical drawing references (E-series) | Text | DO NOT MODIFY | Pre-populated | E0000 to E8002
W | Hyd Dwg Ref# | Hydraulic drawing references (H-series) | Text | DO NOT MODIFY | Pre-populated | H0000 to H9000
X | Land Dwg Ref# | Landscape drawing references (L-series) | Text | DO NOT MODIFY | Pre-populated | L0.00 to L4.02
Y | Description | Full description of work item or deliverable | Text | DO NOT MODIFY | Pre-populated | Defines scope
Z | UOM | Unit of Measure (Lot, Day, m², No., etc.) | Text | DO NOT MODIFY | Standard units | Measurement basis
AA | Pricing | Pricing type (LS=Lump Sum, PS=Provisional Sum) | Text | DO NOT MODIFY | LS or PS | Pricing method
AB | Qty | Quantity for the item | Number | VERIFY/ENTER | Positive number | Check against drawings
AC | Rate | Tenderer's rate per unit of measure in AUD | Currency | ENTER RATE | Positive number | Must include all costs
AD | Amount (AUD) | Calculated amount = Qty × Rate | Formula | AUTO-CALCULATED | N/A | Do not override
AF | Method of Measure | How work will be measured for payment | Text | DO NOT MODIFY | Pre-populated | Measurement basis
AG | Rule of Credit | Payment milestone rules and conditions | Text | DO NOT MODIFY | Pre-populated | Payment triggers
4. PAY TABLE - PRICING TYPES EXPLAINED
Pricing Type | Code | Description | How to Price | Payment Basis
Lump Sum | LS | Fixed price for complete delivery of the item regardless of actual quantities | Enter total fixed price in Rate column, Qty = 1 | Milestone-based per Rule of Credit
Provisional Sum | PS | Allowance for undefined scope - Principal directed expenditure only | Enter rate if applicable; PS amounts are Principal-controlled | Actual costs + margin as defined in Variation Table
5. METHOD OF MEASURE DEFINITIONS
Method | Description | Applies To | Documentation Required
Pro-rata monthly | Payment distributed evenly across contract period | Personnel, ongoing services | Monthly timesheets, attendance records
Milestone | Single payment upon achievement of defined milestone | Deliverables, approvals, certificates | Milestone evidence, sign-off
Milestone + Pro-rata | Partial milestone payment plus monthly pro-rata | Plans with ongoing compliance | Initial acceptance + monthly reports
Per inspection | Payment per completed inspection event | QA inspections, hold points | Signed inspection records
Per ITP | Payment per completed Inspection Test Plan | Quality activities | Completed ITP documentation
Measured in place | Payment based on installed/completed quantities | Construction items | Survey, measurement records
Lump sum complete | Single payment on completion of all works | Discrete packages | Completion certificate
Per device installed | Payment per unit installed and tested | Equipment, fixtures | Installation records, test certs
Per m² / m³ complete | Payment based on measured area/volume | Flooring, earthworks | Survey records, test results
6. RULE OF CREDIT EXAMPLES
Rule | Description | Example Application | Claim Requirement
25% Plan accepted, 75% Monthly | 25% payable on Plan acceptance, 75% paid monthly | WHSMP, CEMP, QMP | Plan approval letter + monthly reports
30% Design, 40% IFC, 30% As-built | Design payments split across key milestones | Design Management | Meeting minutes, IFC issue, As-built acceptance
40% IFC, 30% Form 15, 30% Form 12 | Design deliverables linked to certification | Contractor Design | IFC approval, Form 15 & 12 certificates
100% on completion | Full item value on completion | Discrete work packages | Completion evidence, sign-off
Per inspection/test passed | Payment per successful inspection | QA/Testing activities | Passed inspection/test records
Monthly pro-rata | Equal monthly payments over contract period | Ongoing services, personnel | Monthly attendance/activity records
Per m²/unit installed | Payment based on measured installed quantity | Construction items | Measurement records, QA acceptance
7. VARIATION TABLE - COLUMN DEFINITIONS
Per AS4000-1997 Amended - Clause 36, 38, 41
Column | Header | Description | Data Type | Tenderer Action | Validation | Notes
A | Cost Type | Classification (PERSONNEL, PLANT, MATERIALS, etc.) | Text | DO NOT MODIFY | Pre-populated | Groups items
B | Category | Main category (Management, Earthmoving, Concrete) | Text | DO NOT MODIFY | Pre-populated | Sub-grouping
C | Sub-Category | Further breakdown | Text | DO NOT MODIFY | Pre-populated | Detail level
D | Item No. | Unique variation item number (V1.01, V2.15) | Text | DO NOT MODIFY | Alphanumeric | Reference ID
E | Description | Detailed item description | Text | DO NOT MODIFY | Pre-populated | Item detail
F | UOM | Unit of Measure (Day, Hr, m², No.) | Text | DO NOT MODIFY | Standard units | Rate basis
G | Pricing Type | Rate type (Daywork, Hire, Supply, All-in) | Text | DO NOT MODIFY | Pre-populated | Rate category
H | Normal Rate | Standard rate for normal working hours | Currency | ENTER RATE | Positive number | Mon-Fri standard
I | OT 1.5x | Overtime rate at 1.5 times normal rate | Currency | ENTER RATE | ≥1.5 × Normal | First 2-3 hrs OT
J | OT 2.0x | Overtime rate at 2.0 times normal rate | Currency | ENTER RATE | ≥2.0 × Normal | Saturdays
K | OT 2.5x | Overtime rate at 2.5 times normal rate | Currency | ENTER RATE | ≥2.5 × Normal | Sundays/PH
L | Allowances | Additional allowances (travel, site, height) | Currency | ENTER IF APPLICABLE | Positive or blank | Per EBA/Award
M | Mob Rate | Mobilisation rate for equipment/plant | Currency | ENTER IF APPLICABLE | Positive or blank | One-off mob cost
N | Demob Rate | Demobilisation rate for equipment/plant | Currency | ENTER IF APPLICABLE | Positive or blank | One-off demob cost
O | Dry Hire | Equipment hire rate without operator | Currency | ENTER IF APPLICABLE | Positive or blank | Equipment only
P | Wet Hire | Equipment hire rate with operator and fuel | Currency | ENTER IF APPLICABLE | Positive or blank | Equip + operator
Q | Supply Rate | Rate for supply of materials only | Currency | ENTER IF APPLICABLE | Positive or blank | Materials ex-delivery
R | Install Rate | Rate for installation labour only | Currency | ENTER IF APPLICABLE | Positive or blank | Labour to install
S | All-in Rate | Combined supply and install rate | Currency | ENTER IF APPLICABLE | Positive or blank | Supply + Install
T | Method of Measure | How the item is measured | Text | DO NOT MODIFY | Pre-populated | Measurement basis
U | Rule of Credit | Payment/approval criteria | Text | DO NOT MODIFY | Pre-populated | Approval requirements
V | Min Charge | Minimum charge period | Text | DO NOT MODIFY | Pre-populated | Minimum billing
W | Increment | Billing increment | Text | DO NOT MODIFY | Pre-populated | Billing units
X | Valid From | Rate validity start date | Date | ENTER DATE | Date format | Rate start
Y | Valid To | Rate validity end date | Date | ENTER DATE | Date format | Rate end
Z | Notes | Additional information | Text | OPTIONAL | Free text | Clarifications
8. VARIATION TABLE - COST TYPE CATEGORIES
Section | Cost Type | Description | Key Rate Columns | Examples
V1 | PERSONNEL | Daywork rates for personnel engaged on variations | Normal Rate, OT 1.5x, OT 2.0x, OT 2.5x, Allowances | Project Manager, Electrician, Labourer
V2 | PLANT & EQUIPMENT | Hire rates for plant and equipment | Mob Rate, Demob Rate, Dry Hire, Wet Hire | Excavator, Crane, Generator, EWP
V3 | MATERIALS | Unit rates for materials supply | Supply Rate, Install Rate, All-in Rate | Concrete, Steel, Cladding, Cables
V4 | SUBCONTRACT | Rates for subcontractor works | All-in Rate (Labour + Materials) | Electrical, Plumbing, Painting
V5 | TESTING | Rates for testing and commissioning | Normal Rate (per test/day) | Compaction, Electrical, Mechanical tests
V6 | PROVISIONAL SUM | Rates for PS item work (PS1.01-PS1.05) | Normal Rate, OT rates, Materials | Rock excavation, Contamination, Latent conditions
9. REFERENCE DOCUMENTS
9.1 Contract Documents
Document | Description | Key Clauses/Sections
AS4000-1997 Amended | General Conditions of Contract - Amended for SPS Project | Cl 5, 7, 7A, 8, 12, 21, 22, 23, 26, 27, 29, 30, 32, 35, 36, 37, 38, 41, 42
Scope of Work v2.0 | SPS New Project Office - Scope of Work | SOW 3.0-12.0
Electrical Specification | Q250128 Electrical Services Specification [A] | Electrical requirements
9.2 Drawing Reference Legend
Series | Discipline | Consultant | Drawing Range | Description
A | Architectural | M3 Architecture / BH Architect | A-000001 to A-910001 | Site plans, GA, elevations, sections, facade, interior, joinery, details
S | Structural | Janes & Stewart Structures | S1.01 to S9.02 | Foundations, framing, floor plans, roof framing, hat stand
C | Civil | Janes & Stewart Structures | C01 to C104 | Earthworks, drainage, parking, erosion control
M | Mechanical | JHA Consulting Engineers | M0000 to M2000 | AC layouts, ductwork, ventilation, sections
E | Electrical | JHA Consulting Engineers | E0000 to E8002 | Lighting, power, fire detection, security, schematics
H | Hydraulic | JHA Consulting Engineers | H0000 to H9000 | Drainage, water services, fire coverage, details
L | Landscape | Subtropic Design | L0.00 to L4.02 | Ground plans, courtyard, planting schedules, details
9.3 Contract Clause Reference Key (AS4000-1997 Amended)
Clause | Title | Description
Cl 5 | Subcontracting | Subcontractor engagement and approval requirements
Cl 7 | Site Management | Site access, facilities, and management obligations
Cl 7A | Design by Contractor | Contractor design responsibilities and deliverables
Cl 8 | Documents | Document control, as-builts, and records requirements
Cl 12 | WHS/Safety | Work health and safety obligations and compliance
Cl 21 | Authorities & Approvals | Permits, approvals, and authority requirements
Cl 22, 23 | Superintendence | Superintendent role, directions, and inspections
Cl 26, 27 | Latent Conditions | Unforeseen conditions and claims process
Cl 29 | Quality Assurance | QA system requirements and implementation
Cl 30 | Inspections & Testing | Inspection, testing, and hold point requirements
Cl 32 | Programs | Program requirements, updates, and compliance
Cl 35, 35A | Warranties & Defects | Warranty period and defects liability
Cl 36 | Variations | Variation process, pricing, and approval
Cl 37 | Payments | Payment claims, certification, and timing
Cl 38, 41 | Variation Valuation | Valuation methods for variations
Cl 42 | Practical Completion | PC requirements, handover, and documentation
9.4 Scope of Work (SOW) Section Reference Key
Section | Title | Key Topics
SOW 3.0 | Scope of Works | Demolition, Civil, Structure, Fit-out, Services, Landscaping
SOW 4.0 | Procurement | Procurement planning, local content, subcontracting
SOW 5.0 | Design | Design management, contractor design, shop drawings
SOW 6.0 | Approvals | Building approval, authority inspections, certifications
SOW 7.0 | Project Management | Personnel, reporting, coordination, interface management
SOW 8.0 | Contract Administration | Claims, variations, progress reporting
SOW 9.0 | HSE | WHS management, environmental, permits and controls
SOW 10.0 | Quality | QMP, ITPs, inspections, NCRs, MDRs
SOW 11.0 | Testing & Commissioning | System testing, commissioning, handover
SOW 12.0 | Close-Out | Demobilisation, documentation, defects liability
10. SUBMISSION CHECKLIST
☐ | Item | Description | Location
☐ | Company Details | Enter Tenderer company name and contact person | Introduction tab - C4, D4
☐ | Pay Table - All Rates | Enter Rate (Column AC) for ALL Level 4 line items | Pay Table tab - Column AC
☐ | Pay Table - Verify Quantities | Review and verify quantities against drawings | Pay Table tab - Column AB
☐ | Variation Table - Personnel Rates | Enter Normal Rate, OT rates, and Allowances for V1 items | Variation Table - Columns H-L
☐ | Variation Table - Plant Rates | Enter Mob, Demob, Dry Hire, Wet Hire rates for V2 items | Variation Table - Columns M-P
☐ | Variation Table - Material Rates | Enter Supply, Install, All-in rates for V3 items | Variation Table - Columns Q-S
☐ | Variation Table - Subcontract Rates | Enter All-in rates for V4 items | Variation Table - Column S
☐ | Variation Table - Testing Rates | Enter rates for V5 items | Variation Table - Column H
☐ | Variation Table - PS Rates | Enter rates for V6 items (Provisional Sum works) | Variation Table - Columns H-S
☐ | Variation Table - Validity Dates | Enter Valid From and Valid To dates | Variation Table - Columns X-Y
☐ | Review Formulas | Verify Amount (AUD) calculations are correct | Pay Table - Column AD
☐ | No Modifications | Confirm no changes to structure, headers, or formulas | All tabs
☐ | File Format | Save as .xlsx format with all tabs intact | File properties
☐ | Final Review | Review entire workbook before submission | All tabs

## Pay Table
[14 empty] | RFT # 1221995761 SPS New Project Building | [18 empty] | Payment Claims
Contract Sum
Pricing Table Template
[14 empty] | Revision: | A
[14 empty] | ITEM | [9 empty] | Reference | Quantity UOM | [7 empty] | Claimed to Date |  | Certified to Date |  | This Claim
N1 | N2 | N3 | N32 | N4 | N5 | N6 | N7 | LEVEL | L1 | L2 | L3 | L4 | L5 | Item No. | SOW Ref# | Contract Ref# | Arch Dwg Ref# | Struct Dwg Ref# | Civil Dwg Ref# | Mech Dwg Ref# | Elec Dwg Ref# | Hyd Dwg Ref# | Land Dwg Ref# | Description | UOM | Pricing | Qty | Rate | Amount (AUD) | a | Method of Measure | Rule of Credit | Qty | Amount | Qty | Amount | Qty | Amount
CS | 0 | 0 | CS00 | 01 | 0 | 00 | 00 | 1 | Contract Sum |  |  |  |  | CS | [9 empty] | Contract Sum |  |  |  |  | 0
A | 1 | 0 | A10 | 01 | 0 | 00 | 00 | 2 | Section A - Lump Sum | INDIRECT COSTS |  |  |  | A1 | [9 empty] | INDIRECT COSTS |  |  |  |  | 0
A | 1 | 01 | A101 | 00 | 0 | 00 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE |  |  | A1.01 | SOW 7.0 | Cl 22, 23 | [7 empty] | PROJECT MANAGEMENT & GOVERNANCE |  |  |  |  | 0
A | 1 | 01 | A101 | 01 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Project Director |  | A1.01.01 | SOW 7.0, 7.1 | Cl 22, 23 | [7 empty] | Project Director | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 02 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Project Manager |  | A1.01.02 | SOW 7.0, 7.1 | Cl 22, 23 | [7 empty] | Project Manager | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 03 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Site Manager / Superintendent |  | A1.01.03 | SOW 7.0, 7.1 | Cl 22, 23 | [7 empty] | Site Manager / Superintendent | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 04 | 1 | 04 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Construction Manager |  | A1.01.04 | SOW 7.0, 7.1 | Cl 22, 23 | [7 empty] | Construction Manager | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 05 | 1 | 05 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Assistant Site Manager |  | A1.01.05 | SOW 7.0, 9.0 | Cl 12, 22, 23 | [7 empty] | Assistant Site Manager | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 06 | 1 | 06 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Project Engineer |  | A1.01.06 | SOW 7.0, 10.0 | Cl 29, 22, 23 | [7 empty] | Project Engineer | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 07 | 1 | 07 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Senior Engineer |  | A1.01.07 | SOW 7.0 | Cl 8, 22, 23 | [7 empty] | Senior Engineer | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 08 | 1 | 08 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Graduate Engineer |  | A1.01.08 | SOW 7.0 | Cl 37, 22, 23 | [7 empty] | Graduate Engineer | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 09 | 1 | 09 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Design Engineer |  | A1.01.09 | SOW 7.0 | Cl 37, 22, 23 | [7 empty] | Design Engineer | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 10 | 1 | 10 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Services Engineer (Mech/Elec/Hyd) |  | A1.01.10 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Services Engineer (Mech/Elec/Hyd) | Day | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 11 | 1 | 11 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Site Foreman / Supervisor |  | A1.01.11 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Site Foreman / Supervisor | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 12 | 1 | 12 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Leading Hand |  | A1.01.12 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Leading Hand | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 13 | 1 | 13 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Works Coordinator |  | A1.01.13 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Works Coordinator | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 14 | 1 | 14 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Night Shift Supervisor |  | A1.01.14 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Night Shift Supervisor | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 15 | 1 | 15 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Subcontractor Coordinator |  | A1.01.15 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Subcontractor Coordinator | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 16 | 1 | 16 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | HSE Manager |  | A1.01.16 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | HSE Manager | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 17 | 1 | 17 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | WHS Advisor / Safety Officer |  | A1.01.17 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | WHS Advisor / Safety Officer | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 18 | 1 | 18 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Environmental Officer |  | A1.01.18 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Environmental Officer | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 19 | 1 | 19 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Traffic Controller |  | A1.01.19 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Traffic Controller | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 20 | 1 | 20 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | First Aid Officer |  | A1.01.20 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | First Aid Officer | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 21 | 1 | 21 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Quality Manager |  | A1.01.21 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Quality Manager | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 22 | 1 | 22 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Quality Coordinator |  | A1.01.22 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Quality Coordinator | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 23 | 1 | 23 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Quality Inspector |  | A1.01.23 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Quality Inspector | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 24 | 1 | 24 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Document Controller |  | A1.01.24 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Document Controller | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 25 | 1 | 25 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Contract Administrator |  | A1.01.25 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Contract Administrator | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 26 | 1 | 26 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Cost Controller / Estimator |  | A1.01.26 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Cost Controller / Estimator | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 27 | 1 | 27 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Scheduler / Planner |  | A1.01.27 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Scheduler / Planner | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 28 | 1 | 28 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT & GOVERNANCE | Project Administrator |  | A1.01.28 | SOW 7.0 | Cl 32, 22, 23 | [7 empty] | Project Administrator | Day | LS |  |  | 0 |  | Percentage complete based | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 02 | A102 | 00 | 0 | 28 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) |  |  | A1.02 | SOW 9.0 | Cl 12 | [7 empty] | HSE (WHS / ENVIRONMENTAL) |  |  |  |  | 0
A | 1 | 02 | A102 | 01 | 1 | 29 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | WHS Management System |  | A1.02.01 | SOW 9.1 | Cl 12.3, 12.5 | [7 empty] | WHS Management System | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata monthly | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period
A | 1 | 02 | A102 | 02 | 1 | 30 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | Permits and Controls |  | A1.02.02 | SOW 9.2 | Cl 12.4 | [7 empty] | Permits and Controls | Lot | LS | 1 |  | 0 |  | Per permit/control implemented | Payment per permit obtained and control measure implemented
A | 1 | 02 | A102 | 03 | 1 | 31 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | Environmental Management (CEMP) |  | A1.02.03 | SOW 9.3 | Cl 12.3 |  |  | C05, C104 |  |  |  |  | Environmental Management (CEMP) | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata monthly | 25% upon CEMP acceptance, 75% pro-rata monthly for implementation
A | 1 | 02 | A102 | 04 | 1 | 32 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | SWMS Development & Approvals |  | A1.02.04 | SOW 9.1 | Cl 12.3 | [7 empty] | SWMS Development & Approvals | Lot | LS | 1 |  | 0 |  | Pro-rata per SWMS approved | Payment per SWMS submitted and approved by Principal
A | 1 | 02 | A102 | 05 | 1 | 33 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | Site Inductions & Competency Verification |  | A1.02.05 | SOW 9.1 | Cl 12.3, 12.4 | [7 empty] | Site Inductions & Competency Verification | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Monthly payment based on induction records and competency registers maintained
A | 1 | 02 | A102 | 06 | 1 | 34 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | Incident Management & Reporting |  | A1.02.06 | SOW 9.1 | Cl 12.9 | [7 empty] | Incident Management & Reporting | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Monthly payment subject to incident register maintained and reports submitted within 24hrs
A | 1 | 02 | A102 | 07 | 1 | 35 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE (WHS / ENVIRONMENTAL) | Traffic Management Plan & Implementation |  | A1.02.07 | SOW 9.2, 3.4 | Cl 12.6 | [7 empty] | Traffic Management Plan & Implementation | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata monthly | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period
A | 1 | 03 | A103 | 00 | 0 | 35 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | QUALITY MANAGEMENT SYSTEM |  |  | A1.03 | SOW 10.0 | Cl 29 | [7 empty] | QUALITY MANAGEMENT SYSTEM |  |  |  |  | 0
A | 1 | 03 | A103 | 01 | 1 | 36 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY MANAGEMENT SYSTEM | Quality Management Plan (QMP) |  | A1.03.01 | SOW 10.1 | Cl 29.2 | [7 empty] | Quality Management Plan (QMP) | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon QMP acceptance by Principal
A | 1 | 03 | A103 | 02 | 1 | 37 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY MANAGEMENT SYSTEM | Inspection & Test Plans (ITPs) |  | A1.03.02 | SOW 10.2 | Cl 29.2, 30 | [7 empty] | Inspection & Test Plans (ITPs) | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata | 30% ITPs approved, 70% pro-rata per ITP completed and signed off
A | 1 | 03 | A103 | 03 | 1 | 38 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY MANAGEMENT SYSTEM | Non-Conformance & Corrective Actions |  | A1.03.03 | SOW 10.3 | Cl 29.3 | [7 empty] | Non-Conformance & Corrective Actions | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Monthly payment subject to NCR register maintained and closeout within agreed timeframes
A | 1 | 03 | A103 | 04 | 1 | 39 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY MANAGEMENT SYSTEM | Witness & Hold Point Inspections |  | A1.03.04 | SOW 10.2 | Cl 30 | [7 empty] | Witness & Hold Point Inspections | Lot | LS | 1 |  | 0 |  | Per inspection completed | Payment per witness/hold point inspection completed and signed off
A | 1 | 03 | A103 | 05 | 1 | 40 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY MANAGEMENT SYSTEM | Manufacturer's Data Records (MDR) |  | A1.03.05 | SOW 10.4 | Cl 30.6 | [7 empty] | Manufacturer's Data Records (MDR) | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon all MDRs submitted and accepted prior to Practical Completion
A | 1 | 04 | A104 | 00 | 0 | 40 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | DESIGN & ENGINEERING |  |  | A1.04 | SOW 5.0 | Cl 7A | [7 empty] | DESIGN & ENGINEERING |  |  |  |  | 0
A | 1 | 04 | A104 | 01 | 1 | 41 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | DESIGN & ENGINEERING | Design Management and Coordination |  | A1.04.01 | SOW 5.0, 3.5 | Cl 7A | A-000001 to A-910001 | S1.01 to S9.02 | C01 to C104 | M0000 to M2000 | E0000 to E8002 | H0000 to H9000 | L0.00 to L4.02 | Design Management and Coordination | Lot | LS | 1 |  | 0 |  | Milestone | 30% design kickoff, 40% IFC drawings issued, 30% as-built documentation accepted
A | 1 | 04 | A104 | 02 | 1 | 42 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | DESIGN & ENGINEERING | Contractor Design Deliverables |  | A1.04.02 | SOW 5.0 | Cl 7A.2 | [7 empty] | Contractor Design Deliverables | Lot | LS | 1 |  | 0 |  | Milestone | Per design deliverable accepted by Principal
A | 1 | 04 | A104 | 03 | 1 | 43 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | DESIGN & ENGINEERING | Shop Drawings - All Disciplines |  | A1.04.03 | SOW 5.0 | Cl 7A.2 | [7 empty] | Shop Drawings - All Disciplines | Lot | LS | 1 |  | 0 |  | Per package approved | Payment per shop drawing package submitted and approved
A | 1 | 05 | A105 | 00 | 0 | 43 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | AUTHORITIES & APPROVALS |  |  | A1.05 | SOW 6.0 | Cl 21 | [7 empty] | AUTHORITIES & APPROVALS |  |  |  |  | 0
A | 1 | 05 | A105 | 01 | 1 | 44 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | AUTHORITIES & APPROVALS | Building Approval & Certification |  | A1.05.01 | SOW 6.0 | Cl 21 | A-070001 | [6 empty] | Building Approval & Certification | Lot | LS | 1 |  | 0 |  | Milestone per approval obtained | Payment upon each authority approval/permit obtained and provided to Principal
A | 1 | 05 | A105 | 02 | 1 | 45 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | AUTHORITIES & APPROVALS | Authority Inspections & Certificates |  | A1.05.02 | SOW 6.0 | Cl 21 | [7 empty] | Authority Inspections & Certificates | Lot | LS | 1 |  | 0 |  | Milestone per approval obtained | Payment upon each authority approval/permit obtained and provided to Principal
A | 2 | 0 | A20 | 02 | 0 | 45 | 00 | 2 | Section A - Lump Sum | DIRECT COSTS |  |  |  | A2 | [9 empty] | DIRECT COSTS |  |  |  |  | 0
A | 2 | 01 | A201 | 29 | 0 | 45 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | PROCUREMENT & SUBCONTRACTING |  |  | A2.01 | SOW 4.0 | Cl 5 | [7 empty] | PROCUREMENT & SUBCONTRACTING |  |  |  |  | 0
A | 2 | 01 | A201 | 30 | 1 | 46 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | PROCUREMENT & SUBCONTRACTING | Procurement Planning & Management |  | A2.01.30 | SOW 4.0 | Cl 5 | [7 empty] | Procurement Planning & Management | Lot | LS | 1 |  | 0 |  | Percentage complete based | 20% procurement plan accepted, 80% pro-rata as packages awarded
A | 2 | 01 | A201 | 31 | 1 | 47 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | PROCUREMENT & SUBCONTRACTING | Subcontractor Coordination |  | A2.01.31 | SOW 4.0 | Cl 5 | [7 empty] | Subcontractor Coordination | Lot | LS | 1 |  | 0 |  | Percentage complete based | Payment per subcontract/supply package executed
A | 2 | 02 | A202 | 08 | 0 | 47 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | OFF-SITE FABRICATION |  |  | A2.02 | SOW 5.0 | Cl 5, 30 | [7 empty] | OFF-SITE FABRICATION |  |  |  |  | 0
A | 2 | 02 | A202 | 09 | 1 | 48 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | OFF-SITE FABRICATION | Module Fabrication QA Plan |  | A2.02.09 | SOW 5.0, 10.0 | Cl 29, 30 | A-910001 | [6 empty] | Module Fabrication QA Plan | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon fabrication QA plan and ITPs accepted
A | 2 | 02 | A202 | 10 | 1 | 49 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | OFF-SITE FABRICATION | Module Fabrication & Assembly |  | A2.02.10 | SOW 5.0 | Cl 5, 30 | A-910001 | [6 empty] | Module Fabrication & Assembly | No. | LS |  |  | 0 |  | Pro-rata per module/component | Payment based on % fabrication complete verified by inspection
A | 2 | 02 | A202 | 11 | 1 | 50 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | OFF-SITE FABRICATION | Factory Acceptance Testing |  | A2.02.11 | SOW 5.0 | Cl 30 | A-910001 | [6 empty] | Factory Acceptance Testing | Lot | LS | 1 |  | 0 |  | Per FAT completed | Payment per FAT completed and witnessed
A | 2 | 03 | A203 | 06 | 0 | 50 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | LOGISTICS, DELIVERIES & LAYDOWN |  |  | A2.03 | SOW 3.4 | Cl 7 | [7 empty] | LOGISTICS, DELIVERIES & LAYDOWN |  |  |  |  | 0
A | 2 | 03 | A203 | 07 | 1 | 51 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LOGISTICS, DELIVERIES & LAYDOWN | Delivery Planning & Sequencing |  | A2.03.07 | SOW 3.4 | Cl 7 | [7 empty] | Delivery Planning & Sequencing | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon logistics plan accepted
A | 2 | 03 | A203 | 08 | 1 | 52 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LOGISTICS, DELIVERIES & LAYDOWN | Module Transport (32 Modules) |  | A2.03.08 | SOW 3.4 | Cl 7, 12.6 | [7 empty] | Module Transport (32 Modules) | No. | LS |  |  | 0 |  | Per delivery received | Payment per delivery received, inspected and accepted at site
A | 2 | 03 | A203 | 09 | 1 | 53 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LOGISTICS, DELIVERIES & LAYDOWN | Offloading & Laydown Operations |  | A2.03.09 | SOW 3.4 | Cl 7 | [7 empty] | Offloading & Laydown Operations | Lot | LS | 1 |  | 0 |  | Per delivery received | Payment per delivery received, inspected and accepted at site
A | 2 | 04 | A204 | 04 | 0 | 53 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | MOBILISATION & TEMPORARY WORKS |  |  | A2.04 | SOW 3.3, 3.4 | Cl 7 | [7 empty] | MOBILISATION & TEMPORARY WORKS |  |  |  |  | 0
A | 2 | 04 | A204 | 05 | 1 | 54 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MOBILISATION & TEMPORARY WORKS | Site Establishment |  | A2.04.05 | SOW 3.3 | Cl 7 | [7 empty] | Site Establishment | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon site establishment complete and accepted
A | 2 | 04 | A204 | 06 | 1 | 55 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MOBILISATION & TEMPORARY WORKS | Temporary Fencing & Hoarding |  | A2.04.06 | SOW 3.3.1 | Cl 7 |  |  | C02, C03 |  |  |  |  | Temporary Fencing & Hoarding | Lm | LS |  |  | 0 |  | Lump sum on completion | 100% upon fencing/hoarding installed and accepted
A | 2 | 04 | A204 | 07 | 1 | 56 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MOBILISATION & TEMPORARY WORKS | Temporary Site Offices & Amenities |  | A2.04.07 | SOW 3.3.2 | Cl 7 | [7 empty] | Temporary Site Offices & Amenities | Lot | LS | 1 |  | 0 |  | Milestone + Monthly | 50% upon installation complete, 50% pro-rata monthly for maintenance
A | 2 | 04 | A204 | 08 | 1 | 57 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MOBILISATION & TEMPORARY WORKS | Temporary Power, Water & Comms |  | A2.04.08 | SOW 3.3.3 | Cl 7 |  |  |  |  | E0010 | H0010 |  | Temporary Power, Water & Comms | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon temporary services connected and operational
A | 2 | 04 | A204 | 09 | 1 | 58 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MOBILISATION & TEMPORARY WORKS | Temporary Access & Security |  | A2.04.09 | SOW 3.3.4 | Cl 7 |  |  |  |  | E2000 |  |  | Temporary Access & Security | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon mobilisation item complete and accepted
A | 2 | 05 | A205 | 03 | 0 | 58 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | DEMOLITION & REMOVAL WORKS |  |  | A2.05 | SOW 3.6 | Cl 7 | [7 empty] | DEMOLITION & REMOVAL WORKS |  |  |  |  | 0
A | 2 | 05 | A205 | 04 | 1 | 59 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOLITION & REMOVAL WORKS | Pre-Demolition Planning & Approvals |  | A2.05.04 | SOW 3.6 | Cl 7 | A-040002 | [6 empty] | Pre-Demolition Planning & Approvals | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon demolition plan and methodology accepted
A | 2 | 05 | A205 | 05 | 1 | 60 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOLITION & REMOVAL WORKS | Demolition of Existing Demountables |  | A2.05.05 | SOW 3.6.2 | Cl 7 | A-040002 | [6 empty] | Demolition of Existing Demountables | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % demolition complete verified by site inspection
A | 2 | 05 | A205 | 06 | 1 | 61 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOLITION & REMOVAL WORKS | Services Disconnection & Capping |  | A2.05.06 | SOW 3.6.2 | Cl 7 | A-040002 |  |  |  | E0005 | H0010 |  | Services Disconnection & Capping | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % demolition complete verified by site inspection
A | 2 | 05 | A205 | 07 | 1 | 62 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOLITION & REMOVAL WORKS | Salvage, Waste Disposal & Site Clearance |  | A2.05.07 | SOW 3.6.3 | Cl 12.3 | A-040002 | [6 empty] | Salvage, Waste Disposal & Site Clearance | Lot | LS | 1 |  | 0 |  | Per load disposed | Payment per waste disposed with lawful disposal documentation
A | 2 | 06 | A206 | 00 | 0 | 62 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS |  |  | A2.06 | SOW 3.7 | Cl 7, 30 | [7 empty] | CIVIL, EARTHWORKS & EXTERNAL WORKS |  |  |  |  | 0
A | 2 | 06 | A206 | 01 | 1 | 63 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Survey & Setout |  | A2.06.01 | SOW 3.7 | Cl 7, 30 |  | S1.03 | C02, C03 |  |  |  |  | Survey & Setout | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon survey complete and setout accepted
A | 2 | 06 | A206 | 02 | 1 | 64 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Bulk Earthworks - Cut & Fill |  | A2.06.02 | SOW 3.7.1 | Cl 7, 30 |  |  | C02 |  |  |  |  | Bulk Earthworks - Cut & Fill | m³ | LS |  |  | 0 |  | Per m³ measured | Payment per m³ excavated/filled, measured in place, compaction tests passed
A | 2 | 06 | A206 | 03 | 1 | 65 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Site Regrading & Compaction |  | A2.06.03 | SOW 3.7 | Cl 7, 30 |  |  | C01 to C06 |  |  |  |  | Site Regrading & Compaction | m² | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent
A | 2 | 06 | A206 | 04 | 1 | 66 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Service Trenching & Backfill |  | A2.06.04 | SOW 3.7.2 | Cl 7, 30 |  |  | C03, C04 |  |  |  |  | Service Trenching & Backfill | Lm | LS |  |  | 0 |  | Per m³ measured | Payment per m³ excavated/filled, measured in place, compaction tests passed
A | 2 | 06 | A206 | 05 | 1 | 67 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Stormwater Drainage System |  | A2.06.05 | SOW 3.7.3 | Cl 7, 30 |  |  | C03, C04 |  |  | H1000, H1001 |  | Stormwater Drainage System | Lot | LS | 1 |  | 0 |  | Per linear metre installed | Payment per Lm installed and tested (CCTV/pressure test as applicable)
A | 2 | 06 | A206 | 06 | 1 | 68 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Erosion & Sediment Control |  | A2.06.06 | SOW 3.7 | Cl 7, 30 |  |  | C01 to C06 |  |  |  |  | Erosion & Sediment Control | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent
A | 2 | 06 | A206 | 07 | 1 | 69 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | External Pavements & Footpaths |  | A2.06.07 | SOW 3.7.4 | Cl 7, 30 |  |  | C03, C04, C06 |  |  |  |  | External Pavements & Footpaths | m² | LS |  |  | 0 |  | Per m² complete | Payment per m² placed, cured and accepted (concrete test results compliant)
A | 2 | 06 | A206 | 08 | 1 | 70 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Vehicle Parking Area |  | A2.06.08 | SOW 3.7.7 | Cl 7, 30 |  |  | C101 to C104 |  |  |  |  | Vehicle Parking Area | m² | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent
A | 2 | 06 | A206 | 09 | 1 | 71 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Linemarking |  | A2.06.09 | SOW 3.7 | Cl 7, 30 |  |  | C01 to C06 |  |  |  |  | Linemarking | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent
A | 2 | 06 | A206 | 10 | 1 | 72 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Fencing & Gates |  | A2.06.10 | SOW 3.7.5 | Cl 7, 30 |  |  | C03 |  |  |  |  | Fencing & Gates | Lm | LS |  |  | 0 |  | Per linear metre / each | Payment per Lm fencing / each gate installed and accepted
A | 2 | 06 | A206 | 11 | 1 | 73 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Retaining Walls |  | A2.06.11 | SOW 3.7.6 | Cl 7, 30 |  | S7.01 | C04 |  |  |  |  | Retaining Walls | Lm | LS |  |  | 0 |  | Per linear metre | Payment per Lm retaining wall complete, Engineer certified
A | 2 | 06 | A206 | 12 | 1 | 74 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | CIVIL, EARTHWORKS & EXTERNAL WORKS | Hat Stand Refurbishment |  | A2.06.12 | SOW 3.7.8 | Cl 7, 30 | A-810001 | S9.01, S9.02 | C01 to C06 |  |  |  |  | Hat Stand Refurbishment | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent
A | 2 | 07 | A207 | 00 | 0 | 74 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE |  |  | A2.07 | SOW 3.8 | Cl 7, 30 | [7 empty] | BUILDING STRUCTURE & ENVELOPE |  |  |  |  | 0
A | 2 | 07 | A207 | 01 | 1 | 75 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Foundations & Footings |  | A2.07.01 | SOW 3.8.1 | Cl 7, 30 | A-300002 | S2.01, S2.02 | [5 empty] | Foundations & Footings | Lot | LS | 1 |  | 0 |  | Per m²/m³ complete | Payment upon concrete placed, cured, stripped and accepted (test results compliant)
A | 2 | 07 | A207 | 02 | 1 | 76 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Ground Floor Slab |  | A2.07.02 | SOW 3.8.1 | Cl 7, 30 | A-300001 | S2.01, S2.02 | [5 empty] | Ground Floor Slab | m² | LS |  |  | 0 |  | Per m²/m³ complete | Payment upon concrete placed, cured, stripped and accepted (test results compliant)
A | 2 | 07 | A207 | 03 | 1 | 77 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Suspended Floor Structure |  | A2.07.03 | SOW 3.8.2 | Cl 7, 30 | A-300001 | S3.01, S3.02, S3.03 | [5 empty] | Suspended Floor Structure | m² | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 07 | A207 | 04 | 1 | 78 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Structural Steel Framing |  | A2.07.04 | SOW 3.8.3 | Cl 7, 30 | A-300001 | S3.01, S5.01, S5.02 | [5 empty] | Structural Steel Framing | Lot | LS | 1 |  | 0 |  | Per tonne / % complete | Payment per tonne erected or % framing complete, bolted/welded and inspected
A | 2 | 07 | A207 | 05 | 1 | 79 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Roof Framing |  | A2.07.05 | SOW 3.8.4 | Cl 7, 30 | A-200002, A-300003 | S4.01, S4.02, S6.01 to S6.03 | [5 empty] | Roof Framing | Lot | LS | 1 |  | 0 |  | Per tonne / % complete | Payment per tonne erected or % framing complete, bolted/welded and inspected
A | 2 | 07 | A207 | 06 | 1 | 80 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Roof Sheeting & Insulation |  | A2.07.06 | SOW 3.8.4 | Cl 7, 30 | A-200002, A-720007 | [6 empty] | Roof Sheeting & Insulation | m² | LS |  |  | 0 |  | Per m² complete | Payment per m² roofing installed, flashed and water-tested
A | 2 | 07 | A207 | 07 | 1 | 81 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Roof Flashings, Gutters & Downpipes |  | A2.07.07 | SOW 3.8.5 | Cl 7, 30 | A-720007 |  |  |  |  | H1001 |  | Roof Flashings, Gutters & Downpipes | Lm | LS |  |  | 0 |  | Per m² complete | Payment per m² roofing installed, flashed and water-tested
A | 2 | 07 | A207 | 08 | 1 | 82 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | External Cladding System |  | A2.07.08 | SOW 3.8.6 | Cl 7, 30 | A-400001 to A-400004, A-760001 | [6 empty] | External Cladding System | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² cladding installed, sealed and accepted
A | 2 | 07 | A207 | 09 | 1 | 83 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | External Windows |  | A2.07.09 | SOW 3.8.7 | Cl 7, 30 | A-400001 to A-400004, A-730001 | [6 empty] | External Windows | No. | LS |  |  | 0 |  | Per unit installed | Payment per window/door installed, sealed, hardware complete and operational
A | 2 | 07 | A207 | 10 | 1 | 84 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | External Glazed Doors |  | A2.07.10 | SOW 3.8.7 | Cl 7, 30 | A-730001 | [6 empty] | External Glazed Doors | No. | LS |  |  | 0 |  | Per unit installed | Payment per window/door installed, sealed, hardware complete and operational
A | 2 | 07 | A207 | 11 | 1 | 85 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Courtyard Glazing System |  | A2.07.11 | SOW 3.8.7 | Cl 7, 30 | A-400101, A-410010, A-410011, A-710005 | [6 empty] | Courtyard Glazing System | Lot | LS | 1 |  | 0 |  | Per unit installed | Payment per window/door installed, sealed, hardware complete and operational
A | 2 | 07 | A207 | 12 | 1 | 86 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Entry Walkway Structure |  | A2.07.12 | SOW 3.8.8 | Cl 7, 30 | A-500002 | S1.03 | [5 empty] | Entry Walkway Structure | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 07 | A207 | 13 | 1 | 87 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | External Stairs |  | A2.07.13 | SOW 3.8.8 | Cl 7, 30 | A-500001 | [6 empty] | External Stairs | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 07 | A207 | 14 | 1 | 88 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Mechanical Plant Enclosure |  | A2.07.14 | SOW 3.8.9 | Cl 7, 30 | A-800001 |  |  | M1010 |  |  |  | Mechanical Plant Enclosure | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 07 | A207 | 15 | 1 | 89 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Generator Area Slab |  | A2.07.15 | SOW 3.8.9 | Cl 7, 30 |  | S8.01 |  |  | E8000 |  |  | Generator Area Slab | m² | LS |  |  | 0 |  | Per m²/m³ complete | Payment upon concrete placed, cured, stripped and accepted (test results compliant)
A | 2 | 07 | A207 | 16 | 1 | 90 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | BUILDING STRUCTURE & ENVELOPE | Weatherproofing & Sealing |  | A2.07.16 | SOW 3.8.10 | Cl 7, 30 | A-720001 to A-720007 | [6 empty] | Weatherproofing & Sealing | Lot | LS | 1 |  | 0 |  | Per m² complete | Payment per m² roofing installed, flashed and water-tested
A | 2 | 08 | A208 | 00 | 0 | 90 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) |  |  | A2.08 | SOW 3.9 | Cl 7, 30 | [7 empty] | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) |  |  |  |  | 0
A | 2 | 08 | A208 | 01 | 1 | 91 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Internal Partitions - Standard |  | A2.08.01 | SOW 3.9.1 | Cl 7, 30 | A-220001, A-220002, A-710010 | [6 empty] | Internal Partitions - Standard | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² framed, lined, finished and accepted
A | 2 | 08 | A208 | 02 | 1 | 92 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Internal Partitions - Acoustic Rated |  | A2.08.02 | SOW 3.9.1 | Cl 7, 30 | A-220001, A-220002, A-710010 | [6 empty] | Internal Partitions - Acoustic Rated | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² framed, lined, finished and accepted
A | 2 | 08 | A208 | 03 | 1 | 93 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Internal Glazed Partitions |  | A2.08.03 | SOW 3.9.1 | Cl 7, 30 | A-220001, A-220002, A-710010 | [6 empty] | Internal Glazed Partitions | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² framed, lined, finished and accepted
A | 2 | 08 | A208 | 04 | 1 | 94 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Wall Linings & Insulation |  | A2.08.04 | SOW 3.9.2 | Cl 7, 30 | A-220001, A-220002 | [6 empty] | Wall Linings & Insulation | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² framed, lined, finished and accepted
A | 2 | 08 | A208 | 05 | 1 | 95 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Suspended Ceilings |  | A2.08.05 | SOW 3.9.3 | Cl 7, 30 | A-210001, A-720012 | [6 empty] | Suspended Ceilings | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² ceiling grid and tiles/panels installed and accepted
A | 2 | 08 | A208 | 06 | 1 | 96 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Ceiling Battens |  | A2.08.06 | SOW 3.9.8 | Cl 7, 30 | A-730002 | [6 empty] | Ceiling Battens | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² ceiling grid and tiles/panels installed and accepted
A | 2 | 08 | A208 | 07 | 1 | 97 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Ceiling Bulkheads |  | A2.08.07 | SOW 3.9 | Cl 7, 30 | A-200001 | [6 empty] | Ceiling Bulkheads | Lm | LS |  |  | 0 |  | Per m² installed | Payment per m² ceiling grid and tiles/panels installed and accepted
A | 2 | 08 | A208 | 08 | 1 | 98 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Access Panels |  | A2.08.08 | SOW 3.9.3 | Cl 7, 30 | A-210001 | [6 empty] | Access Panels | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 09 | 1 | 99 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Internal Doors - Solid Core |  | A2.08.09 | SOW 3.9.4 | Cl 7, 30 | A-730001 | [6 empty] | Internal Doors - Solid Core | No. | LS |  |  | 0 |  | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
A | 2 | 08 | A208 | 10 | 1 | 100 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Internal Doors - Glazed |  | A2.08.10 | SOW 3.9.4 | Cl 7, 30 | A-730001 | [6 empty] | Internal Doors - Glazed | No. | LS |  |  | 0 |  | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
A | 2 | 08 | A208 | 11 | 1 | 101 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Acoustic Sliding Doors |  | A2.08.11 | SOW 3.9.1 | Cl 7, 30 | A-220001, A-720011 | [6 empty] | Acoustic Sliding Doors | No. | LS |  |  | 0 |  | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
A | 2 | 08 | A208 | 12 | 1 | 102 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Door Hardware |  | A2.08.12 | SOW 3.9.5 | Cl 7, 30 | A-730001 | [6 empty] | Door Hardware | Lot | LS | 1 |  | 0 |  | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
A | 2 | 08 | A208 | 13 | 1 | 103 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Turnstile |  | A2.08.13 | SOW 3.9.7 | Cl 7, 30 | A-230001 | [6 empty] | Turnstile | No. | LS |  |  | 0 |  | Per m² installed | Payment per m² flooring installed, adhesive cured, accepted
A | 2 | 08 | A208 | 14 | 1 | 104 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Floor Finishes - Carpet/Vinyl |  | A2.08.14 | SOW 3.9.7 | Cl 7, 30 | A-230001, A-720010 | [6 empty] | Floor Finishes - Carpet/Vinyl | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² flooring installed, adhesive cured, accepted
A | 2 | 08 | A208 | 15 | 1 | 105 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Floor Finishes - Wet Areas |  | A2.08.15 | SOW 3.9.7 | Cl 7, 30 | A-230001, A-720010 | [6 empty] | Floor Finishes - Wet Areas | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² flooring installed, adhesive cured, accepted
A | 2 | 08 | A208 | 16 | 1 | 106 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Wall Finishes & Painting |  | A2.08.16 | SOW 3.9.8 | Cl 7, 30 | A-600001 to A-600017 | [6 empty] | Wall Finishes & Painting | m² | LS |  |  | 0 |  | Per m² installed | Payment per m² framed, lined, finished and accepted
A | 2 | 08 | A208 | 17 | 1 | 107 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Skirtings & Trims |  | A2.08.17 | SOW 3.9.8 | Cl 7, 30 | A-730002 | [6 empty] | Skirtings & Trims | Lm | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 18 | 1 | 108 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Kitchen Joinery (JO-BW-1, JO-BW-2) |  | A2.08.18 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | Kitchen Joinery (JO-BW-1, JO-BW-2) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 19 | 1 | 109 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Boardroom Joinery (JO-BW-3) |  | A2.08.19 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | Boardroom Joinery (JO-BW-3) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 20 | 1 | 110 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Health Room Joinery (JO-BW-4) |  | A2.08.20 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | Health Room Joinery (JO-BW-4) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 21 | 1 | 111 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Training Kitchen Joinery (JO-BW-5) |  | A2.08.21 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | Training Kitchen Joinery (JO-BW-5) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 22 | 1 | 112 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | First Aid Joinery (JO-BW-6) |  | A2.08.22 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | First Aid Joinery (JO-BW-6) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 23 | 1 | 113 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Covered Outdoor Joinery (JO-BW-7, JO-ST-1, JO-SE-1) |  | A2.08.23 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | Covered Outdoor Joinery (JO-BW-7, JO-ST-1, JO-SE-1) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 24 | 1 | 114 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Amenities Joinery (JO-BW-8, JO-BW-9) |  | A2.08.24 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [6 empty] | Amenities Joinery (JO-BW-8, JO-BW-9) | Lot | LS | 1 |  | 0 |  | Per item installed | Payment per joinery item installed, services connected, accepted
A | 2 | 08 | A208 | 25 | 1 | 115 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Smart Lockers (JO-LKR-1) |  | A2.08.25 | SOW 3.9.10 | Cl 7, 30 | A-780011 | [6 empty] | Smart Lockers (JO-LKR-1) | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 26 | 1 | 116 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Display Boards (JO-BD-1 to JO-BD-5) |  | A2.08.26 | SOW 3.9.12 | Cl 7, 30 | A-780002, A-780003 | [6 empty] | Display Boards (JO-BD-1 to JO-BD-5) | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 27 | 1 | 117 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Kitchen Storage (JO-ST-2, JO-ST-3) |  | A2.08.27 | SOW 3.9 | Cl 7, 30 | A-200001 | [6 empty] | Kitchen Storage (JO-ST-2, JO-ST-3) | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 28 | 1 | 118 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Male Amenities Fit-out |  | A2.08.28 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H6000, H6001 |  | Male Amenities Fit-out | Lot | LS | 1 |  | 0 |  | Per room complete | Payment per wet area complete including fixtures, fittings and finishes
A | 2 | 08 | A208 | 29 | 1 | 119 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Female Amenities Fit-out |  | A2.08.29 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H6000, H6001 |  | Female Amenities Fit-out | Lot | LS | 1 |  | 0 |  | Per room complete | Payment per wet area complete including fixtures, fittings and finishes
A | 2 | 08 | A208 | 30 | 1 | 120 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | PWD Amenities Fit-out |  | A2.08.30 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H6000, H6001 |  | PWD Amenities Fit-out | Lot | LS | 1 |  | 0 |  | Per room complete | Payment per wet area complete including fixtures, fittings and finishes
A | 2 | 08 | A208 | 31 | 1 | 121 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Shower Room Fit-out |  | A2.08.31 | SOW 3.9.10 | Cl 7, 30 | A-620001 |  |  |  |  | H6000, H6001 |  | Shower Room Fit-out | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 32 | 1 | 122 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Sanitary Fixtures & Accessories |  | A2.08.32 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H0003 |  | Sanitary Fixtures & Accessories | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 33 | 1 | 123 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Acoustic Treatments |  | A2.08.33 | SOW 3.9.1 | Cl 7, 30 | A-220001, A-720011 | [6 empty] | Acoustic Treatments | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 08 | A208 | 34 | 1 | 124 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Signage |  | A2.08.34 | SOW 3.9.11 | Cl 7, 30 | A-770001 | [6 empty] | Signage | No. | LS |  |  | 0 |  | Per sign installed | Payment per sign fabricated, installed and accepted
A | 2 | 08 | A208 | 35 | 1 | 125 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | Window Coverings / Blinds |  | A2.08.35 | SOW 3.9.13 | Cl 7, 30 | A-720012 | [6 empty] | Window Coverings / Blinds | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
A | 2 | 09 | A209 | 00 | 0 | 125 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES |  |  | A2.09 | SOW 3.10 | Cl 7, 30 | [7 empty] | MECHANICAL SERVICES |  |  |  |  | 0
A | 2 | 09 | A209 | 01 | 1 | 126 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | AC Equipment Supply & Install |  | A2.09.01 | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  | AC Equipment Supply & Install | No. | LS |  |  | 0 |  | Per unit installed | Payment per unit installed, connected, pre-commissioned
A | 2 | 09 | A209 | 02 | 1 | 127 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Ductwork Installation |  | A2.09.02 | SOW 3.10.2 | Cl 7, 30 |  |  |  | M1000, M2000 |  |  |  | Ductwork Installation | Lm | LS |  |  | 0 |  | % complete measured monthly | Payment based on % ductwork installed, pressure tested and accepted
A | 2 | 09 | A209 | 03 | 1 | 128 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Diffusers & Grilles |  | A2.09.03 | SOW 3.10.2 | Cl 7, 30 |  |  |  | M0001 |  |  |  | Diffusers & Grilles | No. | LS |  |  | 0 |  | Per item installed | Payment per grille/diffuser installed and balanced
A | 2 | 09 | A209 | 04 | 1 | 129 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Kitchen Exhaust System |  | A2.09.04 | SOW 3.10.3 | Cl 7, 30 |  |  |  | M1000 |  |  |  | Kitchen Exhaust System | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Services Engineer
A | 2 | 09 | A209 | 05 | 1 | 130 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Amenities Exhaust System |  | A2.09.05 | SOW 3.10.3 | Cl 7, 30 |  |  |  | M1000 |  |  |  | Amenities Exhaust System | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Services Engineer
A | 2 | 09 | A209 | 06 | 1 | 131 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Mechanical Controls & BMS Interface |  | A2.09.06 | SOW 3.10.4 | Cl 7, 30 |  |  |  | M0001 | E2000 |  |  | Mechanical Controls & BMS Interface | Lot | LS | 1 |  | 0 |  | Milestone | 50% controllers installed, 50% BMS programmed and operational
A | 2 | 09 | A209 | 07 | 1 | 132 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Piping, Valves & Supports |  | A2.09.07 | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  | Piping, Valves & Supports | Lm | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Services Engineer
A | 2 | 09 | A209 | 08 | 1 | 133 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Mechanical Insulation |  | A2.09.08 | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  | Mechanical Insulation | m² | LS |  |  | 0 |  | Per m²/Lm installed | Payment per insulation installed to specified thickness
A | 2 | 09 | A209 | 09 | 1 | 134 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Comms Room AC (AC-COMMS) |  | A2.09.09 | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  | Comms Room AC (AC-COMMS) | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Services Engineer
A | 2 | 09 | A209 | 10 | 1 | 135 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | MECHANICAL SERVICES | Mechanical Testing & Commissioning |  | A2.09.10 | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  | Mechanical Testing & Commissioning | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon commissioning complete, reports accepted
A | 2 | 10 | A210 | 00 | 0 | 135 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES |  |  | A2.10 | [9 empty] | ELECTRICAL SERVICES |  |  |  |  | 0
A | 2 | 10 | A210 | 01 | 1 | 136 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Main Switchboard & Distribution |  | A2.10.01 | SOW 3.11.1 | Cl 7, 30 |  |  |  |  | E8000, E8001 |  |  | Main Switchboard & Distribution | No. | LS |  |  | 0 |  | Per board installed | Payment per switchboard installed, connected, tested and labelled
A | 2 | 10 | A210 | 02 | 1 | 137 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Sub-Distribution & Circuits |  | A2.10.02 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  | Sub-Distribution & Circuits | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Services Engineer
A | 2 | 10 | A210 | 03 | 1 | 138 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | General Power Outlets |  | A2.10.03 | SOW 3.11.5 | Cl 7, 30 |  |  |  |  | E2000, E2001 |  |  | General Power Outlets | No. | LS |  |  | 0 |  | Per point installed | Payment per GPO/outlet installed, tested and labelled
A | 2 | 10 | A210 | 04 | 1 | 139 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Lighting - Internal |  | A2.10.04 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  | Lighting - Internal | No. | LS |  |  | 0 |  | Per fitting installed | Payment per luminaire installed, connected and operational
A | 2 | 10 | A210 | 05 | 1 | 140 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Lighting - External |  | A2.10.05 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  | Lighting - External | No. | LS |  |  | 0 |  | Per fitting installed | Payment per luminaire installed, connected and operational
A | 2 | 10 | A210 | 06 | 1 | 141 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Emergency Lighting & Exit Signs |  | A2.10.06 | SOW 3.11.4 | Cl 7, 30 |  |  |  |  | E1000 |  |  | Emergency Lighting & Exit Signs | No. | LS |  |  | 0 |  | Per fitting installed | Payment per luminaire installed, connected and operational
A | 2 | 10 | A210 | 07 | 1 | 142 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Lightning Protection & Earthing |  | A2.10.07 | SOW 3.11.9 | Cl 7, 30 |  |  |  |  | E8000 |  |  | Lightning Protection & Earthing | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Services Engineer
A | 2 | 10 | A210 | 08 | 1 | 143 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Data & Communications Cabling |  | A2.10.08 | SOW 3.11.6 | Cl 7, 30 |  |  |  |  | E2000 |  |  | Data & Communications Cabling | Lm | LS |  |  | 0 |  | Per point installed | Payment per data point installed, terminated and tested
A | 2 | 10 | A210 | 09 | 1 | 144 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Security Systems Infrastructure |  | A2.10.09 | SOW 3.11.7 | Cl 7, 30 |  |  |  |  | E2000 |  |  | Security Systems Infrastructure | Lot | LS | 1 |  | 0 |  | Per device installed | Payment per security device installed and operational
A | 2 | 10 | A210 | 10 | 1 | 145 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Access Control & CCTV |  | A2.10.10 | SOW 3.11.7 | Cl 7, 30 |  |  |  |  | E2000 |  |  | Access Control & CCTV | Lot | LS | 1 |  | 0 |  | Per device installed | Payment per security device installed and operational
A | 2 | 10 | A210 | 11 | 1 | 146 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Fire Detection & Alarm System |  | A2.10.11 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  | Fire Detection & Alarm System | Lot | LS | 1 |  | 0 |  | Per device installed | Payment per device installed, connected to FACP and tested
A | 2 | 10 | A210 | 12 | 1 | 147 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | ELECTRICAL SERVICES | Electrical Testing & Commissioning |  | A2.10.12 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  | Electrical Testing & Commissioning | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon commissioning complete, test certificates issued
A | 2 | 11 | A211 | 00 | 0 | 147 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES |  |  | A2.11 | SOW 3.12 | Cl 7, 30 | [7 empty] | HYDRAULIC SERVICES |  |  |  |  | 0
A | 2 | 11 | A211 | 01 | 1 | 148 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Cold Water Reticulation |  | A2.11.01 | SOW 3.12.1 | Cl 7, 30 | [5 empty] | H2000, H6001 |  | Cold Water Reticulation | Lm | LS |  |  | 0 |  | Per linear metre installed | Payment per Lm water pipe installed, pressure tested, chlorinated
A | 2 | 11 | A211 | 02 | 1 | 149 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Hot Water Systems |  | A2.11.02 | SOW 3.12.2 | Cl 7, 30 | [5 empty] | H0003, H6001 |  | Hot Water Systems | No. | LS |  |  | 0 |  | Per linear metre installed | Payment per Lm water pipe installed, pressure tested, chlorinated
A | 2 | 11 | A211 | 03 | 1 | 150 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Sanitary Plumbing |  | A2.11.03 | SOW 3.12.3 | Cl 7, 30 | [5 empty] | H1000, H6000 |  | Sanitary Plumbing | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Hydraulic Engineer
A | 2 | 11 | A211 | 04 | 1 | 151 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Sanitary Drainage |  | A2.11.04 | SOW 3.12.3 | Cl 7, 30 | [5 empty] | H1000, H6000 |  | Sanitary Drainage | Lm | LS |  |  | 0 |  | Per linear metre installed | Payment per Lm drainage installed, tested (air/water) and accepted
A | 2 | 11 | A211 | 05 | 1 | 152 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Roof Drainage |  | A2.11.05 | SOW 3.12.3 | Cl 7, 30 | [5 empty] | H1000, H6000 |  | Roof Drainage | Lm | LS |  |  | 0 |  | Per linear metre installed | Payment per Lm drainage installed, tested (air/water) and accepted
A | 2 | 11 | A211 | 06 | 1 | 153 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Backflow Prevention |  | A2.11.06 | SOW 3.12.6 | Cl 7, 30 | [5 empty] | H0003, H8000 |  | Backflow Prevention | No. | LS |  |  | 0 |  | Per device installed | Payment per backflow device installed, tested and registered
A | 2 | 11 | A211 | 07 | 1 | 154 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Hydraulic Penetrations & Supports |  | A2.11.07 | SOW 3.12 | Cl 7, 30 | [5 empty] | H0000 to H9000 |  | Hydraulic Penetrations & Supports | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Hydraulic Engineer
A | 2 | 11 | A211 | 08 | 1 | 155 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Hydraulic Testing & Certification |  | A2.11.08 | SOW 3.12 | Cl 7, 30 | [5 empty] | H0000 to H9000 |  | Hydraulic Testing & Certification | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon commissioning complete, test certificates issued
A | 2 | 11 | A211 | 09 | 1 | 156 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | HYDRAULIC SERVICES | Authority Inspections - Plumbing |  | A2.11.09 | SOW 3.12 | Cl 7, 30 | [5 empty] | H0000 to H9000 |  | Authority Inspections - Plumbing | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Hydraulic Engineer
A | 2 | 12 | A212 | 00 | 0 | 156 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | FIRE SERVICES |  |  | A2.12 | SOW 3.13 | Cl 7, 30 | [7 empty] | FIRE SERVICES |  |  |  |  | 0
A | 2 | 12 | A212 | 01 | 1 | 157 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | FIRE SERVICES | Fire Hydrant System |  | A2.12.01 | SOW 3.13.2 | Cl 7, 30 | [5 empty] | H2000, H4000 |  | Fire Hydrant System | Lot | LS | 1 |  | 0 |  | Per outlet installed | Payment per hydrant/hose reel installed, flow tested
A | 2 | 12 | A212 | 02 | 1 | 158 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | FIRE SERVICES | Fire Hose Reels |  | A2.12.02 | SOW 3.13.2 | Cl 7, 30 | [5 empty] | H2000, H4000 |  | Fire Hose Reels | No. | LS |  |  | 0 |  | Per outlet installed | Payment per hydrant/hose reel installed, flow tested
A | 2 | 12 | A212 | 03 | 1 | 159 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | FIRE SERVICES | Fire Indicator Panel (FIP) |  | A2.12.03 | SOW 3.13.1 | Cl 7, 30 |  |  |  |  | E1000, E8000 |  |  | Fire Indicator Panel (FIP) | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % complete verified by Fire Engineer
A | 2 | 12 | A212 | 04 | 1 | 160 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | FIRE SERVICES | Fire Services Testing & Certification |  | A2.12.04 | SOW 3.13 | Cl 7, 30 | [7 empty] | Fire Services Testing & Certification | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon fire system commissioning and Form 65/compliance certificate issued
A | 2 | 13 | A213 | 00 | 0 | 160 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER |  |  | A2.13 | SOW 11.0 | Cl 30, 42 | [7 empty] | TESTING, COMMISSIONING & HANDOVER |  |  |  |  | 0
A | 2 | 13 | A213 | 01 | 1 | 161 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Commissioning Plan Development |  | A2.13.01 | SOW 11.0 | Cl 30, 42 | [7 empty] | Commissioning Plan Development | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 02 | 1 | 162 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Pre-Commissioning Checklists |  | A2.13.02 | SOW 11.0 | Cl 30, 42 | [7 empty] | Pre-Commissioning Checklists | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon IST complete and report accepted
A | 2 | 13 | A213 | 03 | 1 | 163 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Mechanical Testing & Balancing |  | A2.13.03 | SOW 11.1 | Cl 30 |  |  |  | M0001 |  |  |  | Mechanical Testing & Balancing | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 04 | 1 | 164 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Electrical Testing |  | A2.13.04 | SOW 11.1 | Cl 30 |  |  |  |  | E0001 |  |  | Electrical Testing | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 05 | 1 | 165 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Hydraulic Pressure Testing |  | A2.13.05 | SOW 11.1 | Cl 30 | [5 empty] | H0002 |  | Hydraulic Pressure Testing | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 06 | 1 | 166 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Fire Systems Testing |  | A2.13.06 | SOW 11.1 | Cl 30 |  |  |  |  | E1000 | H4000 |  | Fire Systems Testing | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 07 | 1 | 167 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Integrated Systems Testing |  | A2.13.07 | SOW 11.1 | Cl 30 | [7 empty] | Integrated Systems Testing | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon IST complete and report accepted
A | 2 | 13 | A213 | 08 | 1 | 168 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | O&M Manuals |  | A2.13.08 | SOW 11.3 | Cl 8, 30.6 | [7 empty] | O&M Manuals | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon O&M manuals submitted and accepted
A | 2 | 13 | A213 | 09 | 1 | 169 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Warranties & Guarantees |  | A2.13.09 | SOW 11.0 | Cl 30, 42 | [7 empty] | Warranties & Guarantees | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 10 | 1 | 170 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Asset Registers |  | A2.13.10 | SOW 11.0 | Cl 30, 42 | [7 empty] | Asset Registers | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon IST complete and report accepted
A | 2 | 13 | A213 | 11 | 1 | 171 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Training Delivery |  | A2.13.11 | SOW 11.2 | Cl 30.6 | [7 empty] | Training Delivery | Lot | LS | 1 |  | 0 |  | Per session conducted | Payment per training session completed with attendance records
A | 2 | 13 | A213 | 12 | 1 | 172 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | Final MDR Compilation |  | A2.13.12 | SOW 11.0 | Cl 30, 42 | [7 empty] | Final MDR Compilation | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon testing/commissioning activity complete and accepted
A | 2 | 13 | A213 | 13 | 1 | 173 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | TESTING, COMMISSIONING & HANDOVER | PC Inspections & Punch List |  | A2.13.13 | SOW 11.0 | Cl 30, 42 | [7 empty] | PC Inspections & Punch List | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon IST complete and report accepted
A | 2 | 14 | A214 | 00 | 0 | 173 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING |  |  | A2.14 | SOW 3.14 | Cl 7, 30 | [7 empty] | LANDSCAPING |  |  |  |  | 0
A | 2 | 14 | A214 | 01 | 1 | 174 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Site Preparation for Landscaping |  | A2.14.01 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Site Preparation for Landscaping | Lot | LS | 1 |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 02 | 1 | 175 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Trees Supply & Plant |  | A2.14.02 | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.01, L2.01 to L2.04 | Trees Supply & Plant | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 03 | 1 | 176 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Shrubs Supply & Plant |  | A2.14.03 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Shrubs Supply & Plant | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 04 | 1 | 177 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Ground Cover Supply & Plant |  | A2.14.04 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Ground Cover Supply & Plant | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 05 | 1 | 178 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Turf Supply & Install |  | A2.14.05 | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.01, L0.02 | Turf Supply & Install | m² | LS |  |  | 0 |  | Per m² / per plant | Payment per m² turf laid / per plant installed as per landscape plan
A | 2 | 14 | A214 | 06 | 1 | 179 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Mulching |  | A2.14.06 | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.02 | Mulching | m² | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 07 | 1 | 180 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Garden Edging |  | A2.14.07 | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.01, L2.01 to L2.05 | Garden Edging | Lm | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 08 | 1 | 181 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Gravel Areas |  | A2.14.08 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Gravel Areas | m² | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 09 | 1 | 182 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Boulder Features |  | A2.14.09 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Boulder Features | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 10 | 1 | 183 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Landscape Seating |  | A2.14.10 | SOW 3.14.5 | Cl 7, 30 | [6 empty] | L0.02, L0.03 | Landscape Seating | No. | LS |  |  | 0 |  | Per item installed | Payment per landscape furniture item installed and accepted
A | 2 | 14 | A214 | 11 | 1 | 184 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Water Features |  | A2.14.11 | SOW 3.14.6 | Cl 7, 30 | [6 empty] | L0.02, L0.03, L3.01 to L3.03 | Water Features | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 12 | 1 | 185 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Artwork Installation |  | A2.14.12 | SOW 3.14.7 | Cl 7, 30 | [6 empty] | L0.02, L0.03 | Artwork Installation | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 13 | 1 | 186 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Irrigation System |  | A2.14.13 | SOW 3.14.3 | Cl 7, 30 | [5 empty] | H0003 | L1.01 to L1.04 | Irrigation System | Lot | LS | 1 |  | 0 |  | Lump sum on completion | 100% upon irrigation system installed, tested and operational
A | 2 | 14 | A214 | 14 | 1 | 187 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Landscape Lighting |  | A2.14.14 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Landscape Lighting | No. | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 15 | 1 | 188 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Courtyard Landscaping |  | A2.14.15 | SOW 3.14.4 | Cl 7, 30 | A-710005 | [5 empty] | L1.05, L2.05 | Courtyard Landscaping | m² | LS |  |  | 0 |  | % complete measured monthly | Payment based on % landscaping complete verified by inspection
A | 2 | 14 | A214 | 16 | 1 | 189 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | LANDSCAPING | Landscape Establishment & Maintenance |  | A2.14.16 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 | Landscape Establishment & Maintenance | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Monthly payment during establishment period subject to plant health
A | 2 | 15 | A215 | 00 | 0 | 189 | 00 | 3 | Section A - Lump Sum | DIRECT COSTS | DEMOBILISATION & CLOSE-OUT |  |  | A2.15 | SOW 12.0 | Cl 42 | [7 empty] | DEMOBILISATION & CLOSE-OUT |  |  |  |  | 0
A | 2 | 15 | A215 | 01 | 1 | 190 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOBILISATION & CLOSE-OUT | Temporary Works Removal |  | A2.15.01 | SOW 12.1 | Cl 42 | [7 empty] | Temporary Works Removal | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon mobilisation item complete and accepted
A | 2 | 15 | A215 | 02 | 1 | 191 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOBILISATION & CLOSE-OUT | Site Reinstatement |  | A2.15.02 | SOW 12.3 | Cl 42 | [7 empty] | Site Reinstatement | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon mobilisation item complete and accepted
A | 2 | 15 | A215 | 03 | 1 | 192 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOBILISATION & CLOSE-OUT | Final Cleaning |  | A2.15.03 | SOW 12.2 | Cl 12.3, 42 | [7 empty] | Final Cleaning | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon mobilisation item complete and accepted
A | 2 | 15 | A215 | 04 | 1 | 193 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOBILISATION & CLOSE-OUT | As-Built Documentation |  | A2.15.04 | SOW 12.4 | Cl 8, 42 | [7 empty] | As-Built Documentation | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon mobilisation item complete and accepted
A | 2 | 15 | A215 | 05 | 1 | 194 | 00 | 4 | Section A - Lump Sum | DIRECT COSTS | DEMOBILISATION & CLOSE-OUT | Defects Rectification Support |  | A2.15.05 | SOW 12.0 | Cl 42 | [7 empty] | Defects Rectification Support | Lot | LS | 1 |  | 0 |  | Milestone | 100% upon mobilisation item complete and accepted
PS | 0 | 0 | PS00 | 03 | 0 | 194 | 00 | 1 | Section B - Provisional Sum Items |  |  |  |  | PS | [9 empty] | Section B - Provisional Sum Items |  |  |  |  | 0
PS | 1 | 0 | PS10 | 04 | 0 | 194 | 00 | 2 | Section B - Provisional Sum Items | PROVISIONAL SUMS |  |  |  | PS1 | [9 empty] | PROVISIONAL SUMS |  |  |  |  | 0
PS | 1 | 0 | PS10 | 05 | 0 | 194 | 00 | 3 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SITE CONDITIONS |  |  | PS1.0 | SOW 3.7.1 | Cl 26, 27, 36 | [7 empty] | SITE CONDITIONS |  |  |  |  | 0
PS | 1 | 0 | PS10 | 06 | 1 | 195 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SITE CONDITIONS | Latent Conditions Allowance |  | PS1.0.06 | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 |  |  |  |  | Latent Conditions Allowance | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 07 | 1 | 196 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SITE CONDITIONS | Rock Excavation Allowance |  | PS1.0.07 | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 |  |  |  |  | Rock Excavation Allowance | m³ | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 08 | 1 | 197 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SITE CONDITIONS | Contaminated Soil Allowance |  | PS1.0.08 | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 |  |  |  |  | Contaminated Soil Allowance | m³ | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 09 | 0 | 197 | 00 | 3 | Section B - Provisional Sum Items | PROVISIONAL SUMS | HAZMAT |  |  | PS1.0 | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 |  |  |  |  | HAZMAT |  |  |  |  | 0
PS | 1 | 0 | PS10 | 10 | 1 | 198 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | HAZMAT | Additional Asbestos Removal |  | PS1.0.10 | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 |  |  |  |  | Additional Asbestos Removal | m² | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 11 | 1 | 199 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | HAZMAT | Lead Paint Removal |  | PS1.0.11 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 | [7 empty] | Lead Paint Removal | m² | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 12 | 1 | 200 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | HAZMAT | Synthetic Mineral Fibre Removal |  | PS1.0.12 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 |  |  |  |  | Synthetic Mineral Fibre Removal | m² | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 13 | 0 | 200 | 00 | 3 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SERVICES |  |  | PS1.0 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 |  |  |  |  | SERVICES |  |  |  |  | 0
PS | 1 | 0 | PS10 | 14 | 1 | 201 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SERVICES | Electrical Services Diversion |  | PS1.0.14 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 |  |  |  |  | Electrical Services Diversion | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 15 | 1 | 202 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SERVICES | Hydraulic Services Diversion |  | PS1.0.15 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 |  |  |  |  | Hydraulic Services Diversion | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 16 | 1 | 203 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | SERVICES | Communications/Data Diversion |  | PS1.0.16 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 |  |  |  |  | Communications/Data Diversion | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 17 | 0 | 203 | 00 | 3 | Section B - Provisional Sum Items | PROVISIONAL SUMS | DESIGN |  |  | PS1.0 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 |  |  |  |  | DESIGN |  |  |  |  | 0
PS | 1 | 0 | PS10 | 18 | 1 | 204 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | DESIGN | Architectural Design Development |  | PS1.0.18 | SOW 3.0 | Cl 26, 27 | [7 empty] | Architectural Design Development | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 19 | 1 | 205 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | DESIGN | Structural Design Development |  | PS1.0.19 | SOW 3.0 | Cl 26, 27 | [7 empty] | Structural Design Development | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 20 | 1 | 206 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | DESIGN | Services Design Development |  | PS1.0.20 | SOW 3.0 | Cl 26, 27 | [7 empty] | Services Design Development | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 21 | 0 | 206 | 00 | 3 | Section B - Provisional Sum Items | PROVISIONAL SUMS | CONTINGENCY |  |  | PS1.0 | SOW 3.0 | Cl 26, 27 | [7 empty] | CONTINGENCY |  |  |  |  | 0
PS | 1 | 0 | PS10 | 22 | 1 | 207 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | CONTINGENCY | General Contingency Allowance |  | PS1.0.22 | SOW 3.0 | Cl 26, 27 | [7 empty] | General Contingency Allowance | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 23 | 1 | 208 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | CONTINGENCY | Interface Coordination Allowance |  | PS1.0.23 | SOW 3.0 | Cl 26, 27 | [7 empty] | Interface Coordination Allowance | Lot | PS | 1 |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 24 | 1 | 209 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | CONTINGENCY | Inclement Weather Allowance |  | PS1.0.24 | SOW 3.0 | Cl 26, 27 | [7 empty] | Inclement Weather Allowance | Days | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 25 | 0 | 209 | 00 | 3 | Section B - Provisional Sum Items | PROVISIONAL SUMS | AV WORKS |  |  | PS1.0 | SOW 3.0 | Cl 36, 38, 41 | [7 empty] | AV WORKS |  |  |  |  | 0
PS | 1 | 0 | PS10 | 26 | 1 | 210 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | AV WORKS | AV Contractor Attendance |  | PS1.0.26 | SOW 3.0 | Cl 36, 38, 41 | [7 empty] | AV Contractor Attendance | Days | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
PS | 1 | 0 | PS10 | 27 | 1 | 211 | 00 | 4 | Section B - Provisional Sum Items | PROVISIONAL SUMS | AV WORKS | AV Power & Data Points |  | PS1.0.27 | SOW 3.0 | Cl 36, 38, 41 | [7 empty] | AV Power & Data Points | No. | PS |  |  | 0 |  | Percentage complete based | Per approved Variation
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Variation Table
RFT # 1221995761 - SPS New Project Building
VARIATION TABLE - DAYWORK RATES
Per AS4000-1997 Amended - Clause 36, 38, 41
⚠️ TENDERER: Enter rates in YELLOW highlighted columns (H-S). All rates exclusive of GST.
Cost Type | Category | Sub-Category | Item No. | Description | UOM | Pricing Type | Normal Rate | OT 1.5x | OT 2.0x | OT 2.5x | Allowances | Mob Rate | Demob Rate | Dry Hire | Wet Hire | Supply Rate | Install Rate | All-in Rate | Method of Measure | Rule of Credit | Min Charge | Increment | Valid From | Valid To | Notes
PERSONNEL |  |  | V1 | PERSONNEL DAYWORK RATES
PERSONNEL | Management |  | V1.01 | Project Director | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Senior oversight
PERSONNEL | Management |  | V1.02 | Project Manager | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Management |  | V1.03 | Site Manager / Superintendent | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Management |  | V1.04 | Construction Manager | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Management |  | V1.05 | Assistant Site Manager | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Engineering |  | V1.06 | Project Engineer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Engineering |  | V1.07 | Senior Engineer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Engineering |  | V1.08 | Graduate Engineer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Engineering |  | V1.09 | Design Engineer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Engineering |  | V1.10 | Services Engineer (Mech/Elec/Hyd) | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Supervision |  | V1.11 | Site Foreman / Supervisor | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Supervision |  | V1.12 | Leading Hand | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Supervision |  | V1.13 | Works Coordinator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Supervision |  | V1.14 | Night Shift Supervisor | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Shift loading included
PERSONNEL | Supervision |  | V1.15 | Subcontractor Coordinator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | HSE |  | V1.16 | HSE Manager | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | HSE |  | V1.17 | WHS Advisor / Safety Officer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | HSE |  | V1.18 | Environmental Officer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | HSE |  | V1.19 | Traffic Controller | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Licensed TC required
PERSONNEL | HSE |  | V1.20 | First Aid Officer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Current cert required
PERSONNEL | Quality |  | V1.21 | Quality Manager | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Quality |  | V1.22 | Quality Coordinator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Quality |  | V1.23 | Quality Inspector | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Administration |  | V1.24 | Document Controller | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Administration |  | V1.25 | Contract Administrator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Administration |  | V1.26 | Cost Controller / Estimator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Administration |  | V1.27 | Scheduler / Planner | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Administration |  | V1.28 | Project Administrator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.29 | Skilled Tradesperson (General) | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.30 | Electrician - A Grade | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Licensed required
PERSONNEL | Trades |  | V1.31 | Electrician - Apprentice | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Supervised
PERSONNEL | Trades |  | V1.32 | Plumber / Drainer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Licensed required
PERSONNEL | Trades |  | V1.33 | Plumber - Apprentice | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Supervised
PERSONNEL | Trades |  | V1.34 | Carpenter / Joiner | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.35 | Steel Fixer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.36 | Concreter | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.37 | Welder / Boilermaker | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Coded welder if reqd
PERSONNEL | Trades |  | V1.38 | Painter | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.39 | Tiler | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.40 | Plasterer / Renderer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.41 | Glazier | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.42 | Roofer / Metal Worker | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Trades |  | V1.43 | HVAC Technician | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | ARC licensed
PERSONNEL | Trades |  | V1.44 | Fire Services Technician | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Licensed required
PERSONNEL | Labour |  | V1.45 | General Labourer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Labour |  | V1.46 | Semi-Skilled Labourer | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Labour |  | V1.47 | Rigger / Dogman | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Ticket required
PERSONNEL | Labour |  | V1.48 | Scaffolder | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Ticket required
PERSONNEL | Labour |  | V1.49 | Cleaner | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Operators |  | V1.50 | Excavator Operator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Ticket required
PERSONNEL | Operators |  | V1.51 | Crane Operator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Ticket required
PERSONNEL | Operators |  | V1.52 | EWP Operator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Ticket required
PERSONNEL | Operators |  | V1.53 | Forklift Operator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr |  |  | Ticket required
PERSONNEL | Operators |  | V1.54 | Roller Operator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PERSONNEL | Operators |  | V1.55 | Bobcat / Skid Steer Operator | Day | Daywork | [12 empty] | Per day worked | Timesheet approved | 4 hrs | 1 hr
PLANT |  |  | V2 | PLANT & EQUIPMENT RATES
PLANT | Earthmoving |  | V2.01 | Excavator 1.5T Mini | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.02 | Excavator 5T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.03 | Excavator 8T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.04 | Excavator 14T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.05 | Excavator 20T+ | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.06 | Bobcat / Skid Steer Loader | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.07 | Backhoe | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.08 | Front End Loader | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.09 | Grader | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Earthmoving |  | V2.10 | Bulldozer D4-D6 | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Compaction |  | V2.11 | Smooth Drum Roller - Walk Behind | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Compaction |  | V2.12 | Smooth Drum Roller - Ride On | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Compaction |  | V2.13 | Padfoot Roller | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Compaction |  | V2.14 | Plate Compactor | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Compaction |  | V2.15 | Trench Rammer / Jumping Jack | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Cranes & Lifting |  | V2.16 | Franna Crane 12T | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Cranes & Lifting |  | V2.17 | Franna Crane 20T | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Cranes & Lifting |  | V2.18 | Mobile Crane 25T | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Cranes & Lifting |  | V2.19 | Mobile Crane 50T | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Cranes & Lifting |  | V2.20 | Mobile Crane 80T+ | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Cranes & Lifting |  | V2.21 | Telehandler 3T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Cranes & Lifting |  | V2.22 | Telehandler 4T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Cranes & Lifting |  | V2.23 | Forklift 2.5T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Cranes & Lifting |  | V2.24 | Forklift 4T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.25 | Scissor Lift - 19ft Electric | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.26 | Scissor Lift - 26ft Electric | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.27 | Scissor Lift - 32ft Rough Terrain | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.28 | Boom Lift - 40ft Knuckle | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.29 | Boom Lift - 60ft Knuckle | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.30 | Boom Lift - 80ft+ Straight | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.31 | Spider Lift | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | EWP & Access |  | V2.32 | Scaffolding - per m² | m² | Hire | [12 empty] | Per m² per week | Docket approved |  | Week |  |  | Erect/dismantle separate
PLANT | Trucks & Transport |  | V2.33 | Ute / Light Vehicle | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Trucks & Transport |  | V2.34 | Tipper Truck 6T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Trucks & Transport |  | V2.35 | Tipper Truck 10T | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Trucks & Transport |  | V2.36 | Tipper Truck - Semi | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Trucks & Transport |  | V2.37 | Water Cart 10,000L | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Trucks & Transport |  | V2.38 | Flat Top Truck | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Trucks & Transport |  | V2.39 | Low Loader / Float | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Concrete |  | V2.40 | Concrete Line Pump | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Concrete |  | V2.41 | Concrete Boom Pump | Day | Hire | [12 empty] | Per day hired | Docket approved | 4 hrs | Hour
PLANT | Concrete |  | V2.42 | Concrete Vibrator | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Concrete |  | V2.43 | Power Trowel / Helicopter | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Concrete |  | V2.44 | Concrete Saw - Hand Held | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Concrete |  | V2.45 | Concrete Saw - Floor / Road | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Power & Air |  | V2.46 | Generator 7.5kVA | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day |  |  | Fuel separate
PLANT | Power & Air |  | V2.47 | Generator 15kVA | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day |  |  | Fuel separate
PLANT | Power & Air |  | V2.48 | Generator 30kVA | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day |  |  | Fuel separate
PLANT | Power & Air |  | V2.49 | Generator 60kVA | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day |  |  | Fuel separate
PLANT | Power & Air |  | V2.50 | Generator 100kVA+ | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day |  |  | Fuel separate
PLANT | Power & Air |  | V2.51 | Air Compressor - Portable | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Power & Air |  | V2.52 | Air Compressor - Towable | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Welding & Fab |  | V2.53 | MIG Welder | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Welding & Fab |  | V2.54 | Stick Welder | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Welding & Fab |  | V2.55 | Oxy-Acetylene Set | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Testing & Survey |  | V2.56 | Total Station | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Testing & Survey |  | V2.57 | GPS RTK Survey Equipment | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Testing & Survey |  | V2.58 | Automatic Level | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Testing & Survey |  | V2.59 | Nuclear Density Gauge | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day |  |  | Licensed operator reqd
PLANT | Testing & Survey |  | V2.60 | Dynamic Cone Penetrometer | Day | Hire | [12 empty] | Per day hired | Docket approved |  | Day
PLANT | Site Facilities |  | V2.61 | Site Office - 6m x 3m | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Site Facilities |  | V2.62 | Site Office - 12m x 3m | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Site Facilities |  | V2.63 | Ablution Block | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Site Facilities |  | V2.64 | Storage Container - 20ft | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Site Facilities |  | V2.65 | Storage Container - 40ft | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Site Facilities |  | V2.66 | DG Store - Flammable Liquids | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Temp Services |  | V2.67 | Temp Power Board - 63A | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Temp Services |  | V2.68 | Lighting Tower | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week |  |  | Fuel separate
PLANT | Temp Services |  | V2.69 | Portable Toilet | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week |  |  | Servicing included
PLANT | Temp Services |  | V2.70 | Water Tank 5,000L | Week | Hire | [12 empty] | Per week hired | Docket approved | 1 week | Week
PLANT | Fencing & Barriers |  | V2.71 | Temp Fencing Panel - 2.4m | Week | Hire | [12 empty] | Per panel per week | Docket approved |  | Week
PLANT | Fencing & Barriers |  | V2.72 | Temp Fencing Gate - Pedestrian | Week | Hire | [12 empty] | Per gate per week | Docket approved |  | Week
PLANT | Fencing & Barriers |  | V2.73 | Temp Fencing Gate - Vehicle | Week | Hire | [12 empty] | Per gate per week | Docket approved |  | Week
PLANT | Fencing & Barriers |  | V2.74 | Shade Cloth / Scrim | m | Hire | [12 empty] | Per linear metre | Docket approved |  | Week
PLANT | Fencing & Barriers |  | V2.75 | Concrete Barrier | Week | Hire | [12 empty] | Per barrier per week | Docket approved |  | Week
PLANT | Fencing & Barriers |  | V2.76 | Water Filled Barrier | Week | Hire | [12 empty] | Per barrier per week | Docket approved |  | Week
PLANT | Fencing & Barriers |  | V2.77 | Traffic Cones & Signage Set | Day | Hire | [12 empty] | Per set per day | Docket approved |  | Day
MATERIALS |  |  | V3 | MATERIALS UNIT RATES |  | Supply | [12 empty] | Per unit supplied | Invoice + approved docket |  |  |  |  | Delivery included unless noted
MATERIALS | Concrete |  | V3.01 | Concrete N20 - 20MPa Pump Mix | m³ | Supply | [12 empty] | Per m³ delivered | Delivery docket |  | m³
MATERIALS | Concrete |  | V3.02 | Concrete N25 - 25MPa Pump Mix | m³ | Supply | [12 empty] | Per m³ delivered | Delivery docket |  | m³
MATERIALS | Concrete |  | V3.03 | Concrete N32 - 32MPa Pump Mix | m³ | Supply | [12 empty] | Per m³ delivered | Delivery docket |  | m³
MATERIALS | Concrete |  | V3.04 | Concrete N40 - 40MPa Pump Mix | m³ | Supply | [12 empty] | Per m³ delivered | Delivery docket |  | m³
MATERIALS | Concrete |  | V3.05 | Non-Shrink Grout | 25kg | Supply | [12 empty] | Per bag | Delivery docket |  | Bag
MATERIALS | Reinforcement |  | V3.06 | Rebar N12 | Tonne | Supply | [12 empty] | Per tonne | Delivery docket |  | Tonne
MATERIALS | Reinforcement |  | V3.07 | Rebar N16 | Tonne | Supply | [12 empty] | Per tonne | Delivery docket |  | Tonne
MATERIALS | Reinforcement |  | V3.08 | Rebar N20 | Tonne | Supply | [12 empty] | Per tonne | Delivery docket |  | Tonne
MATERIALS | Reinforcement |  | V3.09 | Mesh SL82 | Sheet | Supply | [12 empty] | Per sheet | Delivery docket |  | Sheet
MATERIALS | Reinforcement |  | V3.10 | Mesh SL92 | Sheet | Supply | [12 empty] | Per sheet | Delivery docket |  | Sheet
MATERIALS | Structural Steel |  | V3.11 | Structural Steel - Hot Rolled | Tonne | Supply | [12 empty] | Per tonne | Delivery docket |  | Tonne |  |  | Fabricated to drawing
MATERIALS | Structural Steel |  | V3.12 | Structural Steel - Hot Dip Galv | Tonne | Supply | [12 empty] | Per tonne | Delivery docket |  | Tonne |  |  | Fabricated + HDG
MATERIALS | Structural Steel |  | V3.13 | Steel Posts - RHS/SHS | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Timber |  | V3.14 | Timber Framing - MGP10 | m³ | Supply | [12 empty] | Per m³ | Delivery docket |  | m³
MATERIALS | Timber |  | V3.15 | Timber LVL Beams | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Timber |  | V3.16 | Hardwood Battens - 42x19 | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Linings |  | V3.17 | Plasterboard - Standard 13mm | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Linings |  | V3.18 | Plasterboard - Fire Rated 13mm | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Linings |  | V3.19 | Plasterboard - Wet Area 13mm | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Linings |  | V3.20 | Fibre Cement Sheet 6mm | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Insulation |  | V3.21 | Wall Batts R2.5 | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Insulation |  | V3.22 | Ceiling Batts R6.0 | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Insulation |  | V3.23 | Acoustic Batts | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Roofing |  | V3.24 | Colorbond Roof Sheeting | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Roofing |  | V3.25 | Roof Flashings - Colorbond | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Roofing |  | V3.26 | Box Gutter - Colorbond | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Roofing |  | V3.27 | Downpipes - Colorbond 90mm | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Cladding |  | V3.28 | AM-1 Cladding Panel | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m² |  |  | Per Arch dwg
MATERIALS | Cladding |  | V3.29 | AM-2 Horizontal Flashings | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm |  |  | Per Arch dwg
MATERIALS | Cladding |  | V3.30 | AM-3 Vertical Flashings | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm |  |  | Per Arch dwg
MATERIALS | Doors |  | V3.31 | Internal Door - Solid Core | No. | Supply | [12 empty] | Per door | Delivery docket |  | No. |  |  | Complete with hardware
MATERIALS | Doors |  | V3.32 | Internal Door - Glazed | No. | Supply | [12 empty] | Per door | Delivery docket |  | No. |  |  | Complete with hardware
MATERIALS | Doors |  | V3.33 | External Door - Solid Core | No. | Supply | [12 empty] | Per door | Delivery docket |  | No. |  |  | Complete with hardware
MATERIALS | Doors |  | V3.34 | External Door - Glazed | No. | Supply | [12 empty] | Per door | Delivery docket |  | No. |  |  | Complete with hardware
MATERIALS | Doors |  | V3.35 | Acoustic Door - Rw45 | No. | Supply | [12 empty] | Per door | Delivery docket |  | No. |  |  | Complete with hardware
MATERIALS | Doors |  | V3.36 | Sliding Door - Acoustic | No. | Supply | [12 empty] | Per door | Delivery docket |  | No. |  |  | Per Arch dwg
MATERIALS | Windows |  | V3.37 | Window WEF-21 Type | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m² |  |  | Per Arch dwg
MATERIALS | Windows |  | V3.38 | Window WEF-22 Type | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m² |  |  | Per Arch dwg
MATERIALS | Windows |  | V3.39 | Courtyard Glazing WEF-31 | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m² |  |  | Per Arch dwg
MATERIALS | Finishes |  | V3.40 | Paint - Internal Walls (per coat) | m² | Supply | [12 empty] | Per m² per coat | Delivery docket |  | m²
MATERIALS | Finishes |  | V3.41 | Paint - External Walls (per coat) | m² | Supply | [12 empty] | Per m² per coat | Delivery docket |  | m²
MATERIALS | Finishes |  | V3.42 | Carpet Tiles | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Finishes |  | V3.43 | Vinyl / LVT Flooring | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Finishes |  | V3.44 | Ceramic Floor Tiles | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Finishes |  | V3.45 | Ceramic Wall Tiles | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Finishes |  | V3.46 | External Paving | m² | Supply | [12 empty] | Per m² | Delivery docket |  | m²
MATERIALS | Joinery |  | V3.47 | Laminate Benchtop | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Joinery |  | V3.48 | Base Cabinets | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Joinery |  | V3.49 | Overhead Cabinets | Lm | Supply | [12 empty] | Per linear metre | Delivery docket |  | Lm
MATERIALS | Electrical |  | V3.50 | TPS Cable 2.5mm² | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Electrical |  | V3.51 | TPS Cable 4mm² | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Electrical |  | V3.52 | TPS Cable 6mm² | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Electrical |  | V3.53 | Data Cable Cat6 | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Electrical |  | V3.54 | Conduit 25mm MD | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Electrical |  | V3.55 | GPO Double | No. | Supply | [12 empty] | Per outlet | Delivery docket |  | No.
MATERIALS | Electrical |  | V3.56 | Light Switch - Single | No. | Supply | [12 empty] | Per switch | Delivery docket |  | No.
MATERIALS | Electrical |  | V3.57 | Data Outlet - Double | No. | Supply | [12 empty] | Per outlet | Delivery docket |  | No.
MATERIALS | Hydraulic |  | V3.58 | Copper Pipe Type B 15mm | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Hydraulic |  | V3.59 | Copper Pipe Type B 20mm | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Hydraulic |  | V3.60 | PVC-U DWV 100mm | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Hydraulic |  | V3.61 | HDPE PE100 SDR11 50mm | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Hydraulic |  | V3.62 | Hot Water Unit - Instantaneous | No. | Supply | [12 empty] | Per unit | Delivery docket |  | No. |  |  | Stiebel Eltron or equiv
MATERIALS | Mechanical |  | V3.63 | Ductwork - Galv Sheet | m² | Supply | [12 empty] | Per m² surface area | Delivery docket |  | m²
MATERIALS | Mechanical |  | V3.64 | Flex Duct 250mm | m | Supply | [12 empty] | Per metre | Delivery docket |  | m
MATERIALS | Mechanical |  | V3.65 | Supply Grille / Diffuser | No. | Supply | [12 empty] | Per unit | Delivery docket |  | No.
MATERIALS | Mechanical |  | V3.66 | Return Air Grille | No. | Supply | [12 empty] | Per unit | Delivery docket |  | No.
MATERIALS | Mechanical |  | V3.67 | Volume Control Damper | No. | Supply | [12 empty] | Per unit | Delivery docket |  | No.
MATERIALS | Mechanical |  | V3.68 | Refrigerant Pipe 1/4" + 1/2" pair | m | Supply | [12 empty] | Per metre pair | Delivery docket |  | m
SUBCONTRACT |  |  | V4 | SUBCONTRACTOR WORK RATES |  | All-in | [12 empty] | Per unit complete | Work completion approved |  |  |  |  | Supply + Install rates
SUBCONTRACT | Civil |  | V4.01 | Earthworks - Bulk Cut/Fill | m³ | All-in | [12 empty] | Per m³ measured | Survey confirmed |  | m³
SUBCONTRACT | Civil |  | V4.02 | Earthworks - Detailed Excavation | m³ | All-in | [12 empty] | Per m³ measured | Survey confirmed |  | m³
SUBCONTRACT | Civil |  | V4.03 | Concrete Footings | m³ | All-in | [12 empty] | Per m³ placed | ITP signed |  | m³
SUBCONTRACT | Civil |  | V4.04 | Concrete Slab on Ground | m² | All-in | [12 empty] | Per m² placed | ITP signed |  | m²
SUBCONTRACT | Civil |  | V4.05 | Stormwater Drainage Pipe | Lm | All-in | [12 empty] | Per linear metre | CCTV inspection |  | Lm
SUBCONTRACT | Civil |  | V4.06 | Stormwater Pit | No. | All-in | [12 empty] | Per pit complete | Inspection passed |  | No.
SUBCONTRACT | Structural |  | V4.07 | Structural Steel Erection | Tonne | All-in | [12 empty] | Per tonne erected | ITP signed |  | Tonne
SUBCONTRACT | Structural |  | V4.08 | Steel Framing - Wall | m² | All-in | [12 empty] | Per m² framed | Inspection passed |  | m²
SUBCONTRACT | Structural |  | V4.09 | Steel Framing - Roof | m² | All-in | [12 empty] | Per m² framed | Inspection passed |  | m²
SUBCONTRACT | Structural |  | V4.10 | Timber Framing | m² | All-in | [12 empty] | Per m² framed | Inspection passed |  | m²
SUBCONTRACT | Envelope |  | V4.11 | Roofing - Metal Deck | m² | All-in | [12 empty] | Per m² complete | Water test passed |  | m²
SUBCONTRACT | Envelope |  | V4.12 | Cladding - AM Series | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Envelope |  | V4.13 | Glazing - Windows | m² | All-in | [12 empty] | Per m² glazed | Inspection passed |  | m²
SUBCONTRACT | Envelope |  | V4.14 | Glazing - Curtain Wall | m² | All-in | [12 empty] | Per m² glazed | Inspection passed |  | m²
SUBCONTRACT | Envelope |  | V4.15 | External Doors | No. | All-in | [12 empty] | Per door installed | Operation checked |  | No.
SUBCONTRACT | Fit-Out |  | V4.16 | Wall Linings - Plasterboard | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.17 | Ceiling - Plasterboard | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.18 | Ceiling - Acoustic Tile | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.19 | Internal Doors | No. | All-in | [12 empty] | Per door installed | Operation checked |  | No.
SUBCONTRACT | Fit-Out |  | V4.20 | Joinery - Kitchens | Lm | All-in | [12 empty] | Per linear metre | Inspection passed |  | Lm
SUBCONTRACT | Fit-Out |  | V4.21 | Joinery - Vanities | Lm | All-in | [12 empty] | Per linear metre | Inspection passed |  | Lm
SUBCONTRACT | Fit-Out |  | V4.22 | Painting - Internal | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.23 | Painting - External | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.24 | Flooring - Carpet Tiles | m² | All-in | [12 empty] | Per m² laid | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.25 | Flooring - Vinyl/LVT | m² | All-in | [12 empty] | Per m² laid | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.26 | Tiling - Floor | m² | All-in | [12 empty] | Per m² laid | Inspection passed |  | m²
SUBCONTRACT | Fit-Out |  | V4.27 | Tiling - Wall | m² | All-in | [12 empty] | Per m² laid | Inspection passed |  | m²
SUBCONTRACT | Mechanical |  | V4.28 | HVAC - Ductwork Installation | m² | All-in | [12 empty] | Per m² surface area | ITP signed |  | m²
SUBCONTRACT | Mechanical |  | V4.29 | HVAC - FCU Installation | No. | All-in | [12 empty] | Per unit installed | Commissioning passed |  | No.
SUBCONTRACT | Mechanical |  | V4.30 | HVAC - Condensing Unit | No. | All-in | [12 empty] | Per unit installed | Commissioning passed |  | No.
SUBCONTRACT | Mechanical |  | V4.31 | Ventilation - Exhaust Fan | No. | All-in | [12 empty] | Per unit installed | Commissioning passed |  | No.
SUBCONTRACT | Mechanical |  | V4.32 | Mechanical Pipework | Lm | All-in | [12 empty] | Per linear metre | Pressure test passed |  | Lm
SUBCONTRACT | Electrical |  | V4.33 | Electrical Rough-In | Point | All-in | [12 empty] | Per point | ITP signed |  | Point
SUBCONTRACT | Electrical |  | V4.34 | Electrical Final Fix | Point | All-in | [12 empty] | Per point | Testing passed |  | Point
SUBCONTRACT | Electrical |  | V4.35 | Switchboard Supply & Install | No. | All-in | [12 empty] | Per board installed | Testing passed |  | No.
SUBCONTRACT | Electrical |  | V4.36 | Lighting Installation | No. | All-in | [12 empty] | Per fitting installed | Testing passed |  | No.
SUBCONTRACT | Electrical |  | V4.37 | Data Cabling | Point | All-in | [12 empty] | Per point | Testing passed |  | Point
SUBCONTRACT | Electrical |  | V4.38 | Security - CCTV Camera | No. | All-in | [12 empty] | Per camera installed | Commissioning passed |  | No.
SUBCONTRACT | Electrical |  | V4.39 | Security - Access Control | No. | All-in | [12 empty] | Per reader installed | Commissioning passed |  | No.
SUBCONTRACT | Hydraulic |  | V4.40 | Hydraulic Rough-In | Point | All-in | [12 empty] | Per point | Pressure test passed |  | Point
SUBCONTRACT | Hydraulic |  | V4.41 | Hydraulic Final Fix - Basin | No. | All-in | [12 empty] | Per fixture installed | Inspection passed |  | No.
SUBCONTRACT | Hydraulic |  | V4.42 | Hydraulic Final Fix - WC | No. | All-in | [12 empty] | Per fixture installed | Inspection passed |  | No.
SUBCONTRACT | Hydraulic |  | V4.43 | Hydraulic Final Fix - Shower | No. | All-in | [12 empty] | Per fixture installed | Inspection passed |  | No.
SUBCONTRACT | Hydraulic |  | V4.44 | Hot Water System | No. | All-in | [12 empty] | Per system installed | Commissioning passed |  | No.
SUBCONTRACT | Fire Services |  | V4.45 | Fire Detection - Smoke Detector | No. | All-in | [12 empty] | Per detector installed | Testing passed |  | No.
SUBCONTRACT | Fire Services |  | V4.46 | Fire Detection - Heat Detector | No. | All-in | [12 empty] | Per detector installed | Testing passed |  | No.
SUBCONTRACT | Fire Services |  | V4.47 | Fire Detection - MCP | No. | All-in | [12 empty] | Per MCP installed | Testing passed |  | No.
SUBCONTRACT | Fire Services |  | V4.48 | Fire Suppression - Sprinkler Head | No. | All-in | [12 empty] | Per head installed | Testing passed |  | No.
SUBCONTRACT | Fire Services |  | V4.49 | Fire Extinguisher | No. | All-in | [12 empty] | Per unit installed | Inspection passed |  | No.
SUBCONTRACT | Landscape |  | V4.50 | Turf Supply & Lay | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
SUBCONTRACT | Landscape |  | V4.51 | Planting - Trees | No. | All-in | [12 empty] | Per tree planted | Inspection passed |  | No.
SUBCONTRACT | Landscape |  | V4.52 | Planting - Shrubs | No. | All-in | [12 empty] | Per shrub planted | Inspection passed |  | No.
SUBCONTRACT | Landscape |  | V4.53 | Planting - Ground Cover | m² | All-in | [12 empty] | Per m² planted | Inspection passed |  | m²
SUBCONTRACT | Landscape |  | V4.54 | Mulching | m² | All-in | [12 empty] | Per m² mulched | Inspection passed |  | m²
SUBCONTRACT | Landscape |  | V4.55 | Retaining Wall - Concrete | m² | All-in | [12 empty] | Per m² face area | ITP signed |  | m²
SUBCONTRACT | Landscape |  | V4.56 | Irrigation System | m² | All-in | [12 empty] | Per m² coverage | Commissioning passed |  | m²
SUBCONTRACT | Landscape |  | V4.57 | Fencing - Steel | Lm | All-in | [12 empty] | Per linear metre | Inspection passed |  | Lm
SUBCONTRACT | Landscape |  | V4.58 | External Paving | m² | All-in | [12 empty] | Per m² complete | Inspection passed |  | m²
TESTING |  |  | V5 | TESTING & COMMISSIONING RATES |  | Test | [12 empty] | Per test/inspection | Report accepted |  |  |  |  | Including reporting
TESTING | Civil |  | V5.01 | Compaction Test - Sand Replacement | No. | Test | [12 empty] | Per test | Report accepted |  | No.
TESTING | Civil |  | V5.02 | Compaction Test - Nuclear Density | No. | Test | [12 empty] | Per test | Report accepted |  | No.
TESTING | Civil |  | V5.03 | Concrete Slump Test | No. | Test | [12 empty] | Per test | Report accepted |  | No.
TESTING | Civil |  | V5.04 | Concrete Cylinder Test | Set | Test | [12 empty] | Per set (3 cylinders) | Report accepted |  | Set
TESTING | Civil |  | V5.05 | Survey Setout Verification | Day | Test | [12 empty] | Per day | Report accepted |  | Day
TESTING | Civil |  | V5.06 | Drainage CCTV Inspection | Lm | Test | [12 empty] | Per linear metre | Report accepted |  | Lm
TESTING | Civil |  | V5.07 | Drainage Mandrel Test | No. | Test | [12 empty] | Per section | Report accepted |  | No.
TESTING | Structural |  | V5.08 | Weld Visual Inspection | No. | Test | [12 empty] | Per weld | Report accepted |  | No.
TESTING | Structural |  | V5.09 | Weld NDT - MPI | No. | Test | [12 empty] | Per weld | Report accepted |  | No.
TESTING | Structural |  | V5.10 | Weld NDT - UT | No. | Test | [12 empty] | Per weld | Report accepted |  | No.
TESTING | Structural |  | V5.11 | Bolt Tension Testing | No. | Test | [12 empty] | Per bolt | Report accepted |  | No.
TESTING | Structural |  | V5.12 | Coating Thickness Test | No. | Test | [12 empty] | Per reading | Report accepted |  | No.
TESTING | Envelope |  | V5.13 | Water Penetration Test | No. | Test | [12 empty] | Per test location | Report accepted |  | No.
TESTING | Envelope |  | V5.14 | Air Tightness Test | No. | Test | [12 empty] | Per test | Report accepted |  | No.
TESTING | Electrical |  | V5.15 | Insulation Resistance Test | Circuit | Test | [12 empty] | Per circuit | Report accepted |  | Circuit
TESTING | Electrical |  | V5.16 | Earth Continuity Test | Circuit | Test | [12 empty] | Per circuit | Report accepted |  | Circuit
TESTING | Electrical |  | V5.17 | RCD Testing | No. | Test | [12 empty] | Per RCD | Report accepted |  | No.
TESTING | Electrical |  | V5.18 | Switchboard Testing | No. | Test | [12 empty] | Per switchboard | Report accepted |  | No.
TESTING | Electrical |  | V5.19 | Lux Level Testing | Room | Test | [12 empty] | Per room | Report accepted |  | Room
TESTING | Electrical |  | V5.20 | Emergency Light Testing | No. | Test | [12 empty] | Per fitting | Report accepted |  | No.
TESTING | Electrical |  | V5.21 | Data Cable Testing | Point | Test | [12 empty] | Per point | Report accepted |  | Point
TESTING | Mechanical |  | V5.22 | AC Unit Commissioning | No. | Test | [12 empty] | Per unit | Report accepted |  | No.
TESTING | Mechanical |  | V5.23 | Ductwork Leakage Test | Section | Test | [12 empty] | Per section | Report accepted |  | Section
TESTING | Mechanical |  | V5.24 | Air Balance Test | Room | Test | [12 empty] | Per room | Report accepted |  | Room
TESTING | Mechanical |  | V5.25 | Temperature Mapping | Zone | Test | [12 empty] | Per zone | Report accepted |  | Zone
TESTING | Mechanical |  | V5.26 | Exhaust Fan Commissioning | No. | Test | [12 empty] | Per fan | Report accepted |  | No.
TESTING | Hydraulic |  | V5.27 | Water Pressure Test | Section | Test | [12 empty] | Per section | Report accepted |  | Section
TESTING | Hydraulic |  | V5.28 | Drainage Air Test | Section | Test | [12 empty] | Per section | Report accepted |  | Section
TESTING | Hydraulic |  | V5.29 | HWU Commissioning | No. | Test | [12 empty] | Per unit | Report accepted |  | No.
TESTING | Hydraulic |  | V5.30 | Backflow Prevention Test | No. | Test | [12 empty] | Per device | Report accepted |  | No.
TESTING | Fire Services |  | V5.31 | Smoke Detector Test | No. | Test | [12 empty] | Per detector | Report accepted |  | No.
TESTING | Fire Services |  | V5.32 | Fire Alarm Panel Commissioning | No. | Test | [12 empty] | Per panel | Report accepted |  | No.
TESTING | Fire Services |  | V5.33 | Sprinkler Flow Test | Zone | Test | [12 empty] | Per zone | Report accepted |  | Zone
TESTING | Fire Services |  | V5.34 | Hydrant Pressure Test | No. | Test | [12 empty] | Per hydrant | Report accepted |  | No.
TESTING | Systems |  | V5.35 | BMS Commissioning | Day | Test | [12 empty] | Per day | Report accepted |  | Day
TESTING | Systems |  | V5.36 | Access Control Commissioning | No. | Test | [12 empty] | Per door/reader | Report accepted |  | No.
TESTING | Systems |  | V5.37 | CCTV Commissioning | No. | Test | [12 empty] | Per camera | Report accepted |  | No.
TESTING | Final |  | V5.38 | Full Building Commissioning | Day | Test | [12 empty] | Per day | Report accepted |  | Day
TESTING | Final |  | V5.39 | Defects Inspection | Day | Test | [12 empty] | Per day | Report accepted |  | Day
TESTING | Final |  | V5.40 | Training Session - O&M | Session | Test | [12 empty] | Per session (4hr) | Attendance signed |  | Session
PROVISIONAL |  |  | V6 | PROVISIONAL SUM WORK RATES |  | PS | [12 empty] | As directed | Principal approval |  |  |  |  | Per Contract Cl 26, 27, 36
PROVISIONAL | Rock Excavation | PS1.01 | V6.01 | Rock Classification & Assessment | Lot | PS | [12 empty] | Lump sum | Report accepted |  | Lot |  |  | Geotech required
PROVISIONAL | Rock Excavation | PS1.01 | V6.02 | Rock Breaking - Hydraulic Hammer | m³ | PS | [12 empty] | Per m³ broken | Survey confirmed |  | m³
PROVISIONAL | Rock Excavation | PS1.01 | V6.03 | Rock Removal & Disposal | m³ | PS | [12 empty] | Per m³ disposed | Tip dockets |  | m³
PROVISIONAL | Rock Excavation | PS1.01 | V6.04 | Rock Excavation Shoring | m² | PS | [12 empty] | Per m² shored | Inspection passed |  | m²
PROVISIONAL | Rock Excavation | PS1.01 | V6.05 | Backfill to Rock Excavation | m³ | PS | [12 empty] | Per m³ compacted | Test passed |  | m³
PROVISIONAL | Contaminated Material | PS1.02 | V6.06 | Contamination Assessment & Testing | Lot | PS | [12 empty] | Lump sum | Report accepted |  | Lot
PROVISIONAL | Contaminated Material | PS1.02 | V6.07 | Contaminated Soil Excavation | m³ | PS | [12 empty] | Per m³ excavated | Survey confirmed |  | m³
PROVISIONAL | Contaminated Material | PS1.02 | V6.08 | Contaminated Material Handling | m³ | PS | [12 empty] | Per m³ handled | Tracking dockets |  | m³
PROVISIONAL | Contaminated Material | PS1.02 | V6.09 | Contaminated Material Disposal | m³ | PS | [12 empty] | Per m³ disposed | Waste cert received |  | m³ |  |  | Licensed facility
PROVISIONAL | Contaminated Material | PS1.02 | V6.10 | Validation Testing & Reporting | Lot | PS | [12 empty] | Lump sum | Report accepted |  | Lot
PROVISIONAL | Contaminated Material | PS1.02 | V6.11 | Clean Fill Replacement | m³ | PS | [12 empty] | Per m³ placed | Test passed |  | m³
PROVISIONAL | Latent Conditions | PS1.03 | V6.12 | Latent Condition Investigation | Day | PS | [12 empty] | Per day | Report accepted |  | Day |  |  | V1/V2 rates apply
PROVISIONAL | Latent Conditions | PS1.03 | V6.13 | Latent Condition Reporting | Lot | PS | [12 empty] | Lump sum | Report accepted |  | Lot |  |  | Within 5 days
PROVISIONAL | Latent Conditions | PS1.03 | V6.14 | Design Response to Latent Cond. | Lot | PS | [12 empty] | Lump sum | Design approved |  | Lot
PROVISIONAL | Latent Conditions | PS1.03 | V6.15 | Remedial Works - Labour | Day | PS | [12 empty] | Per day | Timesheet approved |  | Day |  |  | V1 rates apply
PROVISIONAL | Latent Conditions | PS1.03 | V6.16 | Remedial Works - Plant | Day | PS | [12 empty] | Per day | Docket approved |  | Day |  |  | V2 rates apply
PROVISIONAL | Latent Conditions | PS1.03 | V6.17 | Remedial Works - Materials | Lot | PS | [12 empty] | Invoice + margin | Invoice verified |  | Lot |  |  | V3 rates or cost+
PROVISIONAL | Principal Variations | PS1.04 | V6.18 | Scope Additions - Labour | Day | PS | [12 empty] | Per day | Timesheet approved |  | Day |  |  | V1 rates apply
PROVISIONAL | Principal Variations | PS1.04 | V6.19 | Scope Additions - Plant | Day | PS | [12 empty] | Per day | Docket approved |  | Day |  |  | V2 rates apply
PROVISIONAL | Principal Variations | PS1.04 | V6.20 | Scope Additions - Materials | Lot | PS | [12 empty] | Invoice + margin | Invoice verified |  | Lot |  |  | V3 rates or cost+
PROVISIONAL | Principal Variations | PS1.04 | V6.21 | Scope Additions - Subcontractors | Lot | PS | [12 empty] | Subcontract + margin | Invoice verified |  | Lot |  |  | V4 rates or cost+
PROVISIONAL | Principal Variations | PS1.04 | V6.22 | Design Changes - Documentation | Lot | PS | [12 empty] | Lump sum | Drawings approved |  | Lot
PROVISIONAL | Principal Variations | PS1.04 | V6.23 | Acceleration Measures | Lot | PS | [12 empty] | As approved | Plan approved |  | Lot |  |  | If directed
PROVISIONAL | Principal Variations | PS1.04 | V6.24 | Delay Costs (if attributable) | Day | PS | [12 empty] | Per day | Claim substantiated |  | Day |  |  | Per Cl 36
PROVISIONAL | AV Systems | PS1.05 | V6.25 | AV Contractor Coordination | Mth | PS | [12 empty] | Per month | Monthly pro-rata |  | Mth
PROVISIONAL | AV Systems | PS1.05 | V6.26 | AV Conduit & Cabling Provisions | Lot | PS | [12 empty] | Lump sum | Infrastructure complete |  | Lot
PROVISIONAL | AV Systems | PS1.05 | V6.27 | AV Power Supply Provisions | No. | PS | [12 empty] | Per power point | Installation complete |  | No.
PROVISIONAL | AV Systems | PS1.05 | V6.28 | AV Equipment Backings & Supports | No. | PS | [12 empty] | Per backing/support | Installation complete |  | No.
PROVISIONAL | AV Systems | PS1.05 | V6.29 | AV Testing & Commissioning Attendance | Day | PS | [12 empty] | Per day | Attendance confirmed |  | Day
PROVISIONAL | AV Systems | PS1.05 | V6.30 | AV System Integration Support | Lot | PS | [12 empty] | Lump sum | Integration complete |  | Lot
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## WBS
ENHANCED WORK BREAKDOWN STRUCTURE (WBS) - Aligned with Pay Table
SPS New Project Building - RFT # 1221995761
WBS Code | Level | WBS Element Description | Pay Item Ref | UOM | Qty | SOW Reference | Contract Clause | Architectural Dwg | Structural Dwg | Civil Dwg | Mechanical Dwg | Electrical Dwg | Hydraulic Dwg | Landscape Dwg | Specification | Key Deliverables | Acceptance Criteria | Method of Measure | Rule of Credit | Notes
0 | 0 | Contract Sum | CS | [12 empty] | Complete Building Delivered | Practical Completion Certificate
1 | 1 | INDIRECT COSTS | A1 | [12 empty] | All INDIRECT COSTS Deliverables | Section Complete
1.01 | 2 | PROJECT MANAGEMENT & GOVERNANCE | A1.01 |  |  | SOW 7.0 | Cl 22, 23 | [8 empty] | PROJECT MANAGEMENT & GOVERNANCE - Complete | Subsection Deliverables Accepted
1.01.01 | 3 | Project Manager | A1.01.01 | Day |  | SOW 7.0, 7.1 | Cl 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.02 | 3 | Site Manager / Superintendent | A1.01.02 | Day |  | SOW 7.0, 7.1 | Cl 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.03 | 3 | Project Engineer | A1.01.03 | Day |  | SOW 7.0, 7.1 | Cl 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.04 | 3 | Site Foreman / Supervisor | A1.01.04 | Day |  | SOW 7.0, 7.1 | Cl 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.05 | 3 | WHS Advisor / Safety Officer | A1.01.05 | Day |  | SOW 7.0, 9.0 | Cl 12, 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.06 | 3 | Quality Manager / Coordinator | A1.01.06 | Day |  | SOW 7.0, 10.0 | Cl 29, 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.07 | 3 | Document Controller | A1.01.07 | Day |  | SOW 7.0 | Cl 8, 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.08 | 3 | Contract Administrator | A1.01.08 | Day |  | SOW 7.0 | Cl 37, 22, 23 | [8 empty] | Contract Administrator - Complete | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.09 | 3 | Cost Controller / Estimator | A1.01.09 | Day |  | SOW 7.0 | Cl 37, 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.01.10 | 3 | Scheduler / Planner | A1.01.10 | Day |  | SOW 7.0 | Cl 32, 22, 23 | [8 empty] | Personnel on site, Monthly reports, Timesheets | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
1.02 | 2 | HSE (WHS / ENVIRONMENTAL) | A1.02 |  |  | SOW 9.0 | Cl 12 | [8 empty] | HSE (WHS / ENVIRONMENTAL) - Complete | Subsection Deliverables Accepted
1.02.01 | 3 | WHS Management System | A1.02.01 | Lot | 1 | SOW 9.1 | Cl 12.3, 12.5 | [8 empty] | Approved Plan Document, Implementation evidence | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period | Milestone + Pro-rata monthly | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period
1.02.02 | 3 | Permits and Controls | A1.02.02 | Lot | 1 | SOW 9.2 | Cl 12.4 | [8 empty] | Permits and Controls - Complete | Payment per permit obtained and control measure implemented | Per permit/control implemented | Payment per permit obtained and control measure implemented
1.02.03 | 3 | Environmental Management (CEMP) | A1.02.03 | Lot | 1 | SOW 9.3 | Cl 12.3 |  |  | C05, C104 | [5 empty] | Environmental Management (CEMP) - Complete | 25% upon CEMP acceptance, 75% pro-rata monthly for implementation | Milestone + Pro-rata monthly | 25% upon CEMP acceptance, 75% pro-rata monthly for implementation
1.02.04 | 3 | SWMS Development & Approvals | A1.02.04 | Lot | 1 | SOW 9.1 | Cl 12.3 | [8 empty] | Approved Plan Document, Implementation evidence | Payment per SWMS submitted and approved by Principal | Pro-rata per SWMS approved | Payment per SWMS submitted and approved by Principal
1.02.05 | 3 | Site Inductions & Competency Verification | A1.02.05 | Lot | 1 | SOW 9.1 | Cl 12.3, 12.4 | [8 empty] | Induction records, Training certificates, Competency registers | Monthly payment based on induction records and competency registers maintained | Pro-rata monthly | Monthly payment based on induction records and competency registers maintained
1.02.06 | 3 | Incident Management & Reporting | A1.02.06 | Lot | 1 | SOW 9.1 | Cl 12.9 | [8 empty] | Incident Management & Reporting - Complete | Monthly payment subject to incident register maintained and reports submitted within 24hrs | Pro-rata monthly | Monthly payment subject to incident register maintained and reports submitted within 24hrs
1.02.07 | 3 | Traffic Management Plan & Implementation | A1.02.07 | Lot | 1 | SOW 9.2, 3.4 | Cl 12.6 | [8 empty] | Approved Plan Document, Implementation evidence | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period | Milestone + Pro-rata monthly | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period
1.03 | 2 | QUALITY MANAGEMENT SYSTEM | A1.03 |  |  | SOW 10.0 | Cl 29 | [8 empty] | Approved Plan Document, Implementation evidence | Subsection Deliverables Accepted
1.03.01 | 3 | Quality Management Plan (QMP) | A1.03.01 | Lot | 1 | SOW 10.1 | Cl 29.2 | [8 empty] | Approved Plan Document, Implementation evidence | 100% upon QMP acceptance by Principal | Milestone | 100% upon QMP acceptance by Principal
1.03.02 | 3 | Inspection & Test Plans (ITPs) | A1.03.02 | Lot | 1 | SOW 10.2 | Cl 29.2, 30 | [8 empty] | Approved Plan Document, Implementation evidence | 30% ITPs approved, 70% pro-rata per ITP completed and signed off | Milestone + Pro-rata | 30% ITPs approved, 70% pro-rata per ITP completed and signed off
1.03.03 | 3 | Non-Conformance & Corrective Actions | A1.03.03 | Lot | 1 | SOW 10.3 | Cl 29.3 | [8 empty] | Non-Conformance & Corrective Actions - Complete | Monthly payment subject to NCR register maintained and closeout within agreed timeframes | Pro-rata monthly | Monthly payment subject to NCR register maintained and closeout within agreed timeframes
1.03.04 | 3 | Witness & Hold Point Inspections | A1.03.04 | Lot | 1 | SOW 10.2 | Cl 30 | [8 empty] | Test reports, Commissioning certificates, Inspection records | Payment per witness/hold point inspection completed and signed off | Per inspection completed | Payment per witness/hold point inspection completed and signed off
1.03.05 | 3 | Manufacturer's Data Records (MDR) | A1.03.05 | Lot | 1 | SOW 10.4 | Cl 30.6 | [8 empty] | Manufacturer's Data Records (MDR) - Complete | 100% upon all MDRs submitted and accepted prior to Practical Completion | Milestone | 100% upon all MDRs submitted and accepted prior to Practical Completion
1.04 | 2 | DESIGN & ENGINEERING | A1.04 |  |  | SOW 5.0 | Cl 7A | [8 empty] | Personnel on site, Monthly reports, Timesheets | Subsection Deliverables Accepted
1.04.01 | 3 | Design Management and Coordination | A1.04.01 | Lot | 1 | SOW 5.0, 3.5 | Cl 7A | A-000001 to A-910001 | S1.01 to S9.02 | C01 to C104 | M0000 to M2000 | E0000 to E8002 | H0000 to H9000 | L0.00 to L4.02 |  | IFC Drawings, Shop Drawings, As-built Drawings | 30% design kickoff, 40% IFC drawings issued, 30% as-built documentation accepted | Milestone | 30% design kickoff, 40% IFC drawings issued, 30% as-built documentation accepted
1.04.02 | 3 | Contractor Design Deliverables | A1.04.02 | Lot | 1 | SOW 5.0 | Cl 7A.2 | [8 empty] | IFC Drawings, Shop Drawings, As-built Drawings | Per design deliverable accepted by Principal | Milestone | Per design deliverable accepted by Principal
1.04.03 | 3 | Shop Drawings - All Disciplines | A1.04.03 | Lot | 1 | SOW 5.0 | Cl 7A.2 | [8 empty] | IFC Drawings, Shop Drawings, As-built Drawings | Payment per shop drawing package submitted and approved | Per package approved | Payment per shop drawing package submitted and approved
1.05 | 2 | AUTHORITIES & APPROVALS | A1.05 |  |  | SOW 6.0 | Cl 21 | [8 empty] | Certificates, Approval documents, Compliance records | Subsection Deliverables Accepted
1.05.01 | 3 | Building Approval & Certification | A1.05.01 | Lot | 1 | SOW 6.0 | Cl 21 | A-070001 | [7 empty] | Certificates, Approval documents, Compliance records | Payment upon each authority approval/permit obtained and provided to Principal | Milestone per approval obtained | Payment upon each authority approval/permit obtained and provided to Principal
1.05.02 | 3 | Authority Inspections & Certificates | A1.05.02 | Lot | 1 | SOW 6.0 | Cl 21 | [8 empty] | Test reports, Commissioning certificates, Inspection records | Payment upon each authority approval/permit obtained and provided to Principal | Milestone per approval obtained | Payment upon each authority approval/permit obtained and provided to Principal
2 | 1 | DIRECT COSTS | A2 | [12 empty] | All DIRECT COSTS Deliverables | Section Complete
2.01 | 2 | PROCUREMENT & SUBCONTRACTING | A2.01 |  |  | SOW 4.0 | Cl 5 | [8 empty] | PROCUREMENT & SUBCONTRACTING - Complete | Subsection Deliverables Accepted
2.01.12 | 3 | Procurement Planning & Management | A2.01.12 | Lot | 1 | SOW 4.0 | Cl 5 | [8 empty] | Approved Plan Document, Implementation evidence | 20% procurement plan accepted, 80% pro-rata as packages awarded | Milestone + Pro-rata | 20% procurement plan accepted, 80% pro-rata as packages awarded
2.01.13 | 3 | Subcontractor Coordination | A2.01.13 | Lot | 1 | SOW 4.0 | Cl 5 | [8 empty] | Subcontractor Coordination - Complete | Payment per subcontract/supply package executed | Per package awarded | Payment per subcontract/supply package executed
2.02 | 2 | OFF-SITE FABRICATION | A2.02 |  |  | SOW 5.0 | Cl 5, 30 | [8 empty] | OFF-SITE FABRICATION - Complete | Subsection Deliverables Accepted
2.02.09 | 3 | Module Fabrication QA Plan | A2.02.09 | Lot | 1 | SOW 5.0, 10.0 | Cl 29, 30 | A-910001 | [7 empty] | Approved Plan Document, Implementation evidence | 100% upon fabrication QA plan and ITPs accepted | Milestone | 100% upon fabrication QA plan and ITPs accepted
2.02.10 | 3 | Module Fabrication & Assembly | A2.02.10 | No. |  | SOW 5.0 | Cl 5, 30 | A-910001 | [7 empty] | Module Fabrication & Assembly - Complete | Payment based on % fabrication complete verified by inspection | Pro-rata per module/component | Payment based on % fabrication complete verified by inspection
2.02.11 | 3 | Factory Acceptance Testing | A2.02.11 | Lot | 1 | SOW 5.0 | Cl 30 | A-910001 | [7 empty] | Test reports, Commissioning certificates, Inspection records | Payment per FAT completed and witnessed | Per FAT completed | Payment per FAT completed and witnessed
2.03 | 2 | LOGISTICS, DELIVERIES & LAYDOWN | A2.03 |  |  | SOW 3.4 | Cl 7 | [8 empty] | LOGISTICS, DELIVERIES & LAYDOWN - Complete | Subsection Deliverables Accepted
2.03.07 | 3 | Delivery Planning & Sequencing | A2.03.07 | Lot | 1 | SOW 3.4 | Cl 7 | [8 empty] | Approved Plan Document, Implementation evidence | 100% upon logistics plan accepted | Milestone | 100% upon logistics plan accepted
2.03.08 | 3 | Module Transport (32 Modules) | A2.03.08 | No. |  | SOW 3.4 | Cl 7, 12.6 | [8 empty] | Module Transport (32 Modules) - Complete | Payment per delivery received, inspected and accepted at site | Per delivery received | Payment per delivery received, inspected and accepted at site
2.03.09 | 3 | Offloading & Laydown Operations | A2.03.09 | Lot | 1 | SOW 3.4 | Cl 7 | [8 empty] | Offloading & Laydown Operations - Complete | Payment per delivery received, inspected and accepted at site | Per delivery received | Payment per delivery received, inspected and accepted at site
2.04 | 2 | MOBILISATION & TEMPORARY WORKS | A2.04 |  |  | SOW 3.3, 3.4 | Cl 7 | [8 empty] | Site established, Facilities operational | Subsection Deliverables Accepted
2.04.05 | 3 | Site Establishment | A2.04.05 | Lot | 1 | SOW 3.3 | Cl 7 | [8 empty] | Site Establishment - Complete | 100% upon site establishment complete and accepted | Milestone | 100% upon site establishment complete and accepted
2.04.06 | 3 | Temporary Fencing & Hoarding | A2.04.06 | Lm |  | SOW 3.3.1 | Cl 7 |  |  | C02, C03 | [5 empty] | Temporary Fencing & Hoarding - Complete | 100% upon fencing/hoarding installed and accepted | Lump sum on completion | 100% upon fencing/hoarding installed and accepted
2.04.07 | 3 | Temporary Site Offices & Amenities | A2.04.07 | Lot | 1 | SOW 3.3.2 | Cl 7 | [8 empty] | Temporary Site Offices & Amenities - Complete | 50% upon installation complete, 50% pro-rata monthly for maintenance | Milestone + Monthly | 50% upon installation complete, 50% pro-rata monthly for maintenance
2.04.08 | 3 | Temporary Power, Water & Comms | A2.04.08 | Lot | 1 | SOW 3.3.3 | Cl 7 |  |  |  |  | E0010 | H0010 |  |  | Installation complete, Tests passed, Certificates issued | 100% upon temporary services connected and operational | Milestone | 100% upon temporary services connected and operational
2.04.09 | 3 | Temporary Access & Security | A2.04.09 | Lot | 1 | SOW 3.3.4 | Cl 7 |  |  |  |  | E2000 |  |  |  | Temporary Access & Security - Complete | 100% upon mobilisation item complete and accepted | Milestone | 100% upon mobilisation item complete and accepted
2.05 | 2 | DEMOLITION & REMOVAL WORKS | A2.05 |  |  | SOW 3.6 | Cl 7 | [8 empty] | DEMOLITION & REMOVAL WORKS - Complete | Subsection Deliverables Accepted
2.05.04 | 3 | Pre-Demolition Planning & Approvals | A2.05.04 | Lot | 1 | SOW 3.6 | Cl 7 | A-040002 | [7 empty] | Approved Plan Document, Implementation evidence | 100% upon demolition plan and methodology accepted | Milestone | 100% upon demolition plan and methodology accepted
2.05.05 | 3 | Demolition of Existing Demountables | A2.05.05 | Lot | 1 | SOW 3.6.2 | Cl 7 | A-040002 | [7 empty] | Demolition of Existing Demountables - Complete | Payment based on % demolition complete verified by site inspection | % complete measured monthly | Payment based on % demolition complete verified by site inspection
2.05.06 | 3 | Services Disconnection & Capping | A2.05.06 | Lot | 1 | SOW 3.6.2 | Cl 7 | A-040002 |  |  |  | E0005 | H0010 |  |  | Services Disconnection & Capping - Complete | Payment based on % demolition complete verified by site inspection | % complete measured monthly | Payment based on % demolition complete verified by site inspection
2.05.07 | 3 | Salvage, Waste Disposal & Site Clearance | A2.05.07 | Lot | 1 | SOW 3.6.3 | Cl 12.3 | A-040002 | [7 empty] | Salvage, Waste Disposal & Site Clearance - Complete | Payment per waste disposed with lawful disposal documentation | Per load disposed | Payment per waste disposed with lawful disposal documentation
2.06 | 2 | CIVIL, EARTHWORKS & EXTERNAL WORKS | A2.06 |  |  | SOW 3.7 | Cl 7, 30 | [8 empty] | Survey records, Compaction tests, Level verification | Subsection Deliverables Accepted
2.06.01 | 3 | Survey & Setout | A2.06.01 | Lot | 1 | SOW 3.7 | Cl 7, 30 |  | S1.03 | C02, C03 | [5 empty] | Survey & Setout - Complete | 100% upon survey complete and setout accepted | Milestone | 100% upon survey complete and setout accepted
2.06.02 | 3 | Bulk Earthworks - Cut & Fill | A2.06.02 | m³ |  | SOW 3.7.1 | Cl 7, 30 |  |  | C02 | [5 empty] | Survey records, Compaction tests, Level verification | Payment per m³ excavated/filled, measured in place, compaction tests passed | Per m³ measured | Payment per m³ excavated/filled, measured in place, compaction tests passed
2.06.03 | 3 | Site Regrading & Compaction | A2.06.03 | m² |  | SOW 3.7 | Cl 7, 30 |  |  | C01 to C06 | [5 empty] | Site Regrading & Compaction - Complete | Payment based on % complete verified by Superintendent | % complete measured monthly | Payment based on % complete verified by Superintendent
2.06.04 | 3 | Service Trenching & Backfill | A2.06.04 | Lm |  | SOW 3.7.2 | Cl 7, 30 |  |  | C03, C04 | [5 empty] | Survey records, Compaction tests, Level verification | Payment per m³ excavated/filled, measured in place, compaction tests passed | Per m³ measured | Payment per m³ excavated/filled, measured in place, compaction tests passed
2.06.05 | 3 | Stormwater Drainage System | A2.06.05 | Lot | 1 | SOW 3.7.3 | Cl 7, 30 |  |  | C03, C04 |  |  | H1000, H1001 |  |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment per Lm installed and tested (CCTV/pressure test as applicable) | Per linear metre installed | Payment per Lm installed and tested (CCTV/pressure test as applicable)
2.06.06 | 3 | Erosion & Sediment Control | A2.06.06 | Lot | 1 | SOW 3.7 | Cl 7, 30 |  |  | C01 to C06 | [5 empty] | Erosion & Sediment Control - Complete | Payment based on % complete verified by Superintendent | % complete measured monthly | Payment based on % complete verified by Superintendent
2.06.07 | 3 | External Pavements & Footpaths | A2.06.07 | m² |  | SOW 3.7.4 | Cl 7, 30 |  |  | C03, C04, C06 | [5 empty] | External Pavements & Footpaths - Complete | Payment per m² placed, cured and accepted (concrete test results compliant) | Per m² complete | Payment per m² placed, cured and accepted (concrete test results compliant)
2.06.08 | 3 | Vehicle Parking Area | A2.06.08 | m² |  | SOW 3.7.7 | Cl 7, 30 |  |  | C101 to C104 | [5 empty] | Vehicle Parking Area - Complete | Payment based on % complete verified by Superintendent | % complete measured monthly | Payment based on % complete verified by Superintendent
2.06.09 | 3 | Linemarking | A2.06.09 | Lot | 1 | SOW 3.7 | Cl 7, 30 |  |  | C01 to C06 | [5 empty] | Linemarking - Complete | Payment based on % complete verified by Superintendent | % complete measured monthly | Payment based on % complete verified by Superintendent
2.06.10 | 3 | Fencing & Gates | A2.06.10 | Lm |  | SOW 3.7.5 | Cl 7, 30 |  |  | C03 | [5 empty] | Fencing & Gates - Complete | Payment per Lm fencing / each gate installed and accepted | Per linear metre / each | Payment per Lm fencing / each gate installed and accepted
2.06.11 | 3 | Retaining Walls | A2.06.11 | Lm |  | SOW 3.7.6 | Cl 7, 30 |  | S7.01 | C04 | [5 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per Lm retaining wall complete, Engineer certified | Per linear metre | Payment per Lm retaining wall complete, Engineer certified
2.06.12 | 3 | Hat Stand Refurbishment | A2.06.12 | No. |  | SOW 3.7.8 | Cl 7, 30 | A-810001 | S9.01, S9.02 | C01 to C06 | [5 empty] | Hat Stand Refurbishment - Complete | Payment based on % complete verified by Superintendent | % complete measured monthly | Payment based on % complete verified by Superintendent
2.07 | 2 | BUILDING STRUCTURE & ENVELOPE | A2.07 |  |  | SOW 3.8 | Cl 7, 30 | [8 empty] | BUILDING STRUCTURE & ENVELOPE - Complete | Subsection Deliverables Accepted
2.07.01 | 3 | Foundations & Footings | A2.07.01 | Lot | 1 | SOW 3.8.1 | Cl 7, 30 | A-300002 | S2.01, S2.02 | [6 empty] | Pour records, Concrete dockets, Strength tests | Payment upon concrete placed, cured, stripped and accepted (test results compliant) | Per m²/m³ complete | Payment upon concrete placed, cured, stripped and accepted (test results compliant)
2.07.02 | 3 | Ground Floor Slab | A2.07.02 | m² |  | SOW 3.8.1 | Cl 7, 30 | A-300001 | S2.01, S2.02 | [6 empty] | Pour records, Concrete dockets, Strength tests | Payment upon concrete placed, cured, stripped and accepted (test results compliant) | Per m²/m³ complete | Payment upon concrete placed, cured, stripped and accepted (test results compliant)
2.07.03 | 3 | Suspended Floor Structure | A2.07.03 | m² |  | SOW 3.8.2 | Cl 7, 30 | A-300001 | S3.01, S3.02, S3.03 | [6 empty] | Surface prep complete, Finishes installed, Accepted | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.07.04 | 3 | Structural Steel Framing | A2.07.04 | Lot | 1 | SOW 3.8.3 | Cl 7, 30 | A-300001 | S3.01, S5.01, S5.02 | [6 empty] | Steel certification, Weld inspections, Bolt tension records | Payment per tonne erected or % framing complete, bolted/welded and inspected | Per tonne / % complete | Payment per tonne erected or % framing complete, bolted/welded and inspected
2.07.05 | 3 | Roof Framing | A2.07.05 | Lot | 1 | SOW 3.8.4 | Cl 7, 30 | A-200002, A-300003 | S4.01, S4.02, S6.01 to S6.03 | [6 empty] | Steel certification, Weld inspections, Bolt tension records | Payment per tonne erected or % framing complete, bolted/welded and inspected | Per tonne / % complete | Payment per tonne erected or % framing complete, bolted/welded and inspected
2.07.06 | 3 | Roof Sheeting & Insulation | A2.07.06 | m² |  | SOW 3.8.4 | Cl 7, 30 | A-200002, A-720007 | [7 empty] | Installation records, Weather sealing tests | Payment per m² roofing installed, flashed and water-tested | Per m² complete | Payment per m² roofing installed, flashed and water-tested
2.07.07 | 3 | Roof Flashings, Gutters & Downpipes | A2.07.07 | Lm |  | SOW 3.8.5 | Cl 7, 30 | A-720007 |  |  |  |  | H1001 |  |  | Installation records, Weather sealing tests | Payment per m² roofing installed, flashed and water-tested | Per m² complete | Payment per m² roofing installed, flashed and water-tested
2.07.08 | 3 | External Cladding System | A2.07.08 | m² |  | SOW 3.8.6 | Cl 7, 30 | A-400001 to A-400004, A-760001 | [7 empty] | Installation records, Weather sealing tests | Payment per m² cladding installed, sealed and accepted | Per m² installed | Payment per m² cladding installed, sealed and accepted
2.07.09 | 3 | External Windows | A2.07.09 | No. |  | SOW 3.8.7 | Cl 7, 30 | A-400001 to A-400004, A-730001 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per window/door installed, sealed, hardware complete and operational | Per unit installed | Payment per window/door installed, sealed, hardware complete and operational
2.07.10 | 3 | External Glazed Doors | A2.07.10 | No. |  | SOW 3.8.7 | Cl 7, 30 | A-730001 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per window/door installed, sealed, hardware complete and operational | Per unit installed | Payment per window/door installed, sealed, hardware complete and operational
2.07.11 | 3 | Courtyard Glazing System | A2.07.11 | Lot | 1 | SOW 3.8.7 | Cl 7, 30 | A-400101, A-410010, A-410011, A-710005 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per window/door installed, sealed, hardware complete and operational | Per unit installed | Payment per window/door installed, sealed, hardware complete and operational
2.07.12 | 3 | Entry Walkway Structure | A2.07.12 | Lot | 1 | SOW 3.8.8 | Cl 7, 30 | A-500002 | S1.03 | [6 empty] | Entry Walkway Structure - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.07.13 | 3 | External Stairs | A2.07.13 | No. |  | SOW 3.8.8 | Cl 7, 30 | A-500001 | [7 empty] | External Stairs - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.07.14 | 3 | Mechanical Plant Enclosure | A2.07.14 | Lot | 1 | SOW 3.8.9 | Cl 7, 30 | A-800001 |  |  | M1010 |  |  |  |  | Approved Plan Document, Implementation evidence | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.07.15 | 3 | Generator Area Slab | A2.07.15 | m² |  | SOW 3.8.9 | Cl 7, 30 |  | S8.01 |  |  | E8000 |  |  |  | Pour records, Concrete dockets, Strength tests | Payment upon concrete placed, cured, stripped and accepted (test results compliant) | Per m²/m³ complete | Payment upon concrete placed, cured, stripped and accepted (test results compliant)
2.07.16 | 3 | Weatherproofing & Sealing | A2.07.16 | Lot | 1 | SOW 3.8.10 | Cl 7, 30 | A-720001 to A-720007 | [7 empty] | Installation records, Weather sealing tests | Payment per m² roofing installed, flashed and water-tested | Per m² complete | Payment per m² roofing installed, flashed and water-tested
2.08 | 2 | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | A2.08 |  |  | SOW 3.9 | Cl 7, 30 | [8 empty] | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) - Complete | Subsection Deliverables Accepted
2.08.01 | 3 | Internal Partitions - Standard | A2.08.01 | m² |  | SOW 3.9.1 | Cl 7, 30 | A-220001, A-220002, A-710010 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² framed, lined, finished and accepted | Per m² installed | Payment per m² framed, lined, finished and accepted
2.08.02 | 3 | Internal Partitions - Acoustic Rated | A2.08.02 | m² |  | SOW 3.9.1 | Cl 7, 30 | A-220001, A-220002, A-710010 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² framed, lined, finished and accepted | Per m² installed | Payment per m² framed, lined, finished and accepted
2.08.03 | 3 | Internal Glazed Partitions | A2.08.03 | m² |  | SOW 3.9.1 | Cl 7, 30 | A-220001, A-220002, A-710010 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² framed, lined, finished and accepted | Per m² installed | Payment per m² framed, lined, finished and accepted
2.08.04 | 3 | Wall Linings & Insulation | A2.08.04 | m² |  | SOW 3.9.2 | Cl 7, 30 | A-220001, A-220002 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² framed, lined, finished and accepted | Per m² installed | Payment per m² framed, lined, finished and accepted
2.08.05 | 3 | Suspended Ceilings | A2.08.05 | m² |  | SOW 3.9.3 | Cl 7, 30 | A-210001, A-720012 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² ceiling grid and tiles/panels installed and accepted | Per m² installed | Payment per m² ceiling grid and tiles/panels installed and accepted
2.08.06 | 3 | Ceiling Battens | A2.08.06 | m² |  | SOW 3.9.8 | Cl 7, 30 | A-730002 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² ceiling grid and tiles/panels installed and accepted | Per m² installed | Payment per m² ceiling grid and tiles/panels installed and accepted
2.08.07 | 3 | Ceiling Bulkheads | A2.08.07 | Lm |  | SOW 3.9 | Cl 7, 30 | A-200001 | [7 empty] | Survey records, Compaction tests, Level verification | Payment per m² ceiling grid and tiles/panels installed and accepted | Per m² installed | Payment per m² ceiling grid and tiles/panels installed and accepted
2.08.08 | 3 | Access Panels | A2.08.08 | No. |  | SOW 3.9.3 | Cl 7, 30 | A-210001 | [7 empty] | Access Panels - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.09 | 3 | Internal Doors - Solid Core | A2.08.09 | No. |  | SOW 3.9.4 | Cl 7, 30 | A-730001 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per door leaf installed with hardware, operational and accepted | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
2.08.10 | 3 | Internal Doors - Glazed | A2.08.10 | No. |  | SOW 3.9.4 | Cl 7, 30 | A-730001 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per door leaf installed with hardware, operational and accepted | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
2.08.11 | 3 | Acoustic Sliding Doors | A2.08.11 | No. |  | SOW 3.9.1 | Cl 7, 30 | A-220001, A-720011 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per door leaf installed with hardware, operational and accepted | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
2.08.12 | 3 | Door Hardware | A2.08.12 | Lot | 1 | SOW 3.9.5 | Cl 7, 30 | A-730001 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per door leaf installed with hardware, operational and accepted | Per leaf installed | Payment per door leaf installed with hardware, operational and accepted
2.08.13 | 3 | Turnstile | A2.08.13 | No. |  | SOW 3.9.7 | Cl 7, 30 | A-230001 | [7 empty] | Surface prep complete, Finishes installed, Accepted | Payment per m² flooring installed, adhesive cured, accepted | Per m² installed | Payment per m² flooring installed, adhesive cured, accepted
2.08.14 | 3 | Floor Finishes - Carpet/Vinyl | A2.08.14 | m² |  | SOW 3.9.7 | Cl 7, 30 | A-230001, A-720010 | [7 empty] | Surface prep complete, Finishes installed, Accepted | Payment per m² flooring installed, adhesive cured, accepted | Per m² installed | Payment per m² flooring installed, adhesive cured, accepted
2.08.15 | 3 | Floor Finishes - Wet Areas | A2.08.15 | m² |  | SOW 3.9.7 | Cl 7, 30 | A-230001, A-720010 | [7 empty] | Surface prep complete, Finishes installed, Accepted | Payment per m² flooring installed, adhesive cured, accepted | Per m² installed | Payment per m² flooring installed, adhesive cured, accepted
2.08.16 | 3 | Wall Finishes & Painting | A2.08.16 | m² |  | SOW 3.9.8 | Cl 7, 30 | A-600001 to A-600017 | [7 empty] | Linings complete, Insulation installed, Fire rating verified | Payment per m² framed, lined, finished and accepted | Per m² installed | Payment per m² framed, lined, finished and accepted
2.08.17 | 3 | Skirtings & Trims | A2.08.17 | Lm |  | SOW 3.9.8 | Cl 7, 30 | A-730002 | [7 empty] | Skirtings & Trims - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.18 | 3 | Kitchen Joinery (JO-BW-1, JO-BW-2) | A2.08.18 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Joinery installed, Services connected, Quality accepted | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.19 | 3 | Boardroom Joinery (JO-BW-3) | A2.08.19 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Joinery installed, Services connected, Quality accepted | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.20 | 3 | Health Room Joinery (JO-BW-4) | A2.08.20 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Joinery installed, Services connected, Quality accepted | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.21 | 3 | Training Kitchen Joinery (JO-BW-5) | A2.08.21 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Induction records, Training certificates, Competency registers | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.22 | 3 | First Aid Joinery (JO-BW-6) | A2.08.22 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Joinery installed, Services connected, Quality accepted | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.23 | 3 | Covered Outdoor Joinery (JO-BW-7, JO-ST-1, JO-SE-1) | A2.08.23 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.24 | 3 | Amenities Joinery (JO-BW-8, JO-BW-9) | A2.08.24 | Lot | 1 | SOW 3.9.9 | Cl 7, 30 | A-780001 to A-780012 | [7 empty] | Joinery installed, Services connected, Quality accepted | Payment per joinery item installed, services connected, accepted | Per item installed | Payment per joinery item installed, services connected, accepted
2.08.25 | 3 | Smart Lockers (JO-LKR-1) | A2.08.25 | No. |  | SOW 3.9.10 | Cl 7, 30 | A-780011 | [7 empty] | Smart Lockers (JO-LKR-1) - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.26 | 3 | Display Boards (JO-BD-1 to JO-BD-5) | A2.08.26 | No. |  | SOW 3.9.12 | Cl 7, 30 | A-780002, A-780003 | [7 empty] | Display Boards (JO-BD-1 to JO-BD-5) - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.27 | 3 | Kitchen Storage (JO-ST-2, JO-ST-3) | A2.08.27 | Lot | 1 | SOW 3.9 | Cl 7, 30 | A-200001 | [7 empty] | Kitchen Storage (JO-ST-2, JO-ST-3) - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.28 | 3 | Male Amenities Fit-out | A2.08.28 | Lot | 1 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H6000, H6001 |  |  | Male Amenities Fit-out - Complete | Payment per wet area complete including fixtures, fittings and finishes | Per room complete | Payment per wet area complete including fixtures, fittings and finishes
2.08.29 | 3 | Female Amenities Fit-out | A2.08.29 | Lot | 1 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H6000, H6001 |  |  | Female Amenities Fit-out - Complete | Payment per wet area complete including fixtures, fittings and finishes | Per room complete | Payment per wet area complete including fixtures, fittings and finishes
2.08.30 | 3 | PWD Amenities Fit-out | A2.08.30 | Lot | 1 | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H6000, H6001 |  |  | PWD Amenities Fit-out - Complete | Payment per wet area complete including fixtures, fittings and finishes | Per room complete | Payment per wet area complete including fixtures, fittings and finishes
2.08.31 | 3 | Shower Room Fit-out | A2.08.31 | Lot | 1 | SOW 3.9.10 | Cl 7, 30 | A-620001 |  |  |  |  | H6000, H6001 |  |  | Shower Room Fit-out - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.32 | 3 | Sanitary Fixtures & Accessories | A2.08.32 | No. |  | SOW 3.9.10 | Cl 7, 30 | A-620001 to A-620004 |  |  |  |  | H0003 |  |  | Sanitary Fixtures & Accessories - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.33 | 3 | Acoustic Treatments | A2.08.33 | Lot | 1 | SOW 3.9.1 | Cl 7, 30 | A-220001, A-720011 | [7 empty] | Acoustic Treatments - Complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.08.34 | 3 | Signage | A2.08.34 | No. |  | SOW 3.9.11 | Cl 7, 30 | A-770001 | [7 empty] | Signage - Complete | Payment per sign fabricated, installed and accepted | Per sign installed | Payment per sign fabricated, installed and accepted
2.08.35 | 3 | Window Coverings / Blinds | A2.08.35 | No. |  | SOW 3.9.13 | Cl 7, 30 | A-720012 | [7 empty] | Units installed, Hardware fitted, Seals complete | Payment based on % complete verified by Superintendent inspection | % complete measured monthly | Payment based on % complete verified by Superintendent inspection
2.09 | 2 | MECHANICAL SERVICES | A2.09 |  |  | SOW 3.10 | Cl 7, 30 | [8 empty] | Equipment installed, Ductwork complete, Commissioning passed | Subsection Deliverables Accepted
2.09.01 | 3 | AC Equipment Supply & Install | A2.09.01 | No. |  | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  |  | Equipment installed, Ductwork complete, Commissioning passed | Payment per unit installed, connected, pre-commissioned | Per unit installed | Payment per unit installed, connected, pre-commissioned
2.09.02 | 3 | Ductwork Installation | A2.09.02 | Lm |  | SOW 3.10.2 | Cl 7, 30 |  |  |  | M1000, M2000 |  |  |  |  | Ductwork Installation - Complete | Payment based on % ductwork installed, pressure tested and accepted | % complete measured monthly | Payment based on % ductwork installed, pressure tested and accepted
2.09.03 | 3 | Diffusers & Grilles | A2.09.03 | No. |  | SOW 3.10.2 | Cl 7, 30 |  |  |  | M0001 |  |  |  |  | Diffusers & Grilles - Complete | Payment per grille/diffuser installed and balanced | Per item installed | Payment per grille/diffuser installed and balanced
2.09.04 | 3 | Kitchen Exhaust System | A2.09.04 | Lot | 1 | SOW 3.10.3 | Cl 7, 30 |  |  |  | M1000 |  |  |  |  | Kitchen Exhaust System - Complete | Payment based on % complete verified by Services Engineer | % complete measured monthly | Payment based on % complete verified by Services Engineer
2.09.05 | 3 | Amenities Exhaust System | A2.09.05 | Lot | 1 | SOW 3.10.3 | Cl 7, 30 |  |  |  | M1000 |  |  |  |  | Amenities Exhaust System - Complete | Payment based on % complete verified by Services Engineer | % complete measured monthly | Payment based on % complete verified by Services Engineer
2.09.06 | 3 | Mechanical Controls & BMS Interface | A2.09.06 | Lot | 1 | SOW 3.10.4 | Cl 7, 30 |  |  |  | M0001 | E2000 |  |  |  | Equipment installed, Ductwork complete, Commissioning passed | 50% controllers installed, 50% BMS programmed and operational | Milestone | 50% controllers installed, 50% BMS programmed and operational
2.09.07 | 3 | Piping, Valves & Supports | A2.09.07 | Lm |  | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  |  | Piping, Valves & Supports - Complete | Payment based on % complete verified by Services Engineer | % complete measured monthly | Payment based on % complete verified by Services Engineer
2.09.08 | 3 | Mechanical Insulation | A2.09.08 | m² |  | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  |  | Equipment installed, Ductwork complete, Commissioning passed | Payment per insulation installed to specified thickness | Per m²/Lm installed | Payment per insulation installed to specified thickness
2.09.09 | 3 | Comms Room AC (AC-COMMS) | A2.09.09 | No. |  | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  |  | Equipment installed, Ductwork complete, Commissioning passed | Payment based on % complete verified by Services Engineer | % complete measured monthly | Payment based on % complete verified by Services Engineer
2.09.10 | 3 | Mechanical Testing & Commissioning | A2.09.10 | Lot | 1 | SOW 3.10 | Cl 7, 30 |  |  |  | M0000 to M2000 |  |  |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon commissioning complete, reports accepted | Milestone | 100% upon commissioning complete, reports accepted
2.1 | 2 | ELECTRICAL SERVICES | A2.10 | [12 empty] | Installation complete, Tests passed, Certificates issued | Subsection Deliverables Accepted
2.10.01 | 3 | Main Switchboard & Distribution | A2.10.01 | No. |  | SOW 3.11.1 | Cl 7, 30 |  |  |  |  | E8000, E8001 |  |  |  | Installation complete, Tests passed, Certificates issued | Payment per switchboard installed, connected, tested and labelled | Per board installed | Payment per switchboard installed, connected, tested and labelled
2.10.02 | 3 | Sub-Distribution & Circuits | A2.10.02 | Lot | 1 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  |  | Sub-Distribution & Circuits - Complete | Payment based on % complete verified by Services Engineer | % complete measured monthly | Payment based on % complete verified by Services Engineer
2.10.03 | 3 | General Power Outlets | A2.10.03 | No. |  | SOW 3.11.5 | Cl 7, 30 |  |  |  |  | E2000, E2001 |  |  |  | Installation complete, Tests passed, Certificates issued | Payment per GPO/outlet installed, tested and labelled | Per point installed | Payment per GPO/outlet installed, tested and labelled
2.10.04 | 3 | Lighting - Internal | A2.10.04 | No. |  | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  |  | Installation complete, Tests passed, Certificates issued | Payment per luminaire installed, connected and operational | Per fitting installed | Payment per luminaire installed, connected and operational
2.10.05 | 3 | Lighting - External | A2.10.05 | No. |  | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  |  | Installation complete, Tests passed, Certificates issued | Payment per luminaire installed, connected and operational | Per fitting installed | Payment per luminaire installed, connected and operational
2.10.06 | 3 | Emergency Lighting & Exit Signs | A2.10.06 | No. |  | SOW 3.11.4 | Cl 7, 30 |  |  |  |  | E1000 |  |  |  | Installation complete, Tests passed, Certificates issued | Payment per luminaire installed, connected and operational | Per fitting installed | Payment per luminaire installed, connected and operational
2.10.07 | 3 | Lightning Protection & Earthing | A2.10.07 | Lot | 1 | SOW 3.11.9 | Cl 7, 30 |  |  |  |  | E8000 |  |  |  | Lightning Protection & Earthing - Complete | Payment based on % complete verified by Services Engineer | % complete measured monthly | Payment based on % complete verified by Services Engineer
2.10.08 | 3 | Data & Communications Cabling | A2.10.08 | Lm |  | SOW 3.11.6 | Cl 7, 30 |  |  |  |  | E2000 |  |  |  | Data & Communications Cabling - Complete | Payment per data point installed, terminated and tested | Per point installed | Payment per data point installed, terminated and tested
2.10.09 | 3 | Security Systems Infrastructure | A2.10.09 | Lot | 1 | SOW 3.11.7 | Cl 7, 30 |  |  |  |  | E2000 |  |  |  | Security Systems Infrastructure - Complete | Payment per security device installed and operational | Per device installed | Payment per security device installed and operational
2.10.10 | 3 | Access Control & CCTV | A2.10.10 | Lot | 1 | SOW 3.11.7 | Cl 7, 30 |  |  |  |  | E2000 |  |  |  | Access Control & CCTV - Complete | Payment per security device installed and operational | Per device installed | Payment per security device installed and operational
2.10.11 | 3 | Fire Detection & Alarm System | A2.10.11 | Lot | 1 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  |  | Equipment installed, System commissioned, Certificates issued | Payment per device installed, connected to FACP and tested | Per device installed | Payment per device installed, connected to FACP and tested
2.10.12 | 3 | Electrical Testing & Commissioning | A2.10.12 | Lot | 1 | SOW 3.11 | Cl 7, 30 |  |  |  |  | E0000 to E8002 |  |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon commissioning complete, test certificates issued | Milestone | 100% upon commissioning complete, test certificates issued
2.11 | 2 | HYDRAULIC SERVICES | A2.11 |  |  | SOW 3.12 | Cl 7, 30 | [8 empty] | Pipework complete, Pressure tests passed, Fixtures installed | Subsection Deliverables Accepted
2.11.01 | 3 | Cold Water Reticulation | A2.11.01 | Lm |  | SOW 3.12.1 | Cl 7, 30 | [5 empty] | H2000, H6001 |  |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment per Lm water pipe installed, pressure tested, chlorinated | Per linear metre installed | Payment per Lm water pipe installed, pressure tested, chlorinated
2.11.02 | 3 | Hot Water Systems | A2.11.02 | No. |  | SOW 3.12.2 | Cl 7, 30 | [5 empty] | H0003, H6001 |  |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment per Lm water pipe installed, pressure tested, chlorinated | Per linear metre installed | Payment per Lm water pipe installed, pressure tested, chlorinated
2.11.03 | 3 | Sanitary Plumbing | A2.11.03 | Lot | 1 | SOW 3.12.3 | Cl 7, 30 | [5 empty] | H1000, H6000 |  |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment based on % complete verified by Hydraulic Engineer | % complete measured monthly | Payment based on % complete verified by Hydraulic Engineer
2.11.04 | 3 | Sanitary Drainage | A2.11.04 | Lm |  | SOW 3.12.3 | Cl 7, 30 | [5 empty] | H1000, H6000 |  |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment per Lm drainage installed, tested (air/water) and accepted | Per linear metre installed | Payment per Lm drainage installed, tested (air/water) and accepted
2.11.05 | 3 | Roof Drainage | A2.11.05 | Lm |  | SOW 3.12.3 | Cl 7, 30 | [5 empty] | H1000, H6000 |  |  | Installation records, Weather sealing tests | Payment per Lm drainage installed, tested (air/water) and accepted | Per linear metre installed | Payment per Lm drainage installed, tested (air/water) and accepted
2.11.06 | 3 | Backflow Prevention | A2.11.06 | No. |  | SOW 3.12.6 | Cl 7, 30 | [5 empty] | H0003, H8000 |  |  | Backflow Prevention - Complete | Payment per backflow device installed, tested and registered | Per device installed | Payment per backflow device installed, tested and registered
2.11.07 | 3 | Hydraulic Penetrations & Supports | A2.11.07 | Lot | 1 | SOW 3.12 | Cl 7, 30 | [5 empty] | H0000 to H9000 |  |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment based on % complete verified by Hydraulic Engineer | % complete measured monthly | Payment based on % complete verified by Hydraulic Engineer
2.11.08 | 3 | Hydraulic Testing & Certification | A2.11.08 | Lot | 1 | SOW 3.12 | Cl 7, 30 | [5 empty] | H0000 to H9000 |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon commissioning complete, test certificates issued | Milestone | 100% upon commissioning complete, test certificates issued
2.11.09 | 3 | Authority Inspections - Plumbing | A2.11.09 | Lot | 1 | SOW 3.12 | Cl 7, 30 | [5 empty] | H0000 to H9000 |  |  | Test reports, Commissioning certificates, Inspection records | Payment based on % complete verified by Hydraulic Engineer | % complete measured monthly | Payment based on % complete verified by Hydraulic Engineer
2.12 | 2 | FIRE SERVICES | A2.12 |  |  | SOW 3.13 | Cl 7, 30 | [8 empty] | Equipment installed, System commissioned, Certificates issued | Subsection Deliverables Accepted
2.12.01 | 3 | Fire Hydrant System | A2.12.01 | Lot | 1 | SOW 3.13.2 | Cl 7, 30 | [5 empty] | H2000, H4000 |  |  | Equipment installed, System commissioned, Certificates issued | Payment per hydrant/hose reel installed, flow tested | Per outlet installed | Payment per hydrant/hose reel installed, flow tested
2.12.02 | 3 | Fire Hose Reels | A2.12.02 | No. |  | SOW 3.13.2 | Cl 7, 30 | [5 empty] | H2000, H4000 |  |  | Equipment installed, System commissioned, Certificates issued | Payment per hydrant/hose reel installed, flow tested | Per outlet installed | Payment per hydrant/hose reel installed, flow tested
2.12.03 | 3 | Fire Indicator Panel (FIP) | A2.12.03 | No. |  | SOW 3.13.1 | Cl 7, 30 |  |  |  |  | E1000, E8000 |  |  |  | Equipment installed, System commissioned, Certificates issued | Payment based on % complete verified by Fire Engineer | % complete measured monthly | Payment based on % complete verified by Fire Engineer
2.12.04 | 3 | Fire Services Testing & Certification | A2.12.04 | Lot | 1 | SOW 3.13 | Cl 7, 30 | [8 empty] | Test reports, Commissioning certificates, Inspection records | 100% upon fire system commissioning and Form 65/compliance certificate issued | Milestone | 100% upon fire system commissioning and Form 65/compliance certificate issued
2.13 | 2 | TESTING, COMMISSIONING & HANDOVER | A2.13 |  |  | SOW 11.0 | Cl 30, 42 | [8 empty] | Test reports, Commissioning certificates, Inspection records | Subsection Deliverables Accepted
2.13.01 | 3 | Commissioning Plan Development | A2.13.01 | Lot | 1 | SOW 11.0 | Cl 30, 42 | [8 empty] | Approved Plan Document, Implementation evidence | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.02 | 3 | Pre-Commissioning Checklists | A2.13.02 | Lot | 1 | SOW 11.0 | Cl 30, 42 | [8 empty] | Test reports, Commissioning certificates, Inspection records | 100% upon IST complete and report accepted | Milestone | 100% upon IST complete and report accepted
2.13.03 | 3 | Mechanical Testing & Balancing | A2.13.03 | Lot | 1 | SOW 11.1 | Cl 30 |  |  |  | M0001 |  |  |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.04 | 3 | Electrical Testing | A2.13.04 | Lot | 1 | SOW 11.1 | Cl 30 |  |  |  |  | E0001 |  |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.05 | 3 | Hydraulic Pressure Testing | A2.13.05 | Lot | 1 | SOW 11.1 | Cl 30 | [5 empty] | H0002 |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.06 | 3 | Fire Systems Testing | A2.13.06 | Lot | 1 | SOW 11.1 | Cl 30 |  |  |  |  | E1000 | H4000 |  |  | Test reports, Commissioning certificates, Inspection records | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.07 | 3 | Integrated Systems Testing | A2.13.07 | Lot | 1 | SOW 11.1 | Cl 30 | [8 empty] | Test reports, Commissioning certificates, Inspection records | 100% upon IST complete and report accepted | Milestone | 100% upon IST complete and report accepted
2.13.08 | 3 | O&M Manuals | A2.13.08 | Lot | 1 | SOW 11.3 | Cl 8, 30.6 | [8 empty] | O&M Manuals - Complete | 100% upon O&M manuals submitted and accepted | Milestone | 100% upon O&M manuals submitted and accepted
2.13.09 | 3 | Warranties & Guarantees | A2.13.09 | Lot | 1 | SOW 11.0 | Cl 30, 42 | [8 empty] | Warranties & Guarantees - Complete | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.10 | 3 | Asset Registers | A2.13.10 | Lot | 1 | SOW 11.0 | Cl 30, 42 | [8 empty] | Asset Registers - Complete | 100% upon IST complete and report accepted | Milestone | 100% upon IST complete and report accepted
2.13.11 | 3 | Training Delivery | A2.13.11 | Lot | 1 | SOW 11.2 | Cl 30.6 | [8 empty] | Induction records, Training certificates, Competency registers | Payment per training session completed with attendance records | Per session conducted | Payment per training session completed with attendance records
2.13.12 | 3 | Final MDR Compilation | A2.13.12 | Lot | 1 | SOW 11.0 | Cl 30, 42 | [8 empty] | Final MDR Compilation - Complete | 100% upon testing/commissioning activity complete and accepted | Milestone | 100% upon testing/commissioning activity complete and accepted
2.13.13 | 3 | PC Inspections & Punch List | A2.13.13 | Lot | 1 | SOW 11.0 | Cl 30, 42 | [8 empty] | Test reports, Commissioning certificates, Inspection records | 100% upon IST complete and report accepted | Milestone | 100% upon IST complete and report accepted
2.14 | 2 | LANDSCAPING | A2.14 |  |  | SOW 3.14 | Cl 7, 30 | [8 empty] | LANDSCAPING - Complete | Subsection Deliverables Accepted
2.14.01 | 3 | Site Preparation for Landscaping | A2.14.01 | Lot | 1 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Site Preparation for Landscaping - Complete | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.02 | 3 | Trees Supply & Plant | A2.14.02 | No. |  | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.01, L2.01 to L2.04 |  | Approved Plan Document, Implementation evidence | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.03 | 3 | Shrubs Supply & Plant | A2.14.03 | No. |  | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Approved Plan Document, Implementation evidence | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.04 | 3 | Ground Cover Supply & Plant | A2.14.04 | No. |  | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Approved Plan Document, Implementation evidence | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.05 | 3 | Turf Supply & Install | A2.14.05 | m² |  | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.01, L0.02 |  | Planting complete, Irrigation tested, Establishment period | Payment per m² turf laid / per plant installed as per landscape plan | Per m² / per plant | Payment per m² turf laid / per plant installed as per landscape plan
2.14.06 | 3 | Mulching | A2.14.06 | m² |  | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.02 |  | Mulching - Complete | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.07 | 3 | Garden Edging | A2.14.07 | Lm |  | SOW 3.14.2 | Cl 7, 30 | [6 empty] | L0.01, L2.01 to L2.05 |  | Planting complete, Irrigation tested, Establishment period | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.08 | 3 | Gravel Areas | A2.14.08 | m² |  | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Gravel Areas - Complete | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.09 | 3 | Boulder Features | A2.14.09 | No. |  | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Boulder Features - Complete | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.10 | 3 | Landscape Seating | A2.14.10 | No. |  | SOW 3.14.5 | Cl 7, 30 | [6 empty] | L0.02, L0.03 |  | Planting complete, Irrigation tested, Establishment period | Payment per landscape furniture item installed and accepted | Per item installed | Payment per landscape furniture item installed and accepted
2.14.11 | 3 | Water Features | A2.14.11 | No. |  | SOW 3.14.6 | Cl 7, 30 | [6 empty] | L0.02, L0.03, L3.01 to L3.03 |  | Pipework complete, Pressure tests passed, Fixtures installed | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.12 | 3 | Artwork Installation | A2.14.12 | No. |  | SOW 3.14.7 | Cl 7, 30 | [6 empty] | L0.02, L0.03 |  | Artwork Installation - Complete | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.13 | 3 | Irrigation System | A2.14.13 | Lot | 1 | SOW 3.14.3 | Cl 7, 30 | [5 empty] | H0003 | L1.01 to L1.04 |  | Irrigation System - Complete | 100% upon irrigation system installed, tested and operational | Lump sum on completion | 100% upon irrigation system installed, tested and operational
2.14.14 | 3 | Landscape Lighting | A2.14.14 | No. |  | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Installation complete, Tests passed, Certificates issued | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.15 | 3 | Courtyard Landscaping | A2.14.15 | m² |  | SOW 3.14.4 | Cl 7, 30 | A-710005 | [5 empty] | L1.05, L2.05 |  | Courtyard Landscaping - Complete | Payment based on % landscaping complete verified by inspection | % complete measured monthly | Payment based on % landscaping complete verified by inspection
2.14.16 | 3 | Landscape Establishment & Maintenance | A2.14.16 | Lot | 1 | SOW 3.14 | Cl 7, 30 | [6 empty] | L0.00 to L4.02 |  | Planting complete, Irrigation tested, Establishment period | Monthly payment during establishment period subject to plant health | Pro-rata monthly | Monthly payment during establishment period subject to plant health
2.15 | 2 | DEMOBILISATION & CLOSE-OUT | A2.15 |  |  | SOW 12.0 | Cl 42 | [8 empty] | Site established, Facilities operational | Subsection Deliverables Accepted
2.15.01 | 3 | Temporary Works Removal | A2.15.01 | Lot | 1 | SOW 12.1 | Cl 42 | [8 empty] | Temporary Works Removal - Complete | 100% upon mobilisation item complete and accepted | Milestone | 100% upon mobilisation item complete and accepted
2.15.02 | 3 | Site Reinstatement | A2.15.02 | Lot | 1 | SOW 12.3 | Cl 42 | [8 empty] | Site Reinstatement - Complete | 100% upon mobilisation item complete and accepted | Milestone | 100% upon mobilisation item complete and accepted
2.15.03 | 3 | Final Cleaning | A2.15.03 | Lot | 1 | SOW 12.2 | Cl 12.3, 42 | [8 empty] | Final Cleaning - Complete | 100% upon mobilisation item complete and accepted | Milestone | 100% upon mobilisation item complete and accepted
2.15.04 | 3 | As-Built Documentation | A2.15.04 | Lot | 1 | SOW 12.4 | Cl 8, 42 | [8 empty] | As-Built Documentation - Complete | 100% upon mobilisation item complete and accepted | Milestone | 100% upon mobilisation item complete and accepted
2.15.05 | 3 | Defects Rectification Support | A2.15.05 | Lot | 1 | SOW 12.0 | Cl 42 | [8 empty] | Defects Rectification Support - Complete | 100% upon mobilisation item complete and accepted | Milestone | 100% upon mobilisation item complete and accepted
3 | 0 | Section B - Provisional Sum Items | PS | [12 empty] | As directed by Principal, Supporting documentation | Practical Completion Certificate
3 | 1 | PROVISIONAL SUMS | PS0 | [12 empty] | As directed by Principal, Supporting documentation | Section Complete
3 | 2 | SITE CONDITIONS | PS0.0 |  |  | SOW 3.7.1 | Cl 26, 27, 36 | [8 empty] | SITE CONDITIONS - Complete | Subsection Deliverables Accepted
3.0.06 | 3 | Latent Conditions Allowance | PS0.0.06 | Lot | 1 | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 | [5 empty] | As directed by Principal, Supporting documentation | Per approved Variation | As directed | Per approved Variation
3.0.07 | 3 | Rock Excavation Allowance | PS0.0.07 | m³ |  | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 | [5 empty] | Survey records, Compaction tests, Level verification | Per approved Variation | Per m³ rock | Per approved Variation
3.0.08 | 3 | Contaminated Soil Allowance | PS0.0.08 | m³ |  | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 | [5 empty] | As directed by Principal, Supporting documentation | Per approved Variation | Per m³ disposed | Per approved Variation
3 | 2 | HAZMAT | PS0.0 |  |  | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 | [5 empty] | HAZMAT - Complete | Subsection Deliverables Accepted
3.0.10 | 3 | Additional Asbestos Removal | PS0.0.10 | m² |  | SOW 3.7.1 | Cl 26, 27, 36 |  | S2.01 | C02, C03, C04 | [5 empty] | Additional Asbestos Removal - Complete | Per approved Variation | Per m² removed | Per approved Variation
3.0.11 | 3 | Lead Paint Removal | PS0.0.11 | m² |  | SOW 3.6, 9.3 | Cl 12.3, 26, 27 | [8 empty] | Prep complete, Coats applied, DFT verified | Per approved Variation | Per m² removed | Per approved Variation
3.0.12 | 3 | Synthetic Mineral Fibre Removal | PS0.0.12 | m² |  | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 | [5 empty] | Synthetic Mineral Fibre Removal - Complete | Per approved Variation | Per m² removed | Per approved Variation
3 | 2 | SERVICES | PS0.0 |  |  | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 | [5 empty] | SERVICES - Complete | Subsection Deliverables Accepted
3.0.14 | 3 | Electrical Services Diversion | PS0.0.14 | Lot | 1 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 | [5 empty] | Installation complete, Tests passed, Certificates issued | Per approved Variation | As directed | Per approved Variation
3.0.15 | 3 | Hydraulic Services Diversion | PS0.0.15 | Lot | 1 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 | [5 empty] | Pipework complete, Pressure tests passed, Fixtures installed | Per approved Variation | As directed | Per approved Variation
3.0.16 | 3 | Communications/Data Diversion | PS0.0.16 | Lot | 1 | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 | [5 empty] | Communications/Data Diversion - Complete | Per approved Variation | As directed | Per approved Variation
3 | 2 | DESIGN | PS0.0 |  |  | SOW 3.6, 9.3 | Cl 12.3, 26, 27 |  |  | C02, C04, C05 | [5 empty] | IFC Drawings, Shop Drawings, As-built Drawings | Subsection Deliverables Accepted
3.0.18 | 3 | Architectural Design Development | PS0.0.18 | Lot | 1 | SOW 3.0 | Cl 26, 27 | [8 empty] | IFC Drawings, Shop Drawings, As-built Drawings | Per approved Variation | As directed | Per approved Variation
3.0.19 | 3 | Structural Design Development | PS0.0.19 | Lot | 1 | SOW 3.0 | Cl 26, 27 | [8 empty] | IFC Drawings, Shop Drawings, As-built Drawings | Per approved Variation | As directed | Per approved Variation
3.0.20 | 3 | Services Design Development | PS0.0.20 | Lot | 1 | SOW 3.0 | Cl 26, 27 | [8 empty] | IFC Drawings, Shop Drawings, As-built Drawings | Per approved Variation | As directed | Per approved Variation
3 | 2 | CONTINGENCY | PS0.0 |  |  | SOW 3.0 | Cl 26, 27 | [8 empty] | As directed by Principal, Supporting documentation | Subsection Deliverables Accepted
3.0.22 | 3 | General Contingency Allowance | PS0.0.22 | Lot | 1 | SOW 3.0 | Cl 26, 27 | [8 empty] | As directed by Principal, Supporting documentation | Per approved Variation | As directed | Per approved Variation
3.0.23 | 3 | Interface Coordination Allowance | PS0.0.23 | Lot | 1 | SOW 3.0 | Cl 26, 27 | [8 empty] | As directed by Principal, Supporting documentation | Per approved Variation | As directed | Per approved Variation
3.0.24 | 3 | Inclement Weather Allowance | PS0.0.24 | Days |  | SOW 3.0 | Cl 26, 27 | [8 empty] | As directed by Principal, Supporting documentation | Per approved Variation | Per qualifying day | Per approved Variation
3 | 2 | AV WORKS | PS0.0 |  |  | SOW 3.0 | Cl 36, 38, 41 | [8 empty] | Infrastructure provisions, Coordination records | Subsection Deliverables Accepted
3.0.26 | 3 | AV Contractor Attendance | PS0.0.26 | Days |  | SOW 3.0 | Cl 36, 38, 41 | [8 empty] | Infrastructure provisions, Coordination records | Per approved Variation | Per week attendance | Per approved Variation
3.0.27 | 3 | AV Power & Data Points | PS0.0.27 | No. |  | SOW 3.0 | Cl 36, 38, 41 | [8 empty] | Installation complete, Tests passed, Certificates issued | Per approved Variation | Per point installed | Per approved Variation
WBS ALIGNMENT SUMMARY
Metric | Count | Status | Notes
Total Pay Table Items | 224 | ✅ | Excluding header
Total WBS Items | 224 | ✅ | Excluding header
Level 0 Items (Contract Sum) | 2 |  | Top level
Level 1 Items (Sections) | 3 |  | A1, A2, PS
Level 2 Items (Categories) | 26 |  | Sub-sections
Level 3 Items (Line Items) | 193 |  | Pricing items
Alignment Status | EXACT MATCH | ✅ | All Pay Table items mapped to WBS
REFERENCE KEY
Reference | Description | Drawing Range | Consultant
SOW Ref | Scope of Work sections | SOW 3.0 - 12.0 | Stanwell
Contract Clause | AS4000-1997 Amended contract clauses | Cl 5 - 42 | Legal
Architectural Dwg | A-series drawings | A-000001 to A-910001 | M3 Architecture / BH Architect
Structural Dwg | S-series drawings | S1.01 to S9.02 | Janes & Stewart Structures
Civil Dwg | C-series drawings | C01 to C104 | Janes & Stewart Structures
Mechanical Dwg | M-series drawings | M0000 to M2000 | JHA Consulting Engineers
Electrical Dwg | E-series drawings | E0000 to E8002 | JHA Consulting Engineers
Hydraulic Dwg | H-series drawings | H0000 to H9000 | JHA Consulting Engineers
Landscape Dwg | L-series drawings | L0.00 to L4.02 | Subtropic Design
CONTRACT CLAUSE KEY (AS4000-1997 Amended)
Clause | Description
Cl 5 | Subcontracting
Cl 7 | Site Management
Cl 7A | Design by Contractor
Cl 8 | Documents
Cl 12 | WHS/Safety
Cl 21 | Authorities & Approvals
Cl 22, 23 | Superintendence
Cl 26, 27 | Latent Conditions
Cl 29 | Quality Assurance
Cl 30 | Inspections & Testing
Cl 32 | Programs
Cl 35, 35A | Warranties & Defects
Cl 36, 38, 41 | Variations
Cl 37 | Payments
Cl 42 | Practical Completion

## Numbering
L1 | L1 Description (Cost Area) | L2 | L2 Description (Area) | L3 | L3 Description (Sub Area) | L4 | L4 Description (Activity / comoditity))
CS | Contract Sum | 1 | INDIRECT COSTS
|  |  |  | 01 | PROJECT MANAGEMENT & GOVERNANCE
|  |  |  | 02 | HSE (WHS / ENVIRONMENTAL)
|  |  |  | 03 | QUALITY MANAGEMENT SYSTEM
|  |  |  | 04 | DESIGN & ENGINEERING
|  |  |  | 05 | AUTHORITIES & APPROVALS
A | Section A - Lump Sum | 2 | DIRECT COSTS | 01 | PROCUREMENT & SUBCONTRACTING
|  |  |  | 02 | OFF-SITE FABRICATION
|  |  |  | 03 | LOGISTICS, DELIVERIES & LAYDOWN
|  |  |  | 04 | MOBILISATION & TEMPORARY WORKS
|  |  |  | 05 | DEMOLITION & REMOVAL WORKS
|  |  |  | 06 | CIVIL, EARTHWORKS & EXTERNAL WORKS
|  |  |  | 07 | BUILDING STRUCTURE & ENVELOPE
|  |  |  | 08 | ARCHITECTURAL FIT-OUT (INTERNAL WORKS)
|  |  |  | 09 | MECHANICAL SERVICES
|  |  |  | 10 | ELECTRICAL SERVICES
|  |  |  | 11 | HYDRAULIC SERVICES
|  |  |  | 12 | FIRE SERVICES
|  |  |  | 13 | TESTING, COMMISSIONING & HANDOVER
|  |  |  | 14 | LANDSCAPING
|  |  |  | 15 | DEMOBILISATION & CLOSE-OUT
PS | Section B - Provisional Sum Items | 1 | PROVISIONAL SUMS
|  |  |  | 01 | ROCK EXCAVATION
|  |  |  | 02 | CONTAMINATED MATERIAL
|  |  |  | 03 | LATENT CONDITIONS
|  |  |  | 04 | PRINCIPAL VARIATIONS
|  |  |  | 05 | AV SYSTEMS
V | Variations

## SOW Cross-Reference
SOW CROSS-REFERENCE MATRIX - SPS New Project Building
RFT # 1221995761 - Stanwell Power Station - 397 Power Station Road, Stanwell QLD 4702
Pay Item No. | Description | Level | Category | Sub-Category | SOW Section | SOW Title | SOW Clause Detail | Contract Clause | Contract Clause Title | Arch Dwg | Struct Dwg | Civil Dwg | Mech Dwg | Elec Dwg | Hyd Dwg | Land Dwg | Primary Deliverable | Acceptance Criteria | Notes
A1 | INDIRECT COSTS | 1 | Section A - Lump Sum
A1.01 | PROJECT MANAGEMENT & GOVERNANCE | 2 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | Management of all project activities | Cl 22, 23 | Superintendence | [7 empty] | Management Plans | Plans accepted by Principal
A1.01.01 | Project Director | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0, 7.1 | Project Management | 7.1 Personnel Requirements | Cl 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly | Senior oversight
A1.01.02 | Project Manager | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0, 7.1 | Project Management | 7.1 Personnel Requirements | Cl 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.03 | Site Manager / Superintendent | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0, 7.1 | Project Management | 7.1 Personnel Requirements | Cl 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.04 | Construction Manager | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0, 7.1 | Project Management | 7.1 Personnel Requirements | Cl 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.05 | Assistant Site Manager | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0, 9.0 | Project Management | 7.1 Personnel Requirements | Cl 12, 22, 23 | Superintendence / WHS | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.06 | Project Engineer | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0, 10.0 | Project Management | 7.1 Personnel Requirements | Cl 29, 22, 23 | Quality / Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.07 | Senior Engineer | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 8, 22, 23 | Documents / Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.08 | Graduate Engineer | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 37, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.09 | Design Engineer | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 37, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.10 | Services Engineer (Mech/Elec/Hyd) | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 32, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.11 | Site Foreman / Supervisor | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 32, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.12 | Leading Hand | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 32, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.13 | Works Coordinator | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 32, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.14 | Night Shift Supervisor | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 32, 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly | Shift loading included
A1.01.15 | Subcontractor Coordinator | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 5, 22, 23 | Subcontracting | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.16 | Document Controller | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 8, 22, 23 | Documents | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.17 | Contract Administrator | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 37, 22, 23 | Payments | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.18 | Cost Controller / Estimator | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 37, 22, 23 | Payments | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.19 | Scheduler / Planner | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 32, 22, 23 | Programs | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.01.20 | Project Administrator | 3 | INDIRECT COSTS | PROJECT MANAGEMENT | SOW 7.0 | Project Management | 7.1 Personnel Requirements | Cl 22, 23 | Superintendence | [7 empty] | Personnel on site | Timesheets submitted monthly
A1.02 | HSE (WHS / ENVIRONMENTAL) | 2 | INDIRECT COSTS | HSE | SOW 9.0 | Health Safety Environment | WHS & Environmental Management | Cl 12 | Work Health & Safety |  |  | C05, C104 |  |  |  |  | HSE Plans | Plans accepted
A1.02.01 | WHS Management System | 3 | INDIRECT COSTS | HSE | SOW 9.1 | WHS Management | 9.1.1 WHSMP Requirements | Cl 12.3, 12.5 | WHS Plans |  |  | C05 |  |  |  |  | WHSMP Document | Plan accepted by Principal
A1.02.02 | Permits and Controls | 3 | INDIRECT COSTS | HSE | SOW 9.2 | WHS Management | 9.2 Permit System | Cl 12.4 | WHS Permits | [7 empty] | Permit Register | Permits issued and controlled
A1.02.03 | Environmental Management (CEMP) | 3 | INDIRECT COSTS | HSE | SOW 9.3 | Environmental Management | 9.3 CEMP Requirements | Cl 12.3 | Environmental |  |  | C05, C104 |  |  |  |  | CEMP Document | Plan accepted by Principal
A1.02.04 | SWMS Development & Approvals | 3 | INDIRECT COSTS | HSE | SOW 9.1 | WHS Management | 9.1.2 SWMS Requirements | Cl 12.3 | WHS Plans | [7 empty] | Approved SWMS | SWMS approved before work
A1.02.05 | Site Inductions & Competency | 3 | INDIRECT COSTS | HSE | SOW 9.1 | WHS Management | 9.1.3 Induction Requirements | Cl 12.3, 12.4 | WHS Inductions | [7 empty] | Induction Records | All personnel inducted
A1.02.06 | Incident Management & Reporting | 3 | INDIRECT COSTS | HSE | SOW 9.1 | WHS Management | 9.1.4 Incident Reporting | Cl 12.9 | Incident Reports | [7 empty] | Incident Register | Reports within 24hrs
A1.02.07 | Traffic Management Plan | 3 | INDIRECT COSTS | HSE | SOW 9.2, 3.4 | WHS Management | 9.2 Traffic Management | Cl 12.6 | Traffic Control |  |  | C02, C03 |  |  |  |  | TMP Document | Plan accepted
A1.03 | QUALITY MANAGEMENT SYSTEM | 2 | INDIRECT COSTS | QUALITY | SOW 10.0 | Quality Management | Quality Assurance Requirements | Cl 29 | Quality Assurance | [7 empty] | QA Plans | Plans accepted
A1.03.01 | Quality Management Plan (QMP) | 3 | INDIRECT COSTS | QUALITY | SOW 10.0, 10.1 | Quality Management | 10.1 QMP Requirements | Cl 29.2 | QA Plans | [7 empty] | QMP Document | Plan accepted by Principal
A1.03.02 | Inspection & Test Plans (ITPs) | 3 | INDIRECT COSTS | QUALITY | SOW 10.2 | Quality Management | 10.2 ITP Requirements | Cl 29.2, 30 | QA/Inspection | A-All | S-All | C-All | M-All | E-All | H-All | L-All | Approved ITPs | ITPs approved before work
A1.03.03 | Non-Conformance & Corrective Actions | 3 | INDIRECT COSTS | QUALITY | SOW 10.3, 10.4 | Quality Management | 10.3 NCR Process | Cl 29.3 | Non-Conformance | [7 empty] | NCR Register | NCRs closed out
A1.03.04 | Witness & Hold Point Inspections | 3 | INDIRECT COSTS | QUALITY | SOW 10.5 | Quality Management | 10.5 Inspections | Cl 30 | Inspections | [7 empty] | Inspection Records | All hold points released
A1.03.05 | MDR Records | 3 | INDIRECT COSTS | QUALITY | SOW 10.6 | Quality Management | 10.6 MDR Requirements | Cl 30.6 | Records | [7 empty] | MDR Package | Records complete
A1.04 | DESIGN & ENGINEERING | 2 | INDIRECT COSTS | DESIGN | SOW 5.0 | Design Responsibility | Contractor Design Requirements | Cl 7A | Design by Contractor | A-All | S-All | C-All | M-All | E-All | H-All | L-All | Design Deliverables | Design approved
A1.04.01 | Design Management & Coordination | 3 | INDIRECT COSTS | DESIGN | SOW 5.0, 3.5 | Design Responsibility | 5.1 Design Coordination | Cl 7A | Design by Contractor | A-All | S-All | C-All | M-All | E-All | H-All | L-All | Design Schedule | Design reviews completed
A1.04.02 | Contractor Design Deliverables | 3 | INDIRECT COSTS | DESIGN | SOW 5.0, 3.5 | Design Responsibility | 5.2 Deliverables | Cl 7A.2 | Design Documentation | A-All | S-All | C-All | M-All | E-All | H-All | L-All | IFC Drawings | IFC issue accepted
A1.04.03 | Shop Drawings - All Disciplines | 3 | INDIRECT COSTS | DESIGN | SOW 3.5, 7.4 | Design Responsibility | 5.3 Shop Drawings | Cl 7A.3, 8.3 | Shop Drawings | A-780 | S1.01-S9.02 |  | M0002-M0004 | E0001-E0003 | H0002-H0003 |  | Shop Drawings | Drawings approved
A1.05 | AUTHORITIES & APPROVALS | 2 | INDIRECT COSTS | APPROVALS | SOW 6.0 | Authority Approvals | Statutory Approvals | Cl 21 | Authorities & Approvals | A-070001 | [6 empty] | Approval Documents | Approvals obtained
A1.05.01 | Building Approval Coordination | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0, 6.1 | Authority Approvals | 6.1 Building Approval | Cl 11 | Approvals | A-070001 | [6 empty] | BA Application | BA approved | NCC Class 5
A1.05.02 | Authority Inspections & Certifications | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0, 6.2 | Authority Approvals | 6.2 Inspections | Cl 11 | Inspections | [7 empty] | Inspection Records | All inspections passed
A1.05.03 | Council / Local Authority Coordination | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0, 6.3 | Authority Approvals | 6.3 Council Liaison | Cl 11 | Council Approvals | [7 empty] | Council Approvals | Approvals obtained
A1.05.04 | Utility Authority Coordination | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0 | Authority Approvals | 6.4 Utilities | Cl 11 | Utility Approvals |  |  | C03 |  | E0010 | H0010 |  | Utility Applications | Connections approved | Power/Water/Comms
A1.05.05 | Fire Authority Approval (QFES) | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0 | Authority Approvals | 6.5 Fire Authority | Cl 11 | Fire Approvals |  |  |  |  | E1000 | H4000 |  | QFES Application | Fire approval obtained
A1.05.06 | Occupancy Certificate | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0 | Authority Approvals | 6.6 Occupancy | Cl 11, 34.6 | Occupancy | [7 empty] | OC Application | OC issued
A1.05.07 | Form 21 / Final Certificate | 3 | INDIRECT COSTS | APPROVALS | SOW 6.0 | Authority Approvals | 6.7 Final Certificate | Cl 11 | Final Cert | [7 empty] | Form 21 | Certificate issued
A2 | DIRECT COSTS | 1 | Section A - Lump Sum
A2.01 | PROCUREMENT & SUBCONTRACTING | 2 | DIRECT COSTS | PROCUREMENT | SOW 4.0 | Procurement | Procurement Requirements | Cl 5 | Subcontracting | [7 empty] | Procurement Plan | Plan accepted
A2.01.01 | Subcontractor Procurement | 3 | DIRECT COSTS | PROCUREMENT | SOW 4.1 | Procurement | 4.1 Subcontractor Selection | Cl 5.1 | Subcontracting | [7 empty] | Subcontract Packages | Subcontracts executed
A2.01.02 | Material Procurement | 3 | DIRECT COSTS | PROCUREMENT | SOW 4.2 | Procurement | 4.2 Materials Procurement | Cl 5.2 | Materials | [7 empty] | Purchase Orders | Materials ordered
A2.01.03 | Long Lead Items | 3 | DIRECT COSTS | PROCUREMENT | SOW 4.3 | Procurement | 4.3 Long Lead Items | Cl 5.3 | Long Lead |  |  |  | M0001 | E0001 | H0003 |  | LLI Schedule | Items ordered on time | HVAC, Switchboards
A2.02 | OFF-SITE FABRICATION | 2 | DIRECT COSTS | FABRICATION | SOW 5.0 | Fabrication | Module Fabrication | Cl 5, 29, 30 | Fabrication | A-910001 | S1.01-S1.02 | [5 empty] | Fabrication Plan | QA approved | MMC Modules
A2.02.01 | Module Fabrication QA | 3 | DIRECT COSTS | FABRICATION | SOW 5.1 | Fabrication | 5.1 QA Requirements | Cl 29, 30 | Quality | A-910001 | S1.01-S1.02 | [5 empty] | Factory ITPs | Factory inspections passed
A2.02.02 | Pre-Delivery Inspections | 3 | DIRECT COSTS | FABRICATION | SOW 5.2 | Fabrication | 5.2 Pre-Delivery | Cl 30 | Inspections | A-910001 | [6 empty] | Inspection Reports | Modules released
A2.03 | LOGISTICS, DELIVERIES & LAYDOWN | 2 | DIRECT COSTS | LOGISTICS | SOW 3.4 | Logistics | Transport & Laydown | Cl 7, 12 | Site Management |  |  | C02, C03 |  |  |  |  | Logistics Plan | Plan accepted
A2.03.01 | Module Transport | 3 | DIRECT COSTS | LOGISTICS | SOW 3.4.1 | Logistics | 3.4.1 Transport | Cl 7 | Transport |  |  | C02, C03 |  |  |  |  | Transport Permits | Modules delivered
A2.03.02 | Laydown Area Management | 3 | DIRECT COSTS | LOGISTICS | SOW 3.4.2 | Logistics | 3.4.2 Laydown | Cl 7 | Laydown |  |  | C02 |  |  |  |  | Laydown Plan | Area maintained
A2.04 | MOBILISATION & TEMPORARY WORKS | 2 | DIRECT COSTS | MOBILISATION | SOW 3.3 | Site Establishment | Mobilisation | Cl 7, 7A | Site Management |  |  | C02, C03 |  | E0010 | H0010 |  | Mobilisation Plan | Site established
A2.04.01 | Site Offices & Amenities | 3 | DIRECT COSTS | MOBILISATION | SOW 3.3.1 | Site Establishment | 3.3.1 Site Facilities | Cl 7 | Facilities |  |  |  |  | E0010 | H0010 |  | Site Layout | Facilities operational
A2.04.02 | Temporary Services | 3 | DIRECT COSTS | MOBILISATION | SOW 3.3.2 | Site Establishment | 3.3.2 Temp Services | Cl 7 | Temp Services |  |  |  |  | E0010 | H0010 |  | Services connected | Power/Water available
A2.04.03 | Temporary Fencing & Hoarding | 3 | DIRECT COSTS | MOBILISATION | SOW 3.3.3 | Site Establishment | 3.3.3 Fencing | Cl 7, 12 | Security |  |  | C02 |  |  |  |  | Fencing installed | Site secured
A2.04.04 | Site Signage | 3 | DIRECT COSTS | MOBILISATION | SOW 3.3.4 | Site Establishment | 3.3.4 Signage | Cl 7, 12 | Signage | A-770001 | [6 empty] | Signage installed | Compliant signage
A2.05 | DEMOLITION & REMOVAL WORKS | 2 | DIRECT COSTS | DEMOLITION | SOW 3.6 | Demolition | Demolition Works | Cl 7, 12.3 | Demolition | A-040002 |  | C02 |  |  |  |  | Demo Plan | Demolition complete
A2.05.01 | Building Demolition | 3 | DIRECT COSTS | DEMOLITION | SOW 3.6.1 | Demolition | 3.6.1 Building Demo | Cl 7 | Demolition | A-040002 | [6 empty] | Demo complete | Site cleared | Existing structures
A2.05.02 | Services Disconnection | 3 | DIRECT COSTS | DEMOLITION | SOW 3.6.2 | Demolition | 3.6.2 Services | Cl 7 | Services |  |  |  |  | E0010 | H0010 |  | Isolation certs | Services isolated
A2.05.03 | Hazmat Removal | 3 | DIRECT COSTS | DEMOLITION | SOW 3.6.3 | Demolition | 3.6.3 Hazmat | Cl 12.3 | Hazmat | [7 empty] | Clearance certs | Hazmat removed | If encountered
A2.05.04 | Waste Disposal | 3 | DIRECT COSTS | DEMOLITION | SOW 3.6.4 | Demolition | 3.6.4 Waste | Cl 7 | Waste | [7 empty] | Waste dockets | Waste disposed
A2.06 | CIVIL, EARTHWORKS & EXTERNAL WORKS | 2 | DIRECT COSTS | CIVIL | SOW 3.7 | Civil Works | Civil & External Works | Cl 7, 30 | Civil |  | S2.01, S7.01 | C01-C06, C101-C104 |  |  |  | L1.01-L1.06 | Civil Complete | Testing passed
A2.06.01 | Site Clearing & Grubbing | 3 | DIRECT COSTS | CIVIL | SOW 3.7.1 | Civil Works | 3.7.1 Site Clearing | Cl 7 | Clearing |  |  | C02 |  |  |  |  | Clearing complete | Site cleared
A2.06.02 | Bulk Earthworks - Cut | 3 | DIRECT COSTS | CIVIL | SOW 3.7.2 | Civil Works | 3.7.2 Earthworks | Cl 7, 30 | Earthworks |  |  | C02 |  |  |  |  | Compaction tests | Tests passed
A2.06.03 | Bulk Earthworks - Fill | 3 | DIRECT COSTS | CIVIL | SOW 3.7.2 | Civil Works | 3.7.2 Earthworks | Cl 7, 30 | Earthworks |  |  | C02 |  |  |  |  | Compaction tests | Tests passed
A2.06.04 | Subgrade Preparation | 3 | DIRECT COSTS | CIVIL | SOW 3.7.3 | Civil Works | 3.7.3 Subgrade | Cl 7, 30 | Subgrade |  |  | C02, C03 |  |  |  |  | Level survey | Levels achieved
A2.06.05 | Stormwater Drainage | 3 | DIRECT COSTS | CIVIL | SOW 3.7.4 | Civil Works | 3.7.4 Drainage | Cl 7, 30 | Drainage |  |  | C03, C04 |  |  | H1000, H1001 |  | CCTV inspection | Drainage tested
A2.06.06 | Building Pad Formation | 3 | DIRECT COSTS | CIVIL | SOW 3.7.5 | Civil Works | 3.7.5 Building Pad | Cl 7, 30 | Building Pad |  | S2.01 | C02, C03 |  |  |  |  | Survey confirm | Levels achieved
A2.06.07 | External Pavements | 3 | DIRECT COSTS | CIVIL | SOW 3.7.6 | Civil Works | 3.7.6 Pavements | Cl 7, 30 | Pavements |  |  | C03, C04 |  |  |  |  | Slump/strength tests | Concrete tested
A2.06.08 | Vehicle Parking Areas | 3 | DIRECT COSTS | CIVIL | SOW 3.7.7 | Civil Works | 3.7.7 Car Park | Cl 7, 30 | Parking |  |  | C101-C104 |  |  |  |  | Line marking | Parking complete
A2.06.09 | Pathways & Walkways | 3 | DIRECT COSTS | CIVIL | SOW 3.7.8 | Civil Works | 3.7.8 Paths | Cl 7, 30 | Paths | A-500002 |  | C06 |  |  |  | L1.01-L1.04 | Levels survey | DDA compliant
A2.06.10 | Erosion & Sediment Control | 3 | DIRECT COSTS | CIVIL | SOW 3.7.9 | Civil Works | 3.7.9 ESC | Cl 7, 12.3 | ESC |  |  | C05, C104 |  |  |  |  | ESC maintained | No incidents
A2.06.11 | External Fencing | 3 | DIRECT COSTS | CIVIL | SOW 3.7.10 | Civil Works | 3.7.10 Fencing | Cl 7 | Fencing | [7 empty] | Fencing complete | Secure perimeter
A2.07 | BUILDING STRUCTURE & ENVELOPE | 2 | DIRECT COSTS | STRUCTURE | SOW 3.8 | Structure & Envelope | Building Structure | Cl 7, 30 | Structure | A-200 to A-400 | S1.01-S9.02 | [5 empty] | Structure Complete | Inspections passed
A2.07.01 | Foundation Works | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.1 | Structure | 3.8.1 Foundations | Cl 7, 30 | Foundations |  | S2.01, S2.02 | C02, C03 |  |  |  |  | Concrete tests | Strength achieved
A2.07.02 | Concrete Slabs | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.2 | Structure | 3.8.2 Slabs | Cl 7, 30 | Slabs |  | S2.01, S2.02, S7.01 | [5 empty] | Concrete tests | Strength achieved
A2.07.03 | Steel Structure - Primary | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.3 | Structure | 3.8.3 Steel Frame | Cl 7, 30 | Steel | A-300001-003 | S3.01-S3.03, S4.01-S4.02 | [5 empty] | Bolt tension tests | Connections verified
A2.07.04 | Steel Structure - Secondary | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.3 | Structure | 3.8.3 Steel Frame | Cl 7, 30 | Steel | A-300001-003 | S5.01-S5.02 | [5 empty] | Weld inspections | Welds approved
A2.07.05 | Floor Framing | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.4 | Structure | 3.8.4 Floor Framing | Cl 7, 30 | Framing |  | S3.01-S3.03 | [5 empty] | Level survey | Levels achieved
A2.07.06 | Roof Framing | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.5 | Structure | 3.8.5 Roof Framing | Cl 7, 30 | Roofing | A-200002-003 | S4.01-S4.02, S6.01-S6.03 | [5 empty] | Framing complete | Alignment verified
A2.07.07 | Roof Sheeting & Flashings | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.6 | Structure | 3.8.6 Roofing | Cl 7, 30 | Roofing | A-200002 | S4.01-S4.02 | [5 empty] | Water test | No leaks | Colorbond
A2.07.08 | External Cladding | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.7 | Structure | 3.8.7 Cladding | Cl 7, 30 | Cladding | A-400001-004, A-760001 | [6 empty] | Cladding complete | Alignment verified | AM-1 series
A2.07.09 | External Glazing & Windows | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.8 | Structure | 3.8.8 Glazing | Cl 7, 30 | Glazing | A-400001-004, A-410001-011 | [6 empty] | Glazing complete | Water test passed | WEF-21, WEF-22
A2.07.10 | External Doors | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.9 | Structure | 3.8.9 External Doors | Cl 7, 30 | Doors | A-730001 | [6 empty] | Doors installed | Operation verified
A2.07.11 | Gutters & Downpipes | 3 | DIRECT COSTS | STRUCTURE | SOW 3.8.10 | Structure | 3.8.10 Rainwater | Cl 7, 30 | Rainwater | A-200002 |  |  |  |  | H1001 |  | Flow test | No leaks
A2.08 | ARCHITECTURAL FIT-OUT (INTERNAL WORKS) | 2 | DIRECT COSTS | FIT-OUT | SOW 3.9 | Internal Fit-Out | Architectural Finishes | Cl 7, 30 | Fit-Out | A-210 to A-780 | [6 empty] | Fit-Out Complete | Inspections passed
A2.08.01 | Internal Walls & Partitions | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.1 | Internal Fit-Out | 3.9.1 Partitions | Cl 7, 30 | Partitions | A-220001-002, A-710010 | [6 empty] | Walls complete | Acoustic test passed | WIP-1, WIP-2
A2.08.02 | Internal Glazed Partitions | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.2 | Internal Fit-Out | 3.9.2 Glazed Partitions | Cl 7, 30 | Glazing | A-720011 | [6 empty] | Glazing complete | Installed & sealed | WIG-1
A2.08.03 | Ceiling Systems | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.3 | Internal Fit-Out | 3.9.3 Ceilings | Cl 7, 30 | Ceilings | A-210001-002, A-720012 | [6 empty] | Ceilings complete | Level verified
A2.08.04 | Ceiling Battens | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.3 | Internal Fit-Out | 3.9.3 Battens | Cl 7, 30 | Battens | A-210002, A-730002 | [6 empty] | Battens complete | Alignment verified
A2.08.05 | Floor Finishes - Tiles | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.4 | Internal Fit-Out | 3.9.4 Tiling | Cl 7, 30 | Flooring | A-230001 | [6 empty] | Tiling complete | No defects | FL-22
A2.08.06 | Floor Finishes - Carpet/Vinyl | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.4 | Internal Fit-Out | 3.9.4 Flooring | Cl 7, 30 | Flooring | A-230001 | [6 empty] | Flooring complete | No defects | FL-21
A2.08.07 | Internal Doors | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.5 | Internal Fit-Out | 3.9.5 Doors | Cl 7, 30 | Doors | A-730001 | [6 empty] | Doors installed | Operation verified | SC-1, TV-1
A2.08.08 | Acoustic Doors | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.5 | Internal Fit-Out | 3.9.5 Acoustic Doors | Cl 7, 30 | Doors | A-730001 | [6 empty] | Doors installed | Acoustic test passed | AL-Slide-1
A2.08.09 | Painting & Coatings | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.6 | Internal Fit-Out | 3.9.6 Painting | Cl 7, 30 | Painting | A-600001-017 | [6 empty] | Painting complete | DFT verified
A2.08.10 | Wall Linings & Finishes | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.7 | Internal Fit-Out | 3.9.7 Wall Finishes | Cl 7, 30 | Linings | A-600001-017 | [6 empty] | Linings complete | No defects
A2.08.11 | Wet Area Linings | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.8 | Internal Fit-Out | 3.9.8 Wet Areas | Cl 7, 30 | Wet Areas | A-620001-004 | [6 empty] | Waterproofing test | No leaks | MLAM-1 to MLAM-5
A2.08.12 | Joinery - Kitchen | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Kitchen Joinery | Cl 7, 30 | Joinery | A-600002, A-780001-005 | [6 empty] | Joinery installed | Services connected | JO-BW-1, JO-BW-2
A2.08.13 | Joinery - Boardroom | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Boardroom Joinery | Cl 7, 30 | Joinery | A-600004, A-780006 | [6 empty] | Joinery installed | Services connected | JO-BW-3
A2.08.14 | Joinery - Health Room | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Health Joinery | Cl 7, 30 | Joinery | A-600005, A-780006 | [6 empty] | Joinery installed | Services connected | JO-BW-4
A2.08.15 | Joinery - Training Kitchen | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Training Joinery | Cl 7, 30 | Joinery | A-600003, A-780007 | [6 empty] | Joinery installed | Services connected | JO-BW-5
A2.08.16 | Joinery - First Aid | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 First Aid Joinery | Cl 7, 30 | Joinery | A-600009, A-780007 | [6 empty] | Joinery installed | Services connected | JO-BW-6
A2.08.17 | Joinery - BBQ Area | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 BBQ Joinery | Cl 7, 30 | Joinery | A-600001, A-780008 | [6 empty] | Joinery installed | Services connected | JO-BW-7
A2.08.18 | Joinery - Amenities | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Amenities Joinery | Cl 7, 30 | Joinery | A-620003-004, A-780009 | [6 empty] | Joinery installed | Services connected | JO-BW-8, JO-BW-9
A2.08.19 | Joinery - Servery Units | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Servery Joinery | Cl 7, 30 | Joinery | A-600001, A-780010 | [6 empty] | Joinery installed | Services connected | JO-SE-1, JO-SE-2
A2.08.20 | Joinery - Display Boards | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.9 | Internal Fit-Out | 3.9.9 Display Boards | Cl 7, 30 | Joinery | A-780002-003 | [6 empty] | Boards installed | AV connected | JO-BD-1 to JO-BD-5
A2.08.21 | Lockers | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.10 | Internal Fit-Out | 3.9.10 Lockers | Cl 7, 30 | Lockers | A-600002, A-780011 | [6 empty] | Lockers installed | Smart system tested | JO-LKR-1 (60 lockers)
A2.08.22 | Signage | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.11 | Internal Fit-Out | 3.9.11 Signage | Cl 7, 30 | Signage | A-770001 | [6 empty] | Signage installed | Compliant
A2.08.23 | Stairs & Handrails | 3 | DIRECT COSTS | FIT-OUT | SOW 3.9.12 | Internal Fit-Out | 3.9.12 Stairs | Cl 7, 30 | Stairs | A-500001 | [6 empty] | Stairs complete | DDA compliant | TGSI included
A2.09 | MECHANICAL SERVICES | 2 | DIRECT COSTS | MECHANICAL | SOW 3.10 | Mechanical Services | HVAC & Ventilation | Cl 7, 30 | Mechanical | A-200003 |  |  | M0000-M2000 |  |  |  | Mechanical Complete | Commissioning passed
A2.09.01 | HVAC Equipment Supply | 3 | DIRECT COSTS | MECHANICAL | SOW 3.10.1 | Mechanical Services | 3.10.1 Equipment Supply | Cl 7 | Equipment |  |  |  | M0001 |  |  |  | Equipment delivered | Factory test certs | AC units, CU units
A2.09.02 | Ductwork Installation | 3 | DIRECT COSTS | MECHANICAL | SOW 3.10.2 | Mechanical Services | 3.10.2 Ductwork | Cl 7, 30 | Ductwork |  |  |  | M1000, M1010, M2000 |  |  |  | Ductwork complete | Leakage test passed
A2.09.03 | Grilles & Diffusers | 3 | DIRECT COSTS | MECHANICAL | SOW 3.10.3 | Mechanical Services | 3.10.3 Air Terminals | Cl 7, 30 | Terminals |  |  |  | M0001, M1000 |  |  |  | Terminals installed | Airflow balanced | S1, R1, E1, E2
A2.09.04 | Refrigerant Pipework | 3 | DIRECT COSTS | MECHANICAL | SOW 3.10.4 | Mechanical Services | 3.10.4 Refrigerant | Cl 7, 30 | Refrigerant |  |  |  | M1000, M2000 |  |  |  | Pipework complete | Pressure test passed
A2.09.05 | Exhaust Ventilation | 3 | DIRECT COSTS | MECHANICAL | SOW 3.10.5 | Mechanical Services | 3.10.5 Exhaust | Cl 7, 30 | Exhaust |  |  |  | M1000 |  |  |  | Exhaust installed | Airflow verified | KEH-1, EF-1
A2.09.06 | Controls & BMS Integration | 3 | DIRECT COSTS | MECHANICAL | SOW 3.10.6 | Mechanical Services | 3.10.6 Controls | Cl 7, 30 | Controls |  |  |  | M0001 | E2000 |  |  | BMS commissioned | Integration verified
A2.10 | ELECTRICAL SERVICES | 2 | DIRECT COSTS | ELECTRICAL | SOW 3.11 | Electrical Services | Electrical Installation | Cl 7, 30 | Electrical |  |  |  |  | E0000-E8002 |  |  | Electrical Complete | Testing passed
A2.10.01 | Main Switchboard (MSB) | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.1 | Electrical Services | 3.11.1 MSB | Cl 7, 30 | Switchboard |  |  |  |  | E8000 |  |  | MSB energised | Testing complete
A2.10.02 | Distribution Boards | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.2 | Electrical Services | 3.11.2 DBs | Cl 7, 30 | Distribution |  |  |  |  | E8000, E8001 |  |  | DBs energised | Testing complete
A2.10.03 | Cable Reticulation | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.3 | Electrical Services | 3.11.3 Cabling | Cl 7, 30 | Cabling |  |  |  |  | E0001, E0002 |  |  | Cabling complete | IR testing passed
A2.10.04 | Lighting Installation | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.4 | Electrical Services | 3.11.4 Lighting | Cl 7, 30 | Lighting |  |  |  |  | E1000, E0002 |  |  | Lighting installed | Lux levels achieved
A2.10.05 | Power Outlets (GPOs) | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.5 | Electrical Services | 3.11.5 Power | Cl 7, 30 | Power |  |  |  |  | E2000 |  |  | GPOs installed | Testing complete
A2.10.06 | Data & Communications | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.6 | Electrical Services | 3.11.6 Data | Cl 7, 30 | Comms |  |  |  |  | E2000, E2001 |  |  | Data installed | Testing complete
A2.10.07 | Security & Access Control | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.7 | Electrical Services | 3.11.7 Security | Cl 7, 30 | Security |  |  |  |  | E2000 |  |  | Security installed | Testing complete | Turnstile
A2.10.08 | Emergency Lighting | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.8 | Electrical Services | 3.11.8 Emergency | Cl 7, 30 | Emergency |  |  |  |  | E1000 |  |  | Emergency installed | Testing complete
A2.10.09 | External Lighting | 3 | DIRECT COSTS | ELECTRICAL | SOW 3.11.9 | Electrical Services | 3.11.9 External | Cl 7, 30 | External |  |  |  |  | E0010, E1000 |  | L1.01-L1.06 | Lighting installed | Lux levels achieved
A2.11 | HYDRAULIC SERVICES | 2 | DIRECT COSTS | HYDRAULIC | SOW 3.12 | Hydraulic Services | Water & Sanitary | Cl 7, 30 | Hydraulic | [5 empty] | H0000-H9000 |  | Hydraulic Complete | Testing passed
A2.11.01 | Water Supply & Reticulation | 3 | DIRECT COSTS | HYDRAULIC | SOW 3.12.1 | Hydraulic Services | 3.12.1 Water Supply | Cl 7, 30 | Water | [5 empty] | H0010, H2000 |  | Water connected | Pressure test passed
A2.11.02 | Hot Water Systems | 3 | DIRECT COSTS | HYDRAULIC | SOW 3.12.2 | Hydraulic Services | 3.12.2 Hot Water | Cl 7, 30 | Hot Water | [5 empty] | H0003, H6001 |  | HWU installed | Temperature verified | Stiebel Eltron
A2.11.03 | Sanitary Drainage | 3 | DIRECT COSTS | HYDRAULIC | SOW 3.12.3 | Hydraulic Services | 3.12.3 Drainage | Cl 7, 30 | Drainage | [5 empty] | H1000, H6000 |  | Drainage complete | Air test passed
A2.11.04 | Fixtures & Fittings | 3 | DIRECT COSTS | HYDRAULIC | SOW 3.12.4 | Hydraulic Services | 3.12.4 Fixtures | Cl 7, 30 | Fixtures | A-620001-004 |  |  |  |  | H0003, H6001 |  | Fixtures installed | Operation verified | WC, Basins, Showers
A2.11.05 | Roof Drainage | 3 | DIRECT COSTS | HYDRAULIC | SOW 3.12.5 | Hydraulic Services | 3.12.5 Roof Drainage | Cl 7, 30 | Roof | [5 empty] | H1001 |  | Drainage complete | Flow test passed
A2.12 | FIRE SERVICES | 2 | DIRECT COSTS | FIRE | SOW 3.13 | Fire Services | Fire Protection | Cl 7, 30 | Fire |  |  |  |  | E1000 | H2000, H4000 |  | Fire Complete | QFES certified
A2.12.01 | Fire Detection & Alarm | 3 | DIRECT COSTS | FIRE | SOW 3.13.1 | Fire Services | 3.13.1 Detection | Cl 7, 30 | Detection |  |  |  |  | E1000 |  |  | Detection installed | Testing complete
A2.12.02 | Fire Suppression (Sprinklers) | 3 | DIRECT COSTS | FIRE | SOW 3.13.2 | Fire Services | 3.13.2 Sprinklers | Cl 7, 30 | Sprinklers | [5 empty] | H4000 |  | Sprinklers installed | Flow test passed
A2.12.03 | Fire Hydrants & Hose Reels | 3 | DIRECT COSTS | FIRE | SOW 3.13.3 | Fire Services | 3.13.3 Hydrants | Cl 7, 30 | Hydrants | [5 empty] | H2000, H4000 |  | Hydrants installed | Flow test passed
A2.12.04 | Fire Extinguishers | 3 | DIRECT COSTS | FIRE | SOW 3.13.4 | Fire Services | 3.13.4 Extinguishers | Cl 7, 30 | Extinguishers | [7 empty] | Extinguishers installed | Locations verified
A2.12.05 | Emergency Egress | 3 | DIRECT COSTS | FIRE | SOW 3.13.5 | Fire Services | 3.13.5 Egress | Cl 7, 30 | Egress | A-070001 |  |  |  | E1000 |  |  | Egress compliant | QFES approved | Exit signs, paths
A2.13 | TESTING, COMMISSIONING & HANDOVER | 2 | DIRECT COSTS | T&C | SOW 11.0 | Testing & Commissioning | T&C Requirements | Cl 30, 42 | T&C | [7 empty] | T&C Complete | All systems verified
A2.13.01 | Pre-Commissioning Checks | 3 | DIRECT COSTS | T&C | SOW 11.1 | Testing & Commissioning | 11.1 Pre-Comm | Cl 30 | Pre-Comm |  |  |  | M-All | E-All | H-All |  | Checklists complete | All systems ready
A2.13.02 | Mechanical Commissioning | 3 | DIRECT COSTS | T&C | SOW 11.2 | Testing & Commissioning | 11.2 Mech Comm | Cl 30 | Mech T&C |  |  |  | M0000-M2000 |  |  |  | Mech commissioned | Reports accepted
A2.13.03 | Electrical Testing | 3 | DIRECT COSTS | T&C | SOW 11.3 | Testing & Commissioning | 11.3 Elec Test | Cl 30 | Elec T&C |  |  |  |  | E0000-E8002 |  |  | Elec tested | Certs issued
A2.13.04 | Fire Systems Commissioning | 3 | DIRECT COSTS | T&C | SOW 11.4 | Testing & Commissioning | 11.4 Fire Comm | Cl 30 | Fire T&C |  |  |  |  | E1000 | H2000, H4000 |  | Fire commissioned | QFES approved
A2.13.05 | Hydraulic Testing | 3 | DIRECT COSTS | T&C | SOW 11.5 | Testing & Commissioning | 11.5 Hyd Test | Cl 30 | Hyd T&C | [5 empty] | H0000-H9000 |  | Hyd tested | Reports accepted
A2.13.06 | BMS Commissioning | 3 | DIRECT COSTS | T&C | SOW 11.6 | Testing & Commissioning | 11.6 BMS Comm | Cl 30 | BMS T&C |  |  |  | M0001 | E2000 |  |  | BMS commissioned | Integration verified
A2.13.07 | Integrated Systems Testing | 3 | DIRECT COSTS | T&C | SOW 11.7 | Testing & Commissioning | 11.7 Integration | Cl 30 | Integration |  |  |  | M-All | E-All | H-All |  | Systems integrated | Full testing passed
A2.13.08 | As-Built Documentation | 3 | DIRECT COSTS | T&C | SOW 11.8 | Testing & Commissioning | 11.8 As-Builts | Cl 8, 42 | Documentation | A-All | S-All | C-All | M-All | E-All | H-All | L-All | As-builts complete | Documents accepted
A2.13.09 | O&M Manuals | 3 | DIRECT COSTS | T&C | SOW 11.9 | Testing & Commissioning | 11.9 O&M | Cl 42 | Documentation |  |  |  | M-All | E-All | H-All |  | O&M complete | Manuals accepted
A2.13.10 | Training Delivery | 3 | DIRECT COSTS | T&C | SOW 11.10 | Testing & Commissioning | 11.10 Training | Cl 42 | Training |  |  |  | M-All | E-All | H-All |  | Training delivered | Sign-off received
A2.14 | LANDSCAPING | 2 | DIRECT COSTS | LANDSCAPE | SOW 3.14 | Landscaping | Landscape Works | Cl 7, 30 | Landscape | [6 empty] | L0.00-L4.02 | Landscape Complete | Establishment period
A2.14.01 | Planting - Trees | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.1 | Landscaping | 3.14.1 Trees | Cl 7, 30 | Planting | [6 empty] | L0.01, L2.01-L2.05 | Trees planted | Establishment verified | 51 trees total
A2.14.02 | Planting - Shrubs & Ground Cover | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.2 | Landscaping | 3.14.2 Planting | Cl 7, 30 | Planting | [6 empty] | L0.01, L2.01-L2.05 | Planting complete | Establishment verified | 12,000+ plants
A2.14.03 | Turf | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.3 | Landscaping | 3.14.3 Turf | Cl 7, 30 | Turf | [6 empty] | L0.02, L2.01-L2.04 | Turf installed | Establishment verified | Wintergreen Couch
A2.14.04 | Irrigation System | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.4 | Landscaping | 3.14.4 Irrigation | Cl 7, 30 | Irrigation | [5 empty] | H0010 | L0.02 | Irrigation installed | System tested
A2.14.05 | Landscape Furniture | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.5 | Landscaping | 3.14.5 Furniture | Cl 7, 30 | Furniture | [6 empty] | L0.02-L0.03 | Furniture installed | Fixed in place | S1, S2 seats
A2.14.06 | Water Features | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.6 | Landscaping | 3.14.6 Water Features | Cl 7, 30 | Water Feature | [6 empty] | L0.02-L0.03 | Features complete | Pumps operational | POND A, POND B
A2.14.07 | Artworks | 3 | DIRECT COSTS | LANDSCAPE | SOW 3.14.7 | Landscaping | 3.14.7 Artworks | Cl 7, 30 | Artworks | [6 empty] | L0.02 | Artworks installed | Fixed in place | ART1 Jet Burners, ART2
A2.15 | DEMOBILISATION & CLOSE-OUT | 2 | DIRECT COSTS | DEMOB | SOW 12.0 | Demobilisation | Close-Out Activities | Cl 42 | Demobilisation | [7 empty] | Demob Complete | Site handed back
A2.15.01 | Site Demobilisation | 3 | DIRECT COSTS | DEMOB | SOW 12.1 | Demobilisation | 12.1 Demob | Cl 42 | Demob | [7 empty] | Site cleared | Facilities removed
A2.15.02 | Make Good & Reinstatement | 3 | DIRECT COSTS | DEMOB | SOW 12.2 | Demobilisation | 12.2 Make Good | Cl 42 | Reinstatement | [7 empty] | Areas reinstated | Condition verified
A2.15.03 | Final Cleaning | 3 | DIRECT COSTS | DEMOB | SOW 12.3 | Demobilisation | 12.3 Cleaning | Cl 42 | Cleaning | [7 empty] | Building cleaned | Ready for occupation
A2.15.04 | Defects Liability Support | 3 | DIRECT COSTS | DEMOB | SOW 12.4 | Demobilisation | 12.4 DLP | Cl 35, 35A | Defects | [7 empty] | DLP support | Defects rectified | 12 month DLP
PS | PROVISIONAL SUM ITEMS | 1 | Section B - Provisional Sum
PS1.01 | ROCK EXCAVATION | 2 | PROVISIONAL SUM | ROCK | SOW 3.7.1 | Civil Works | Rock if encountered | Cl 26, 27, 36 | Latent Conditions |  | S2.01 | C02-C04 |  |  |  |  | Rock assessment | Geotechnical report | If encountered
PS1.01.01 | Rock Identification & Classification | 3 | PROVISIONAL SUM | ROCK | SOW 3.7.1 | Civil Works | Rock classification | Cl 26, 27 | Latent Conditions |  |  | C02 |  |  |  |  | Geotech assessment | Report accepted
PS1.01.02 | Rock Breaking | 3 | PROVISIONAL SUM | ROCK | SOW 3.7.1 | Civil Works | Rock breaking | Cl 36 | Variations |  |  | C02, C04 |  |  |  |  | m³ broken | Measured in place
PS1.01.03 | Rock Removal & Disposal | 3 | PROVISIONAL SUM | ROCK | SOW 3.7.1 | Civil Works | Rock disposal | Cl 36 | Variations |  |  | C02 |  |  |  |  | m³ removed | Disposal dockets
PS1.01.04 | Backfill to Rock Excavation | 3 | PROVISIONAL SUM | ROCK | SOW 3.7.1 | Civil Works | Backfill | Cl 36 | Variations |  |  | C02 |  |  |  |  | m³ backfilled | Compaction tests
PS1.02 | CONTAMINATED MATERIAL | 2 | PROVISIONAL SUM | CONTAMINATION | SOW 3.6, 9.3 | Demolition / HSE | Contamination if encountered | Cl 12.3, 26, 27 | Latent Conditions |  |  | C02, C04, C05 |  |  |  |  | Contamination assessment | Validation report | If encountered
PS1.02.01 | Contamination Assessment & Testing | 3 | PROVISIONAL SUM | CONTAMINATION | SOW 3.6, 9.3 | HSE | Contamination testing | Cl 26, 27 | Latent Conditions | [7 empty] | Assessment report | Report accepted
PS1.02.02 | Contaminated Soil Excavation | 3 | PROVISIONAL SUM | CONTAMINATION | SOW 3.6 | Demolition | Soil excavation | Cl 36 | Variations |  |  | C02 |  |  |  |  | m³ excavated | Measured in place
PS1.02.03 | Contaminated Material Transport | 3 | PROVISIONAL SUM | CONTAMINATION | SOW 3.6 | Demolition | Transport & disposal | Cl 36 | Variations | [7 empty] | m³ disposed | Waste certificates
PS1.02.04 | Validation Testing | 3 | PROVISIONAL SUM | CONTAMINATION | SOW 9.3 | HSE | Validation testing | Cl 26, 27 | Latent Conditions | [7 empty] | Validation report | Report accepted
PS1.02.05 | Clean Fill Replacement | 3 | PROVISIONAL SUM | CONTAMINATION | SOW 3.7 | Civil Works | Fill replacement | Cl 36 | Variations |  |  | C02 |  |  |  |  | m³ replaced | Compaction tests
PS1.03 | LATENT CONDITIONS | 2 | PROVISIONAL SUM | LATENT | SOW 3.0 | General | Unforeseen conditions | Cl 26, 27 | Latent Conditions | [7 empty] | Condition report | Principal direction
PS1.03.01 | Latent Condition Investigation | 3 | PROVISIONAL SUM | LATENT | SOW 3.0 | General | Investigation | Cl 26, 27 | Latent Conditions | [7 empty] | Investigation report | Report accepted | Daywork V1/V2
PS1.03.02 | Design Response | 3 | PROVISIONAL SUM | LATENT | SOW 5.0 | Design | Design changes | Cl 26, 27, 36 | Variations | [7 empty] | Revised design | Design approved
PS1.03.03 | Remedial Works - Labour | 3 | PROVISIONAL SUM | LATENT | SOW 3.0 | General | Remedial labour | Cl 36, 38 | Variations | [7 empty] | Timesheets | Approved daywork | V1 rates
PS1.03.04 | Remedial Works - Plant | 3 | PROVISIONAL SUM | LATENT | SOW 3.0 | General | Remedial plant | Cl 36, 38 | Variations | [7 empty] | Plant dockets | Approved daywork | V2 rates
PS1.03.05 | Remedial Works - Materials | 3 | PROVISIONAL SUM | LATENT | SOW 3.0 | General | Remedial materials | Cl 36, 38 | Variations | [7 empty] | Invoices | Cost + margin
PS1.04 | PRINCIPAL-DIRECTED VARIATIONS | 2 | PROVISIONAL SUM | VARIATIONS | SOW 3.0 | General | Principal directed changes | Cl 36, 38, 41 | Variations | [7 empty] | Variation instruction | VR approved
PS1.04.01 | Scope Additions - Labour | 3 | PROVISIONAL SUM | VARIATIONS | SOW 3.0 | General | Additional labour | Cl 36, 38 | Variations | [7 empty] | Timesheets | Approved daywork | V1 rates
PS1.04.02 | Scope Additions - Plant | 3 | PROVISIONAL SUM | VARIATIONS | SOW 3.0 | General | Additional plant | Cl 36, 38 | Variations | [7 empty] | Plant dockets | Approved daywork | V2 rates
PS1.04.03 | Scope Additions - Materials | 3 | PROVISIONAL SUM | VARIATIONS | SOW 3.0 | General | Additional materials | Cl 36, 38 | Variations | [7 empty] | Invoices | Cost + margin
PS1.04.04 | Scope Additions - Subcontractors | 3 | PROVISIONAL SUM | VARIATIONS | SOW 3.0 | General | Additional subcontract | Cl 5, 36 | Variations | [7 empty] | Subcontract invoices | Cost + margin
PS1.04.05 | Design Changes | 3 | PROVISIONAL SUM | VARIATIONS | SOW 5.0 | Design | Design variations | Cl 7A, 36 | Variations | [7 empty] | Revised drawings | Design approved
PS1.04.06 | Acceleration Measures | 3 | PROVISIONAL SUM | VARIATIONS | SOW 3.0 | General | Acceleration | Cl 36, 41 | Variations | [7 empty] | Acceleration plan | Plan approved | If directed
PS1.05 | AV SYSTEMS INSTALLATION | 2 | PROVISIONAL SUM | AV | SOW 3.11 | Electrical Services | AV by others | Cl 5, 7 | Subcontracting | A-600001-017 |  |  |  | E1000, E2000 |  |  | AV coordination | AV operational | By others
PS1.05.01 | AV Contractor Coordination | 3 | PROVISIONAL SUM | AV | SOW 3.11 | Electrical Services | AV coordination | Cl 5, 7 | Coordination | A-600001-017 |  |  |  | E2000 |  |  | Coordination plan | Interfaces defined
PS1.05.02 | AV Conduit & Cabling Provisions | 3 | PROVISIONAL SUM | AV | SOW 3.11 | Electrical Services | AV infrastructure | Cl 7 | Infrastructure |  |  |  |  | E0002, E2000 |  |  | Conduit installed | Pathways verified
PS1.05.03 | AV Power Supply Provisions | 3 | PROVISIONAL SUM | AV | SOW 3.11 | Electrical Services | AV power | Cl 7 | Power |  |  |  |  | E2000 |  |  | Power points | Circuits verified
PS1.05.04 | AV Equipment Supports | 3 | PROVISIONAL SUM | AV | SOW 3.11 | Electrical Services | AV backings | Cl 7 | Structure | A-780002-003 | [6 empty] | Supports installed | Locations verified | TV mounts, boards
PS1.05.05 | AV Integration Support | 3 | PROVISIONAL SUM | AV | SOW 3.11 | Electrical Services | AV integration | Cl 7 | Integration |  |  |  |  | E2000 |  |  | Integration support | AV operational
REFERENCE KEYS
SOW SECTIONS |  |  |  |  | CONTRACT CLAUSES (AS4000-1997 AMENDED)
SOW 3.0 | Site Works & Construction |  |  |  | Cl 5 | Subcontracting
SOW 4.0 | Procurement |  |  |  | Cl 7 | Site Management
SOW 5.0 | Design Responsibility |  |  |  | Cl 7A | Design by Contractor
SOW 6.0 | Authority Approvals |  |  |  | Cl 8 | Documents
SOW 7.0 | Project Management |  |  |  | Cl 11 | Statutory Requirements
SOW 9.0 | Health Safety Environment |  |  |  | Cl 12 | Work Health & Safety
SOW 10.0 | Quality Management |  |  |  | Cl 21 | Authorities & Approvals
SOW 11.0 | Testing & Commissioning |  |  |  | Cl 22, 23 | Superintendence
SOW 12.0 | Demobilisation & Handover |  |  |  | Cl 26, 27 | Latent Conditions
[5 empty] | Cl 29 | Quality Assurance
[5 empty] | Cl 30 | Inspections & Testing
[5 empty] | Cl 32 | Programs
[5 empty] | Cl 35, 35A | Warranties & Defects
[5 empty] | Cl 36, 38 | Variations
[5 empty] | Cl 37 | Payments
[5 empty] | Cl 41 | Acceleration
[5 empty] | Cl 42 | Practical Completion
DRAWING REFERENCE KEYS
Discipline | Series | Consultant | Description
Architectural | A-000 to A-910 | M3 Architecture / BH Architect | Site plans, GA, finishes, facades, interiors, joinery, signage
Structural | S1.01 to S9.02 | Janes & Stewart Structures | Foundations, framing, roof, hat stand, generator area
Civil | C01 to C104 | Janes & Stewart Structures | Earthworks, drainage, parking, ESC plans
Mechanical | M0000 to M2000 | JHA Consulting Engineers | HVAC layouts, ductwork, sections, schedules
Electrical | E0000 to E8002 | JHA Consulting Engineers | Lighting, power, fire detection, schematics
Hydraulic | H0000 to H9000 | JHA Consulting Engineers | Drainage, water services, fire coverage, details
Landscape | L0.00 to L4.02 | Subtropic Design | Planting plans, materials, sections, details
SUMMARY STATISTICS
Total Pay Items: | 201
Level 1 Items: | 3
Level 2 Items: | 25
Level 3 Items: | 173
SUMMARY STATISTICS
Metric | Count |  | Drawing Coverage | Count
Total Pay Items: | 201 |  | Architectural Drawings: | 54
Level 1 Items (Sections): | 3 |  | Structural Drawings: | 19
Level 2 Items (Categories): | 25 |  | Civil Drawings: | 36
Level 3 Items (Line Items): | 173 |  | Mechanical Drawings: | 20
|  |  | Electrical Drawings: | 39
SOW Sections Referenced: | All (3.0-12.0) |  | Hydraulic Drawings: | 31
Contract Clauses Referenced: | 16 |  | Landscape Drawings: | 16