## Instructions
RFT #
SPS Annex Refurbishment Project
TENDERER INSTRUCTIONS
Pricing Table & Variation Table Completion Guide
1. INTRODUCTION
This document provides instructions for Tenderers on how to complete the Pay Table and Variation Table.
All pricing must be entered in Australian Dollars (AUD) exclusive of GST unless otherwise stated.
Do not modify the structure of the tables, column headings, or item numbers.
2. PAY TABLE - COLUMN DEFINITIONS
Column | Header | Description | Data Type | Tenderer Action | Validation | Notes
A-H | N1-N7 | Internal numbering hierarchy codes used for sorting and filtering | Text/Number | DO NOT MODIFY | System generated | Used for data management only
I | LEVEL | Hierarchy level indicator (1=Section, 2=Category, 3=Sub-category, 4=Line Item) | Number (1-4) | DO NOT MODIFY | 1, 2, 3, or 4 | Level 4 items require pricing
J | L1 | Level 1 Description - Major section heading (e.g., Section A - Lump Sum) | Text | DO NOT MODIFY | Pre-populated | Section identifier
K | L2 | Level 2 Description - Cost category (e.g., INDIRECT COSTS, SITE WIDE) | Text | DO NOT MODIFY | Pre-populated | Cost area classification
L | L3 | Level 3 Description - Sub-category (e.g., PROJECT MANAGEMENT, DEMOLITION) | Text | DO NOT MODIFY | Pre-populated | Work type classification
M | L4 | Level 4 Description - Activity/Commodity detail | Text | DO NOT MODIFY | Pre-populated | Specific work item
N | L5 | Level 5 Description - Additional detail level (if required) | Text | DO NOT MODIFY | Pre-populated | Extended detail
O | Item No. | Unique Pay Table item number (e.g., A1.01.01, A3.12.05) | Text | DO NOT MODIFY | Alphanumeric format | Reference for WBS linkage
P | SOW Ref# | Scope of Work reference clause(s) applicable to this item | Text | DO NOT MODIFY | Pre-populated | Links to SOW document
Q | Contract Ref# | Contract clause reference(s) applicable to this item | Text | DO NOT MODIFY | Pre-populated | Links to Contract conditions
R | Drawing Ref# | Drawing reference(s) applicable to this item | Text | DO NOT MODIFY | Pre-populated | Links to project drawings
S | WBS Ref# | Work Breakdown Structure reference code | Text | DO NOT MODIFY | Pre-populated | Links to WBS for scheduling
T | Description | Full description of the work item or deliverable | Text | DO NOT MODIFY | Pre-populated | Defines scope of item
U | UOM | Unit of Measure (e.g., Lot, m², m³, No., Days, Wk) | Text | DO NOT MODIFY | Standard units | Basis for quantity measurement
V | Pricing | Pricing type indicator (LS=Lump Sum, SOR=Schedule of Rates, PS=Provisional Sum) | Text | DO NOT MODIFY | LS, SOR, or PS | Determines pricing method
W | Qty | Quantity for the item - Principal estimated or Tenderer to confirm | Number | VERIFY/ENTER | Positive number | Check against drawings/specs
X | Rate | Tenderer's rate per unit of measure in AUD | Currency | ENTER RATE | Positive number | Must include all costs
Y | Amount (AUD) | Calculated amount = Qty × Rate | Currency (Formula) | AUTO-CALCULATED | N/A | Do not manually override
Z | a | Reserved column for internal use | N/A | DO NOT USE | N/A | System reserved
AA | Method of Measure | How the work will be measured for payment purposes | Text | DO NOT MODIFY | Pre-populated | Defines measurement basis
AB | Rule of Credit | Payment milestone rules and conditions for claiming | Text | DO NOT MODIFY | Pre-populated | Defines payment triggers
3. PAY TABLE - PRICING TYPES EXPLAINED
Pricing Type
Lump Sum | LS | Fixed price for complete delivery of the item regardless of actual quantities | Enter total fixed price in Rate column, Qty = 1 | Milestone-based per Rule of Credit
Schedule of Rates | SOR | Unit rate applied to measured quantities | Enter rate per UOM; final payment based on actual measured qty | Measured quantities × Rate
Provisional Sum | PS | Allowance for undefined scope - Principal directed expenditure only | Enter rate if applicable; PS amounts are Principal-controlled | Actual costs + margin as defined
4. METHOD OF MEASURE DEFINITIONS
Method | Description | Applies To | Documentation Required
Pro-rata monthly | Payment distributed evenly across contract period | Personnel, ongoing services | Monthly timesheets, attendance records
Pro-rata monthly over contract period | Same as above with specific contract duration reference | Management roles, site services | Monthly reports, site diaries
Milestone | Single payment upon achievement of defined milestone | Deliverables, approvals, certificates | Milestone evidence, sign-off
Milestone + Pro-rata | Partial milestone payment plus monthly pro-rata | Plans with ongoing compliance | Initial acceptance + monthly reports
Milestone by discipline | Separate milestones per discipline/trade | Multi-discipline design work | Per-discipline completion evidence
Per inspection | Payment per completed inspection event | QA inspections, hold points | Signed inspection records
Per ITP | Payment per completed Inspection Test Plan | Quality activities | Completed ITP documentation
Per utility
Measured in place | Payment based on installed/completed quantities | Construction items | Survey, measurement records
Lump sum complete | Single payment on completion of all works | Discrete packages | Completion certificate
5. RULE OF CREDIT DEFINITIONS
Rule | Description | Example | Claim Requirement
25% WHSMP accepted, 75% Monthly pro-rata | 25% payable on WHS Management Plan acceptance, remaining 75% paid monthly | HSE Management | WHSMP approval letter + monthly HSE reports
30% TMP accepted, 70% Monthly pro-rata | 30% payable on Traffic Management Plan acceptance, remaining 70% monthly | Traffic Management | TMP approval + monthly compliance records
30% Design kickoff, 40% IFC, 30% As-built | Design payments split across key milestones | Design Management | Design meeting minutes, IFC issue, As-built acceptance
40% IFC approved, 30% Form 15, 30% Form 12 | Design deliverable payments linked to certification | Contractor Design | IFC approval, Form 15 & 12 certificates
100% on completion
100% per milestone passed | Full item value on milestone achievement | Inspections, approvals | Passed inspection/approval evidence
Pro-rata monthly, records maintained | Monthly payment subject to record keeping compliance | Ongoing compliance activities | Up-to-date registers and records
6. VARIATION TABLE - COLUMN DEFINITIONS
Column | Header | Description | Data Type | Tenderer Action | Validation | Notes
A | Cost Type | Classification of cost (VARIATION) | Text | DO NOT MODIFY | Pre-populated | All items are variations
B | Category | Main category (e.g., PERSONNEL DAYWORK RATES, PLANT & EQUIPMENT) | Text | DO NOT MODIFY | Pre-populated | Groups similar items
C | Sub-Category | Sub-category detail (e.g., Management, Engineering, Trades) | Text | DO NOT MODIFY | Pre-populated | Further classification
D | Item No. | Unique Variation item number (e.g., V1.01.01, V2.03.05) | Text | DO NOT MODIFY | Alphanumeric format | Reference for variations
E
F | UOM | Unit of Measure (e.g., Day, Hr, Wk, m², m³, No.) | Text | DO NOT MODIFY | Standard units | Basis for rate application
G | Pricing Type | Rate type indicator (SOR=Schedule of Rates) | Text | DO NOT MODIFY | SOR | All variation items are SOR
H | Normal Rate | Standard hourly/daily rate for normal working hours | Currency | ENTER RATE | Positive number | Mon-Fri, standard hours
I | OT 1.5x | Overtime rate at 1.5 times normal rate | Currency | ENTER RATE | ≥1.5 × Normal Rate | First 2-3 hours OT
J | OT 2.0x | Overtime rate at 2.0 times normal rate | Currency | ENTER RATE | ≥2.0 × Normal Rate | After initial OT / Saturdays
K | OT 2.5x | Overtime rate at 2.5 times normal rate | Currency | ENTER RATE | ≥2.5 × Normal Rate | Sundays / Public Holidays
L | Allowances | Additional allowances applicable (travel, site, height, etc.) | Currency | ENTER IF APPLICABLE | Positive number or blank | Per applicable EBA/Award
M | Mob Rate | Mobilisation rate for equipment/plant | Currency | ENTER IF APPLICABLE | Positive number or blank | One-off mobilisation cost
N | Demob Rate | Demobilisation rate for equipment/plant | Currency | ENTER IF APPLICABLE | Positive number or blank | One-off demobilisation cost
O | Dry Hire | Equipment hire rate without operator | Currency | ENTER IF APPLICABLE | Positive number or blank | Equipment only
P | Wet Hire | Equipment hire rate including operator and fuel | Currency | ENTER IF APPLICABLE | Positive number or blank | Equipment + operator + fuel
Q | Supply Rate | Rate for supply of materials only | Currency | ENTER IF APPLICABLE | Positive number or blank | Materials ex-delivery
R | Install Rate | Rate for installation labour only | Currency | ENTER IF APPLICABLE | Positive number or blank | Labour to install
S | All-in Rate | Combined supply and install rate | Currency | ENTER IF APPLICABLE | Positive number or blank | Supply + Install combined
T | Method of Measure | How the variation work will be measured | Text | DO NOT MODIFY | Pre-populated | Measurement basis
U | Rule of Credit | Conditions for claiming variation payment | Text | DO NOT MODIFY | Pre-populated | Approval requirements
V | Min Charge | Minimum charge per call-out/engagement | Text/Number | ENTER IF APPLICABLE | e.g., 4 hrs | Minimum billing increment
W | Increment | Billing increment after minimum | Text/Number | ENTER IF APPLICABLE | e.g., 1 hr | Charging increment
X | Valid From | Rate validity start date | Date | ENTER DATE | DD-MMM-YY | Rate effective from
Y
Z | Notes | Additional notes or conditions | Text | ENTER IF REQUIRED | Free text | Clarifications, exclusions
7. GENERAL INSTRUCTIONS FOR TENDERERS
Ref | Instruction
7.1 | Complete ALL Level 4 items in the Pay Table with rates. Do not leave blank cells.
7.2 | Ensure all rates are inclusive of overheads, margins, insurances, and all costs to complete the work.
7.3 | Verify quantities against the drawings and specifications. Note any discrepancies in the Notes column.
7.4 | For Provisional Sum items, enter your proposed margin percentage in the Notes column.
7.5 | All rates in the Variation Table will be used for valuing variations and daywork during the contract.
7.7 | Plant & Equipment rates must distinguish between Dry Hire (equipment only) and Wet Hire (with operator).
7.8 | Material rates should be based on current supplier pricing and include delivery to site.
7.9 | All rates are to remain fixed for the duration of the contract unless rise and fall provisions apply.
7.1 | If adding Tenderer Identified Items, use the designated rows at the end of each section.

## Pay Table
[14 empty] | RFT # 1221995761 Annex Works | [13 empty] | Payment Claims
Contract Sum
Pricing Table Template
[14 empty] | Revision: | A
[14 empty] | ITEM |  |  |  |  | Reference | Quantity UOM | [7 empty] | Claimed to Date |  | Certified to Date |  | This Claim
N1 | N2 | N3 | N32 | N4 | N5 | N6 | N7 | LEVEL | L1 | L2 | L3 | L4 | L5 | Item No. | SOW Ref# | Contract Ref# | Drawing Ref# | WBS Ref# | Description | UOM | Pricing | Qty | Rate | Amount (AUD) | a | Method of Measure | Rule of Credit | Qty | Amount | Qty | Amount | Qty | Amount
CS | 0 | 0 | CS00 | 01 | 0 | 00 | 00 | 1 | Contract Sum |  |  |  |  | CS |  |  |  |  | Contract Sum |  |  |  |  | 0
A | 0 | 0 | A00 | 01 | 0 | 00 | 00 | 1 | Section A - Lump Sum |  |  |  |  | A |  |  |  |  | Section A - Lump Sum |  |  |  |  | 0
A | 1 | 0 | A10 | 01 | 0 | 00 | 00 | 2 | Section A - Lump Sum | INDIRECT COSTS |  |  |  | A1 |  |  |  |  | INDIRECT COSTS |  |  |  |  | 0
A | 1 | 01 | A101 | 00 | 0 | 00 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT |  |  | A1.01 |  |  |  |  | PROJECT MANAGEMENT |  |  |  |  | 0
A | 1 | 01 | A101 | 00 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Project Director |  | A1.01.00 | SOW 7.0, 7.1 | Cl 22, 23 |  | 1.01.01 | Project Director | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 01 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Project Manager |  | A1.01.01 | SOW 7.0, 7.1 | Cl 22, 23 |  | 1.01.02 | Project Manager | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 02 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Site Manager / Superintendent |  | A1.01.02 | SOW 7.0, 7.1 | Cl 22, 23 |  | 1.01.03 | Site Manager / Superintendent | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 03 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Construction Manager |  | A1.01.03 | SOW 7.0, 7.1 | Cl 22, 23 |  | 1.01.04 | Construction Manager | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 04 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Assistant Site Manager |  | A1.01.04 | SOW 7.0, 9.0 | Cl 12, 22, 23 |  | 1.01.05 | Assistant Site Manager | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 05 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Project Engineer |  | A1.01.05 | SOW 7.0, 10.0 | Cl 29, 22, 23 |  | 1.01.06 | Project Engineer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 06 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Senior Engineer |  | A1.01.06 | SOW 7.0, 7.4 | Cl 8, 22, 23 |  | 1.01.07 | Senior Engineer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 07 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Graduate Engineer |  | A1.01.07 | SOW 7.0 | Cl 22, 23, 37 |  | 1.01.08 | Graduate Engineer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 08 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Design Engineer |  | A1.01.08 | SOW 7.0 | Cl 37, 22, 23 |  | 1.01.09 | Design Engineer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 09 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Services Engineer (Mech/Elec/Hyd) |  | A1.01.09 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  | 1.01.10 | Services Engineer (Mech/Elec/Hyd) | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 10 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Site Foreman / Supervisor |  | A1.01.10 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Site Foreman / Supervisor | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 11 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Leading Hand |  | A1.01.11 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Leading Hand | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 12 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Works Coordinator |  | A1.01.12 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Works Coordinator | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 13 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Night Shift Supervisor |  | A1.01.13 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Night Shift Supervisor | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 14 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Subcontractor Coordinator |  | A1.01.14 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Subcontractor Coordinator | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 15 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | HSE Manager |  | A1.01.15 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | HSE Manager | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 16 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | WHS Advisor / Safety Officer |  | A1.01.16 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | WHS Advisor / Safety Officer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 17 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Environmental Officer |  | A1.01.17 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Environmental Officer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 18 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Traffic Controller |  | A1.01.18 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Traffic Controller | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 19 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | First Aid Officer |  | A1.01.19 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | First Aid Officer | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 20 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Quality Manager |  | A1.01.20 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Quality Manager | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 21 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Quality Coordinator |  | A1.01.21 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Quality Coordinator | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 22 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Quality Inspector |  | A1.01.22 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Quality Inspector | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 23 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Document Controller |  | A1.01.23 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Document Controller | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 24 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Contract Administrator |  | A1.01.24 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Contract Administrator | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 25 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Cost Controller / Estimator |  | A1.01.25 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Cost Controller / Estimator | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 26 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Scheduler / Planner |  | A1.01.26 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Scheduler / Planner | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 01 | A101 | 27 | 1 | 01 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | PROJECT MANAGEMENT | Project Administrator |  | A1.01.27 | SOW 7.0, 7.3 | Cl 32, 22, 23 |  |  | Project Administrator | Days | LS |  |  | 0 |  | Pro-rata monthly based on contract duration | Monthly payment subject to: (1) Personnel actively engaged on project, (2) Monthly progress report submitted, (3) All management plans current and accepted
A | 1 | 02 | A102 | 00 | 0 | 01 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | HSE |  |  | A1.02 |  |  |  |  | HSE |  |  |  |  | 0
A | 1 | 02 | A102 | 00 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | WHS Management System |  | A1.02.00 | SOW 9.1, 9.2 | Cl 12.3, 12.5 |  | 1.02.01 | WHS Management System | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata monthly | 25% upon Plan acceptance by Principal, 75% pro-rata monthly over construction period
A | 1 | 02 | A102 | 01 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | Permits and Controls |  | A1.02.01 | SOW 9.3 | Cl 12.4 |  | 1.02.02 | Permits and Controls | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Pro-rata monthly, all permits maintained current
A | 1 | 02 | A102 | 02 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | Environmental Management |  | A1.02.02 | SOW 9.4 | Cl 12.3 |  | 1.02.03 | Environmental Management | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata | 25% CEMP accepted, 75% Monthly pro-rata
A | 1 | 02 | A102 | 03 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | SWMS Development & Approvals |  | A1.02.03 | SOW 9.2 | Cl 12.3 |  | 1.02.04 | SWMS Development & Approvals | Lot | LS | 1 |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 1 | 02 | A102 | 04 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | Site Inductions & Competency Verification |  | A1.02.04 | SOW 9.2 | Cl 12.3, 12.4 |  | 1.02.05 | Site Inductions & Competency Verification | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Pro-rata monthly, records maintained
A | 1 | 02 | A102 | 05 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | Incident Management & Reporting |  | A1.02.05 | SOW 9.5 | Cl 12.9 |  | 1.02.06 | Incident Management & Reporting | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Pro-rata monthly, incident reports submitted within 24hrs
A | 1 | 02 | A102 | 06 | 1 | 02 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | HSE | Traffic Management Plan & Implementation |  | A1.02.06 | SOW 9.3, 3.4.5 | Cl 12.6 |  | 1.02.07 | Traffic Management Plan & Implementation | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata | 30% TMP accepted, 70% Monthly pro-rata
A | 1 | 03 | A103 | 00 | 0 | 02 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | QUALITY |  |  | A1.03 |  |  |  |  | QUALITY |  |  |  |  | 0
A | 1 | 03 | A103 | 00 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY | Quality Management Plan (QMP) |  | A1.03.00 | SOW 10.1 | Cl 29.2 |  | 1.03.01 | Quality Management Plan (QMP) | Lot | LS | 1 |  | 0 |  | Milestone | 100% QMP accepted prior to works commencing
A | 1 | 03 | A103 | 01 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY | Inspection & Test Plans (ITPs) |  | A1.03.01 | SOW 10.2 | Cl 29.2, 30 |  | 1.03.02 | Inspection & Test Plans (ITPs) | Lot | LS | 1 |  | 0 |  | Milestone + Per ITP | 30% ITPs approved, 70% Per ITP completed
A | 1 | 03 | A103 | 02 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY | Non-Conformance & Corrective Actions |  | A1.03.02 | SOW 10.3, 10.4 | Cl 29.3 |  | 1.03.03 | Non-Conformance & Corrective Actions | Lot | LS | 1 |  | 0 |  | Pro-rata monthly | Pro-rata monthly, NCR register maintained
A | 1 | 03 | A103 | 03 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY | Witness & Hold Point Inspections |  | A1.03.03 | SOW 10.5 | Cl 30 |  | 1.03.04 | Witness & Hold Point Inspections | Lot | LS | 1 |  | 0 |  | Per inspection | Per inspection completed and signed off
A | 1 | 03 | A103 | 04 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | QUALITY | Manufacturer's Data Records (MDR) |  | A1.03.04 | SOW 10.6, SDRL | Cl 30.6 |  | 1.03.05 | Manufacturer's Data Records (MDR) | Lot | LS | 1 |  | 0 |  | Milestone | 100% MDR submitted and accepted at PC
A | 1 | 04 | A104 | 00 | 0 | 03 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | DESIGN |  |  | A1.04 |  |  |  |  | DESIGN |  |  |  |  | 0
A | 1 | 04 | A104 | 00 | 1 | 04 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | DESIGN | Design Management and Coordination |  | A1.04.00 | SOW 5.0, 3.5 | Cl 7A |  | 1.04.01 | Design Management and Coordination | Lot | LS | 1 |  | 0 |  | Milestone | 30% Design kickoff, 40% IFC, 30% As-built accepted
A | 1 | 04 | A104 | 01 | 1 | 04 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | DESIGN | Contractor Design Deliverables |  | A1.04.01 | SOW 5.0, 3.5 | Cl 7A.2 |  | 1.04.02 | Contractor Design Deliverables | Lot | LS | 1 |  | 0 |  | Milestone | 40% IFC approved, 30% Form 15, 30% Form 12
A | 1 | 04 | A104 | 02 | 1 | 04 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | DESIGN | Shop Drawings - All Disciplines |  | A1.04.02 | SOW 3.5, 7.4 | Cl 7A.3, 8.3 |  | 1.04.03 | Shop Drawings - All Disciplines | Lot | LS | 1 |  | 0 |  | Milestone by discipline | 40% Model, 40% IFC accepted, 20% As-built
A | 1 | 05 | A105 | 00 | 0 | 04 | 00 | 3 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS |  |  | A1.05 |  |  |  |  | APPROVALS |  |  |  |  | 0
A | 1 | 05 | A105 | 00 | 1 | 05 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Building Approval Coordination |  | A1.05.00 | SOW 6.1 | Cl 11 |  | 1.05.01 | Building Approval Coordination | Lot | LS | 1 |  | 0 |  | Milestone | 100% Building approval obtained
A | 1 | 05 | A105 | 01 | 1 | 05 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Authority Inspections & Certifications |  | A1.05.01 | SOW 6.2 | Cl 11 |  | 1.05.02 | Authority Inspections & Certifications | Lot | LS | 1 |  | 0 |  | Per inspection | 100% per inspection passed
A | 1 | 05 | A105 | 02 | 1 | 05 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Council / Local Authority Coordination |  | A1.05.02 | SOW 6.3 | Cl 11 |  | 1.05.03 | Council / Local Authority Coordination | Lot | LS | 1 |  | 0 |  | Pro-rata | Pro-rata over approval period
A | 1 | 05 | A105 | 03 | 1 | 04 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Utility Authority Coordination (Power/Water/Comms) |  | A1.05.03 | SOW 6.4 | Cl 11 |  | 1.05.04 | Utility Authority Coordination (Power/Water/Comms) | Lot | LS | 1 |  | 0 |  | Per utility | 100% per utility connected
A | 1 | 05 | A105 | 04 | 1 | 04 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Fire Authority Approval (QFES) |  | A1.05.04 | SOW 6.5 | Cl 11 |  | 1.05.05 | Fire Authority Approval (QFES) | Lot | LS | 1 |  | 0 |  | Milestone | 100% QFES approval obtained
A | 1 | 05 | A105 | 05 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Occupancy Certificate / Final Inspection |  | A1.05.05 | SOW 6.6 | Cl 11, 34.6 |  | 1.05.06 | Occupancy Certificate / Final Inspection | Lot | LS | 1 |  | 0 |  | Milestone | 100% Occupancy certificate issued
A | 1 | 05 | A105 | 06 | 1 | 03 | 00 | 4 | Section A - Lump Sum | INDIRECT COSTS | APPROVALS | Form 21 / Final Certificate Coordination |  | A1.05.06 | SOW 6.7 | Cl 11 |  | 1.05.07 | Form 21 / Final Certificate Coordination | Lot | LS | 1 |  | 0 |  | Milestone | 100% Form 21 lodged
A | 2 | 0 | A20 | 03 | 0 | 00 | 00 | 2 | Section A - Lump Sum | SITE WIDE |  |  |  | A2 |  |  |  |  | SITE WIDE |  |  |  |  | 0
A | 2 | 01 | A201 | 29 | 0 | 00 | 00 | 3 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT |  |  | A2.01 |  |  |  |  | SITE ESTABLISHMENT |  |  |  |  | 0
A | 2 | 01 | A201 | 29 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT | Site Mobilisation |  | A2.01.29 | SOW 3.1, 3.2 | Cl 27, 32 | A0/01-03 | 2.01.01 | Site Mobilisation | Lot | LS | 1 |  | 0 |  | Milestone | 100% Site establishment complete
A | 2 | 01 | A201 | 30 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT | Site Offices & Amenities |  | A2.01.30 | SOW 3.1 | Cl 27.1 | A0/01-03 | 2.01.02 | Site Offices & Amenities | Lot | LS | 1 |  | 0 |  | Milestone | 100% Offices operational
A | 2 | 01 | A201 | 31 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT | Temporary Services (Power/Water) |  | A2.01.31 | SOW 3.1 | Cl 27 |  | 2.01.03 | Temporary Services (Power/Water) | Lot | LS | 1 |  | 0 |  | Milestone | 100% Services connected
A | 2 | 01 | A201 | 32 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT | Temporary Fencing & Hoarding |  | A2.01.32 | SOW 3.1 | Cl 27 | A0/01-03 | 2.01.04 | Temporary Fencing & Hoarding | Lot | LS |  |  | 0 |  | Per linear metre installed | Pro-rata per metre installed
A | 2 | 01 | A201 | 33 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT | Site Signage & Safety Barriers |  | A2.01.33 | SOW 3.1 | Cl 27 |  | 2.01.05 | Site Signage & Safety Barriers | Lot | LS | 1 |  | 0 |  | Milestone | 100% Signage installed
A | 2 | 01 | A201 | 34 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | SITE ESTABLISHMENT | Waste Management Setup |  | A2.01.34 | SOW 3.1, 9.4 | Cl 27 |  | 2.01.06 | Waste Management Setup | Lot | LS | 1 |  | 0 |  | Milestone + Pro-rata | 30% Setup, 70% Monthly pro-rata
A | 2 | 02 | A202 | 08 | 0 | 00 | 00 | 3 | Section A - Lump Sum | SITE WIDE | DEMOBILISATION |  |  | A2.02 |  |  |  |  | DEMOBILISATION |  |  |  |  | 0
A | 2 | 02 | A202 | 08 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | DEMOBILISATION | Demobilisation |  | A2.02.08 | SOW 3.12.1 | Cl 27, 40B |  | 2.02.01 | Demobilisation | Lot | LS | 1 |  | 0 |  | Milestone | 100% Site demobilised post PC
A | 2 | 02 | A202 | 09 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | DEMOBILISATION | Make-good and Reinstatement |  | A2.02.09 | SOW 3.12.2 | Cl 27 |  | 2.02.02 | Make-good and Reinstatement | Lot | LS | 1 |  | 0 |  | Milestone | 100% Site reinstated to pre-works condition
A | 2 | 02 | A202 | 10 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | DEMOBILISATION | Defects Liability & Close-out |  | A2.02.10 | SOW 3.11.6, 3.12.6 | Cl 35 |  | 2.02.03 | Defects Liability & Close-out | Lot | LS | 1 |  | 0 |  | Pro-rata over DLP | Pro-rata over 12-month DLP
A | 2 | 03 | A203 | 06 | 0 | 00 | 00 | 3 | Section A - Lump Sum | SITE WIDE | PROCUREMENT |  |  | A2.03 |  |  |  |  | PROCUREMENT |  |  |  |  | 0
A | 2 | 03 | A203 | 06 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | PROCUREMENT | Long Lead Items - HVAC Equipment |  | A2.03.06 | SOW 5.2, SDRL | Cl 9.1 | M-01 to M-05 | 2.03.01 | Long Lead Items - HVAC Equipment | Lot | LS | 1 |  | 0 |  | Milestone on delivery | 100% Equipment delivered to site
A | 2 | 03 | A203 | 07 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | PROCUREMENT | Long Lead Items - Switchboards |  | A2.03.07 | SOW 5.2, SDRL | Cl 9.1 | E-01 to E-05 | 2.03.02 | Long Lead Items - Switchboards | Lot | LS | 1 |  | 0 |  | Milestone on delivery | 100% Switchboards delivered to site
A | 2 | 03 | A203 | 08 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | PROCUREMENT | Long Lead Items - Fire Services Equipment |  | A2.03.08 | SOW 5.2 | Cl 9.2 | 690a-d | 2.03.03 | Long Lead Items - Fire Services Equipment | Lot | LS | 1 |  | 0 |  | Milestone on delivery | 100% Fire equipment delivered to site
A | 2 | 03 | A203 | 09 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | PROCUREMENT | Architectural Materials Supply |  | A2.03.09 | SOW 4.2.3 | Cl 9.2 | A1-A4 | 2.03.04 | Architectural Materials Supply | Lot | LS | 1 |  | 0 |  | Pro-rata on delivery | Pro-rata per material category delivered
A | 2 | 03 | A203 | 10 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | PROCUREMENT | Structural Materials Supply |  | A2.03.10 | SOW 4.2.1 | Cl 9.2 | 25-595_A1-A4 | 2.03.05 | Structural Materials Supply | Lot | LS | 1 |  | 0 |  | Milestone on delivery | 100% Steel/concrete materials delivered
A | 2 | 04 | A204 | 04 | 0 | 00 | 00 | 3 | Section A - Lump Sum | SITE WIDE | COMMISSIONING |  |  | A2.04 |  |  |  |  | COMMISSIONING |  |  |  |  | 0
A | 2 | 04 | A204 | 04 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | Pre-Commissioning Checks - All Services |  | A2.04.04 | SOW 5.1 | Cl 34, 35 |  | 2.04.01 | Pre-Commissioning Checks - All Services | Lot | LS | 1 |  | 0 |  | Milestone | 100% Pre-comm checklists complete
A | 2 | 04 | A204 | 05 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | HVAC Commissioning & Balancing |  | A2.04.05 | SOW 5.1 | Cl 34.3 | M-01 to M-05 | 2.04.02 | HVAC Commissioning & Balancing | Lot | LS | 1 |  | 0 |  | Milestone | 100% TAB report accepted
A | 2 | 04 | A204 | 06 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | Electrical Testing & Certification |  | A2.04.06 | SOW 5.1 | Cl 34.4 | E-01 to E-05 | 2.04.03 | Electrical Testing & Certification | Lot | LS | 1 |  | 0 |  | Milestone | 100% CCEW issued
A | 2 | 04 | A204 | 07 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | Fire Services Commissioning & Certification |  | A2.04.07 | SOW 5.1 | Cl 34.5 | 690a-d | 2.04.04 | Fire Services Commissioning & Certification | Lot | LS | 1 |  | 0 |  | Milestone | 100% Form 80/81 issued
A | 2 | 04 | A204 | 08 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | Hydraulic Testing |  | A2.04.08 | SOW 5.1 | Cl 34.6 | 690a-d | 2.04.05 | Hydraulic Testing | Lot | LS | 1 |  | 0 |  | Milestone | 100% Pressure tests passed
A | 2 | 04 | A204 | 09 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | BMS Integration & Commissioning |  | A2.04.09 | SOW 5.1 | Cl 35 |  | 2.04.06 | BMS Integration & Commissioning | Lot | LS | 1 |  | 0 |  | Milestone | 100% BMS functional, integrated with HVAC
A | 2 | 04 | A204 | 10 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | COMMISSIONING | Integrated Systems Testing |  | A2.04.10 | SOW 5.1 | Cl 35.2 |  | 2.04.07 | Integrated Systems Testing | Lot | LS | 1 |  | 0 |  | Milestone | 100% All systems functional together
A | 2 | 05 | A205 | 08 | 0 | 03 | 00 | 3 | Section A - Lump Sum | SITE WIDE | CLOSEOUT |  |  | A2.05 |  |  |  |  | CLOSEOUT |  |  |  |  | 0
A | 2 | 05 | A205 | 08 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | CLOSEOUT | As-Built Documentation |  | A2.05.08 | SOW 5.2, SDRL | Cl 8.4, 42 |  | 2.05.01 | As-Built Documentation | Lot | LS | 1 |  | 0 |  | Milestone | 100% As-builts accepted at PC
A | 2 | 05 | A205 | 09 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | CLOSEOUT | O&M Manuals |  | A2.05.09 | SOW 5.2 | Cl 42 |  | 2.05.02 | O&M Manuals | Lot | LS | 1 |  | 0 |  | Milestone | 100% O&M manuals accepted at PC
A | 2 | 05 | A205 | 10 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | CLOSEOUT | Training Delivery |  | A2.05.10 | SOW 5.3 | Cl 42 |  | 2.05.03 | Training Delivery | Lot | LS | 1 |  | 0 |  | Per session | Per training session delivered
A | 2 | 05 | A205 | 11 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | CLOSEOUT | Practical Completion Requirements |  | A2.05.11 | SOW 5.4 | Cl 42.1 |  | 2.05.04 | Practical Completion Requirements | Lot | LS | 1 |  | 0 |  | Milestone | 100% PC achieved
A | 2 | 05 | A205 | 12 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | CLOSEOUT | Defects Liability Period Support |  | A2.05.12 | SOW 5.5 | Cl 42.5 |  | 2.05.05 | Defects Liability Period Support | Lot | LS | 1 |  | 0 |  | Pro-rata over DLP | Pro-rata over 12-month DLP
A | 2 | 05 | A205 | 13 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | CLOSEOUT | Demobilisation & Site Restoration |  | A2.05.13 | SOW 3.12 | Cl 27 |  | 2.05.06 | Demobilisation & Site Restoration | Lot | LS | 1 |  | 0 |  | Milestone | 100% Site restored post PC
A | 2 | 06 | A206 | 00 | 0 | 00 | 00 | 3 | Section A - Lump Sum | SITE WIDE | EARTHWORKS |  |  | A2.06 |  |  |  |  | EARTHWORKS |  |  |  |  | 0
A | 2 | 06 | A206 | 00 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | EARTHWORKS | Site Clearing & Stripping |  | A2.06.00 | SOW 4.1, 9.2 | Cl 29.2 | A0/01-02 | 2.06.01 | Site Clearing & Stripping | m² | LS |  |  | 0 |  | Per m² of area cleared | Payment upon completion of clearing, stripping and stockpiling of topsoil
A | 2 | 06 | A206 | 01 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | EARTHWORKS | Bulk Earthworks - Cut & Fill |  | A2.06.01 | SOW 9.2 | Cl 29.2 | A0/01-02, 25-595_A4 | 2.06.02 | Bulk Earthworks - Cut & Fill | m³ | LS |  |  | 0 |  | Per m³ of material moved | Payment upon compaction testing passed
A | 2 | 06 | A206 | 02 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | EARTHWORKS | Subgrade Compaction & Proof Rolling |  | A2.06.02 | SOW 9.2 | Cl 29.2 | A0/01-02 | 2.06.03 | Subgrade Compaction & Proof Rolling | m² | LS |  |  | 0 |  | Per m² of area compacted | Payment upon compaction certificate issued
A | 2 | 06 | A206 | 03 | 1 | 01 | 00 | 4 | Section A - Lump Sum | SITE WIDE | EARTHWORKS | Import of Approved Fill Material |  | A2.06.03 | SOW 9.2 | Cl 29.2 | A0/01-02 | 2.06.04 | Import of Approved Fill Material | m³ | LS |  |  | 0 |  | Per m³ delivered and placed | Delivery dockets, compaction tests
A | 2 | 07 | A207 | 00 | 0 | 01 | 00 | 3 | Section A - Lump Sum | SITE WIDE | STORMWATER |  |  | A2.07 |  |  |  |  | STORMWATER |  |  |  |  | 0
A | 2 | 07 | A207 | 00 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | STORMWATER | Stormwater Pipes & Fittings |  | A2.07.00 | SOW 4.5, 9.4 | Cl 29.2 | 690a-d, A0/02 | 2.07.01 | Stormwater Pipes & Fittings | Lm | LS |  |  | 0 |  | Per linear metre installed | 60% supply delivered, 40% installed & tested
A | 2 | 07 | A207 | 01 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | STORMWATER | Stormwater Pits & Grates |  | A2.07.01 | SOW 4.5, 9.4 | Cl 29.2 | 690a-d, A0/02 | 2.07.02 | Stormwater Pits & Grates | No. | LS |  |  | 0 |  | Per pit complete | 50% supply, 50% installed with lid/grate
A | 2 | 07 | A207 | 02 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | STORMWATER | Headwalls & Outlet Structures |  | A2.07.02 | SOW 9.4 | Cl 29.2 | A0/02 | 2.07.03 | Headwalls & Outlet Structures | No. | LS |  |  | 0 |  | Per structure complete | Per structure complete including erosion protection
A | 2 | 07 | A207 | 03 | 1 | 02 | 00 | 4 | Section A - Lump Sum | SITE WIDE | STORMWATER | Stormwater Testing & CCTV |  | A2.07.03 | SOW 9.4, 5.1 | Cl 34.5 | 690a-d | 2.07.04 | Stormwater Testing & CCTV | Lot | LS | 1 |  | 0 |  | Lump sum upon completion | Test certificates and CCTV report submitted
A | 2 | 08 | A208 | 00 | 0 | 02 | 00 | 3 | Section A - Lump Sum | SITE WIDE | TRENCHING |  |  | A2.08 |  |  |  |  | TRENCHING |  |  |  |  | 0
A | 2 | 08 | A208 | 00 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | TRENCHING | Electrical Service Trenching & Conduits |  | A2.08.00 | SOW 4.4, 9.3 | Cl 29.2 | E-01 to E-05 | 2.08.01 | Electrical Service Trenching & Conduits | Lm | LS |  |  | 0 |  | Per linear metre complete | Trench, conduit, backfill, compaction
A | 2 | 08 | A208 | 01 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | TRENCHING | Communications Service Trenching |  | A2.08.01 | SOW 4.4, 9.3 | Cl 29.2 | E-01 to E-05 | 2.08.02 | Communications Service Trenching | Lm | LS |  |  | 0 |  | Per linear metre complete | Trench, conduit, pit, backfill
A | 2 | 08 | A208 | 02 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | TRENCHING | Hydraulic Service Trenching |  | A2.08.02 | SOW 4.5, 9.3 | Cl 29.2 | 690a-d | 2.08.03 | Hydraulic Service Trenching | Lm | LS |  |  | 0 |  | Per linear metre complete | Trench, pipe, backfill, testing
A | 2 | 08 | A208 | 03 | 1 | 03 | 00 | 4 | Section A - Lump Sum | SITE WIDE | TRENCHING | Service Pits & Duct Banks |  | A2.08.03 | SOW 9.3 | Cl 29.2 | E-01 to E-05 | 2.08.04 | Service Pits & Duct Banks | No. | LS |  |  | 0 |  | Per pit complete | Pit installed with lids and frames
A | 2 | 09 | A209 | 00 | 0 | 03 | 00 | 3 | Section A - Lump Sum | SITE WIDE | ROADS |  |  | A2.09 |  |  |  |  | ROADS |  |  |  |  | 0
A | 2 | 09 | A209 | 00 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | ROADS | Road Subbase Preparation |  | A2.09.00 | SOW 9.5 | Cl 29.2 | A0/01-02 | 2.09.01 | Road Subbase Preparation | m² | LS |  |  | 0 |  | Per m² of subbase prepared | Compaction test certificates
A | 2 | 09 | A209 | 01 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | ROADS | Road Base Course |  | A2.09.01 | SOW 9.5 | Cl 29.2 | A0/01-02 | 2.09.02 | Road Base Course | m² | LS |  |  | 0 |  | Per m² of base laid | Material delivery, compaction tests
A | 2 | 09 | A209 | 02 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | ROADS | Asphalt Wearing Course |  | A2.09.02 | SOW 9.5 | Cl 29.2 | A0/01-02 | 2.09.03 | Asphalt Wearing Course | m² | LS |  |  | 0 |  | Per m² of asphalt laid | Material delivered, surface complete
A | 2 | 09 | A209 | 03 | 1 | 04 | 00 | 4 | Section A - Lump Sum | SITE WIDE | ROADS | Road Line Marking & Signage |  | A2.09.03 | SOW 9.5 | Cl 29.2 | A0/01-02 | 2.09.04 | Road Line Marking & Signage | Lot | LS | 1 |  | 0 |  | Lump sum upon completion | Line marking and signage complete
A | 3 | 0 | A30 | 04 | 0 | 00 | 00 | 2 | Section A - Lump Sum | NEW OFFICE BUILDING |  |  |  | A3 |  |  |  |  | NEW OFFICE BUILDING |  |  |  |  | 0
A | 3 | 01 | A301 | 36 | 0 | 00 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION |  |  | A3.01 |  |  |  |  | DEMOLITION |  |  |  |  | 0
A | 3 | 01 | A301 | 36 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Strip Out Existing Finishes |  | A3.01.36 | SOW 4.1.1 | Cl 29.1 | A4/01-02 | 3.01.01 | Strip Out Existing Finishes | m² | LS |  |  | 0 |  | Per m² demolished | Per m² complete, waste removed
A | 3 | 01 | A301 | 37 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Asbestos Survey |  | A3.01.37 | SOW 4.1.2 | Cl 29.3, WHS Reg | A4/01-02 | 3.01.02 | Asbestos Survey | Lot | LS | 1 |  | 0 |  | Milestone | 100% Survey report accepted
A | 3 | 01 | A301 | 38 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Asbestos Removal (Licensed) |  | A3.01.38 | SOW 4.1.2 | Cl 29.3, WHS Reg | A4/01-02 | 3.01.03 | Asbestos Removal (Licensed) | m² | LS |  |  | 0 |  | Per m² removed | Per clearance certificate issued
A | 3 | 01 | A301 | 39 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Ceiling & Wall Demolition |  | A3.01.39 | SOW 4.1.1 | Cl 29.1 | A4/01-02 | 3.01.04 | Ceiling & Wall Demolition | m² | LS |  |  | 0 |  | Per m² demolished | Per m² complete, waste removed
A | 3 | 01 | A301 | 40 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Floor Covering Removal |  | A3.01.40 | SOW 4.1.1 | Cl 29.1 | A4/01-02 | 3.01.05 | Floor Covering Removal | m² | LS |  |  | 0 |  | Per m² removed | Per m² complete, waste removed
A | 3 | 01 | A301 | 41 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Services Strip Out (Mech/Elec/Hyd) |  | A3.01.41 | SOW 4.1.1 | Cl 29.1 | A4/01-02 | 3.01.06 | Services Strip Out (Mech/Elec/Hyd) | Lot | LS | 1 |  | 0 |  | Per discipline complete | Per discipline isolated and removed
A | 3 | 01 | A301 | 42 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | DEMOLITION | Waste Removal & Disposal |  | A3.01.42 | SOW 4.1.1 | Cl 29.1 |  | 3.01.07 | Waste Removal & Disposal | Lot | LS | 1 |  | 0 |  | Milestone | 100% Waste disposed lawfully
A | 3 | 02 | A302 | 12 | 0 | 00 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE |  |  | A3.02 |  |  |  |  | STRUCTURE |  |  |  |  | 0
A | 3 | 02 | A302 | 12 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Structural Assessment Report |  | A3.02.12 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-06 | 3.02.01 | Structural Assessment Report | Lot | LS | 1 |  | 0 |  | Milestone | 100% Report accepted
A | 3 | 02 | A302 | 13 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Bored Piers (BP1: 450Ø, 3.0m deep) |  | A3.02.13 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-02 | 3.02.02 | Bored Piers (BP1: 450Ø, 3.0m deep) | No. | LS |  |  | 0 |  | Per pier complete | 40% reo fixed, 60% concrete poured & cured
A | 3 | 02 | A302 | 14 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Ground Beams |  | A3.02.14 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-02 | 3.02.03 | Ground Beams | m | LS |  |  | 0 |  | Per linear metre | 40% reo fixed, 60% concrete poured & cured
A | 3 | 02 | A302 | 15 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Concrete Slab on Ground |  | A3.02.15 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-02 | 3.02.04 | Concrete Slab on Ground | m² | LS |  |  | 0 |  | Per m² complete | 30% prep/reo, 70% pour & finish
A | 3 | 02 | A302 | 16 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | SHS Columns (C1: 150x150x6, C2: 125x125x5, C3: 100x100x4) |  | A3.02.16 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/03-04 | 3.02.05 | SHS Columns (C1: 150x150x6, C2: 125x125x5, C3: 100x100x4) | No. | LS |  |  | 0 |  | Per column installed | 60% supply, 40% install & connect
A | 3 | 02 | A302 | 17 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Roof Beams (B1-B4) |  | A3.02.17 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/03-05 | 3.02.06 | Roof Beams (B1-B4) | m | LS |  |  | 0 |  | Per linear metre | 60% supply, 40% install & connect
A | 3 | 02 | A302 | 18 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Blockwork - 200 Series (Mech Stores) |  | A3.02.18 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/04 | 3.02.07 | Blockwork - 200 Series (Mech Stores) | m² | LS |  |  | 0 |  | Per m² laid | 50% blocks delivered, 50% laid & grouted
A | 3 | 02 | A302 | 19 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | STRUCTURE | Lintels (L1, L2) |  | A3.02.19 | SOW 4.2.1 | Cl 29.2 | 25-595_A4/04 | 3.02.08 | Lintels (L1, L2) | No. | LS |  |  | 0 |  | Per lintel installed | 60% supply, 40% install
A | 3 | 03 | A303 | 12 | 0 | 01 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF |  |  | A3.03 |  |  |  |  | ROOF |  |  |  |  | 0
A | 3 | 03 | A303 | 12 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Roof Trusses (T1) |  | A3.03.12 | SOW 4.2.2 | Cl 29.2 | 25-595_A4/05 | 3.03.01 | Roof Trusses (T1) | No. | LS |  |  | 0 |  | Per truss installed | 60% fabricated/delivered, 40% installed
A | 3 | 03 | A303 | 13 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Purlins (P1) |  | A3.03.13 | SOW 4.2.2 | Cl 29.2 | 25-595_A4/05 | 3.03.02 | Purlins (P1) | m | LS |  |  | 0 |  | Per linear metre | 50% supply, 50% fix
A | 3 | 03 | A303 | 14 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Roof Sheeting - Strammit Monoclad |  | A3.03.14 | SOW 4.2.2 | Cl 29.2 | A4/05 | 3.03.03 | Roof Sheeting - Strammit Monoclad | m² | LS |  |  | 0 |  | Per m² installed | 50% supply, 50% fix complete
A | 3 | 03 | A303 | 15 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Roof Insulation |  | A3.03.15 | SOW 4.2.2 | Cl 29.2 | A4/05 | 3.03.04 | Roof Insulation | m² | LS |  |  | 0 |  | Per m² installed | 50% supply, 50% fix complete
A | 3 | 03 | A303 | 16 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Gutters & Downpipes |  | A3.03.16 | SOW 4.2.2 | Cl 29.2 | A4/05, 690b | 3.03.05 | Gutters & Downpipes | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% fix & connect
A | 3 | 03 | A303 | 17 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Flashings & Penetrations |  | A3.03.17 | SOW 4.2.2 | Cl 29.2 | A4/05 | 3.03.06 | Flashings & Penetrations | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% fix & seal
A | 3 | 03 | A303 | 18 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ROOF | Awnings - Bondor Metecnospan |  | A3.03.18 | SOW 4.2.2 | Cl 29.2 | A4/05 | 3.03.07 | Awnings - Bondor Metecnospan | m² | LS |  |  | 0 |  | Per m² installed | 50% supply, 50% fix complete
A | 3 | 04 | A304 | 12 | 0 | 02 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL |  |  | A3.04 |  |  |  |  | EXTERNAL |  |  |  |  | 0
A | 3 | 04 | A304 | 12 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL | External Cladding |  | A3.04.12 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.04.01 | External Cladding | m² | LS |  |  | 0 |  | Per m² installed | 50% supply, 50% fix complete
A | 3 | 04 | A304 | 13 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL | Windows - G.James 475 Series (24 No.) |  | A3.04.13 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.04.02 | Windows - G.James 475 Series (24 No.) | No. | LS |  |  | 0 |  | Per window installed | 60% supply, 40% install & flash
A | 3 | 04 | A304 | 14 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL | External Doors (Types A-K) |  | A3.04.14 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.04.03 | External Doors (Types A-K) | No. | LS |  |  | 0 |  | Per door installed | 60% supply, 40% install complete
A | 3 | 04 | A304 | 15 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL | External Painting & Finishes |  | A3.04.15 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.04.04 | External Painting & Finishes | m² | LS |  |  | 0 |  | Per m² complete | 30% prep, 70% paint system complete
A | 3 | 05 | A305 | 15 | 0 | 03 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT |  |  | A3.05 |  |  |  |  | FITOUT |  |  |  |  | 0
A | 3 | 05 | A305 | 15 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT | Partitions - Steel Stud/Plasterboard |  | A3.05.15 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.05.01 | Partitions - Steel Stud/Plasterboard | m² | LS |  |  | 0 |  | Per m² complete | 40% frame, 60% line & finish
A | 3 | 05 | A305 | 16 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT | Suspended Ceilings - 1200x600 Acoustic |  | A3.05.16 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.05.02 | Suspended Ceilings - 1200x600 Acoustic | m² | LS |  |  | 0 |  | Per m² complete | 40% grid, 60% tiles installed
A | 3 | 05 | A305 | 17 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT | Ceiling Insulation |  | A3.05.17 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.05.03 | Ceiling Insulation | m² | LS |  |  | 0 |  | Per m² installed | 50% supply, 50% install
A | 3 | 05 | A305 | 18 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT | Internal Doors (24 No.) |  | A3.05.18 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.05.04 | Internal Doors (24 No.) | No. | LS |  |  | 0 |  | Per door complete | 60% supply, 40% install & hardware
A | 3 | 05 | A305 | 19 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT | Internal Glazing & Screens |  | A3.05.19 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.05.05 | Internal Glazing & Screens | m² | LS |  |  | 0 |  | Per m² installed | 60% supply, 40% install
A | 3 | 05 | A305 | 20 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FITOUT | Bulkheads & Soffits |  | A3.05.20 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.05.06 | Bulkheads & Soffits | m² | LS |  |  | 0 |  | Per m² complete | 40% frame, 60% line & finish
A | 3 | 06 | A306 | 05 | 0 | 00 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL |  |  | A3.06 |  |  |  |  | MECHANICAL |  |  |  |  | 0
A | 3 | 06 | A306 | 05 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL | Air Conditioning Units (AC-1 to AC-5) |  | A3.06.05 | SOW 4.3 | Cl 29.2 | M-01, M-05 | 3.06.01 | Air Conditioning Units (AC-1 to AC-5) | No. | LS |  |  | 0 |  | Per unit complete | 70% supply, 30% install & commission
A | 3 | 06 | A306 | 06 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL | VAV Boxes (VAV-1 to VAV-7) |  | A3.06.06 | SOW 4.3 | Cl 29.2 | M-01, M-05 | 3.06.02 | VAV Boxes (VAV-1 to VAV-7) | No. | LS |  |  | 0 |  | Per unit complete | 70% supply, 30% install & balance
A | 3 | 06 | A306 | 07 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL | Ductwork - Supply & Return |  | A3.06.07 | SOW 4.3 | Cl 29.2 | M-01 to M-05 | 3.06.03 | Ductwork - Supply & Return | m² | LS |  |  | 0 |  | Per m² duct face | 50% fabricate, 50% install
A | 3 | 06 | A306 | 08 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL | Diffusers & Grilles |  | A3.06.08 | SOW 4.3 | Cl 29.2 | M-01 to M-05 | 3.06.04 | Diffusers & Grilles | No. | LS |  |  | 0 |  | Per diffuser installed | 60% supply, 40% install & balance
A | 3 | 06 | A306 | 09 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL | Controls & BMS Integration |  | A3.06.09 | SOW 4.3 | Cl 29.2 | M-01 to M-05 | 3.06.05 | Controls & BMS Integration | Lot | LS | 1 |  | 0 |  | Milestone | 40% hardware, 60% commission
A | 3 | 06 | A306 | 10 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | MECHANICAL | Refrigerant Pipework |  | A3.06.10 | SOW 4.3 | Cl 29.2 | M-01 to M-05 | 3.06.06 | Refrigerant Pipework | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% install & pressure test
A | 3 | 07 | A307 | 05 | 0 | 01 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL |  |  | A3.07 |  |  |  |  | ELECTRICAL |  |  |  |  | 0
A | 3 | 07 | A307 | 05 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Main Switchboard (MSB) |  | A3.07.05 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.01 | Main Switchboard (MSB) | No. | LS | 1 |  | 0 |  | Per board complete | 70% supply, 30% install & connect
A | 3 | 07 | A307 | 06 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Distribution Boards |  | A3.07.06 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.02 | Distribution Boards | No. | LS |  |  | 0 |  | Per board complete | 70% supply, 30% install & connect
A | 3 | 07 | A307 | 07 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Submains Cabling |  | A3.07.07 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.03 | Submains Cabling | m | LS |  |  | 0 |  | Per linear metre | 50% supply, 50% install & terminate
A | 3 | 07 | A307 | 08 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | General Power Outlets |  | A3.07.08 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.04 | General Power Outlets | No. | LS |  |  | 0 |  | Per outlet complete | 40% supply, 60% install & test
A | 3 | 07 | A307 | 09 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Lighting Installation |  | A3.07.09 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.05 | Lighting Installation | No. | LS |  |  | 0 |  | Per fitting complete | 50% supply, 50% install & commission
A | 3 | 07 | A307 | 10 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Emergency Lighting |  | A3.07.10 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.06 | Emergency Lighting | No. | LS |  |  | 0 |  | Per fitting complete | 50% supply, 50% install & test
A | 3 | 07 | A307 | 11 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Data/Communications Cabling |  | A3.07.11 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.07 | Data/Communications Cabling | No. | LS |  |  | 0 |  | Per outlet complete | 50% supply/cable, 50% terminate & test
A | 3 | 07 | A307 | 12 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | ELECTRICAL | Earthing System |  | A3.07.12 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.07.08 | Earthing System | Lot | LS | 1 |  | 0 |  | Milestone | 40% materials, 60% install & test
A | 3 | 08 | A308 | 05 | 0 | 02 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | HYDRAULIC |  |  | A3.08 |  |  |  |  | HYDRAULIC |  |  |  |  | 0
A | 3 | 08 | A308 | 05 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | HYDRAULIC | Cold Water Reticulation |  | A3.08.05 | SOW 4.5 | Cl 29.2 | 690b | 3.08.01 | Cold Water Reticulation | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% install & pressure test
A | 3 | 08 | A308 | 06 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | HYDRAULIC | Hot Water System & Reticulation |  | A3.08.06 | SOW 4.5 | Cl 29.2 | 690b | 3.08.02 | Hot Water System & Reticulation | Lot | LS | 1 |  | 0 |  | Per system complete | 60% supply, 40% install & commission
A | 3 | 08 | A308 | 07 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | HYDRAULIC | Sanitary Plumbing |  | A3.08.07 | SOW 4.5 | Cl 29.2 | 690b | 3.08.03 | Sanitary Plumbing | Lot | LS | 1 |  | 0 |  | Per fixture connected | 40% rough-in, 60% fit-off & test
A | 3 | 08 | A308 | 08 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | HYDRAULIC | Sewer Drainage |  | A3.08.08 | SOW 4.5 | Cl 29.2 | 690b | 3.08.04 | Sewer Drainage | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% install & CCTV
A | 3 | 08 | A308 | 09 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | HYDRAULIC | Stormwater Drainage |  | A3.08.09 | SOW 4.5 | Cl 29.2 | 690b | 3.08.05 | Stormwater Drainage | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% install & test
A | 3 | 09 | A309 | 05 | 0 | 03 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | FIRE |  |  | A3.09 |  |  |  |  | FIRE |  |  |  |  | 0
A | 3 | 09 | A309 | 05 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FIRE | Fire Hydrants |  | A3.09.05 | SOW 4.5 | Cl 29.2 | 690b | 3.09.01 | Fire Hydrants | No. | LS |  |  | 0 |  | Per hydrant complete | 60% supply, 40% install & commission
A | 3 | 09 | A309 | 06 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FIRE | Fire Hose Reels |  | A3.09.06 | SOW 4.5 | Cl 29.2 | 690b | 3.09.02 | Fire Hose Reels | No. | LS |  |  | 0 |  | Per hose reel complete | 60% supply, 40% install & commission
A | 3 | 09 | A309 | 07 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FIRE | Fire Indicator Panel (FIP) |  | A3.09.07 | SOW 4.5 | Cl 29.2 | 690b | 3.09.03 | Fire Indicator Panel (FIP) | No. | LS | 1 |  | 0 |  | Per FIP complete | 70% supply, 30% install & commission
A | 3 | 09 | A309 | 08 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FIRE | Smoke/Heat Detectors |  | A3.09.08 | SOW 4.5 | Cl 29.2 | 690b | 3.09.04 | Smoke/Heat Detectors | No. | LS |  |  | 0 |  | Per detector installed | 50% supply, 50% install & commission
A | 3 | 09 | A309 | 09 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FIRE | Fire Extinguishers & Blankets |  | A3.09.09 | SOW 4.5 | Cl 29.2 | 690b | 3.09.05 | Fire Extinguishers & Blankets | No. | LS |  |  | 0 |  | Per unit installed | 80% supply, 20% install & tag
A | 3 | 10 | A310 | 00 | 0 | 00 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES |  |  | A3.10 |  |  |  |  | FINISHES |  |  |  |  | 0
A | 3 | 10 | A310 | 00 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES | Floor Tiles - Amenities |  | A3.10.00 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.10.01 | Floor Tiles - Amenities | m² | LS |  |  | 0 |  | Per m² complete | 50% supply, 50% lay & grout
A | 3 | 10 | A310 | 01 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES | Carpet Tiles - Office Areas |  | A3.10.01 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.10.02 | Carpet Tiles - Office Areas | m² | LS |  |  | 0 |  | Per m² complete | 50% supply, 50% install
A | 3 | 10 | A310 | 02 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES | Vinyl - Wet Areas |  | A3.10.02 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.10.03 | Vinyl - Wet Areas | m² | LS |  |  | 0 |  | Per m² complete | 50% supply, 50% install
A | 3 | 10 | A310 | 03 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES | Wall Tiles - Amenities |  | A3.10.03 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.10.04 | Wall Tiles - Amenities | m² | LS |  |  | 0 |  | Per m² complete | 50% supply, 50% lay & grout
A | 3 | 10 | A310 | 04 | 1 | 01 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES | Internal Painting |  | A3.10.04 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.10.05 | Internal Painting | m² | LS |  |  | 0 |  | Per m² complete | 30% prep, 70% paint system complete
A | 3 | 10 | A310 | 05 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FINISHES | Skirtings & Architraves |  | A3.10.05 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.10.06 | Skirtings & Architraves | m | LS |  |  | 0 |  | Per linear metre | 40% supply, 60% install & finish
A | 3 | 11 | A311 | 00 | 0 | 01 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | JOINERY |  |  | A3.11 |  |  |  |  | JOINERY |  |  |  |  | 0
A | 3 | 11 | A311 | 00 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | JOINERY | Kitchenette Joinery |  | A3.11.00 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.11.01 | Kitchenette Joinery | No. | LS |  |  | 0 |  | Per kitchenette complete | 70% fabricate, 30% install & connect
A | 3 | 11 | A311 | 01 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | JOINERY | Reception Counter |  | A3.11.01 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.11.02 | Reception Counter | No. | LS | 1 |  | 0 |  | Per item complete | 70% fabricate, 30% install
A | 3 | 11 | A311 | 02 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | JOINERY | Storage Cupboards |  | A3.11.02 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.11.03 | Storage Cupboards | No. | LS |  |  | 0 |  | Per cupboard complete | 70% fabricate, 30% install
A | 3 | 11 | A311 | 03 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | JOINERY | Vanity Units - Amenities |  | A3.11.03 | SOW 4.2.3 | Cl 29.2 | A4/03-04 | 3.11.04 | Vanity Units - Amenities | No. | LS |  |  | 0 |  | Per vanity complete | 70% fabricate, 30% install & connect
A | 3 | 12 | A312 | 00 | 0 | 02 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE |  |  | A3.12 |  |  |  |  | FFE |  |  |  |  | 0
A | 3 | 12 | A312 | 00 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE | Workstations |  | A3.12.00 | SOW 4.6 | Cl 29.2 | A4 Furniture | 3.12.01 | Workstations | No. | LS |  |  | 0 |  | Per workstation complete | 90% supply, 10% install
A | 3 | 12 | A312 | 01 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE | Task Chairs |  | A3.12.01 | SOW 4.6 | Cl 29.2 | A4 Furniture | 3.12.02 | Task Chairs | No. | LS |  |  | 0 |  | Per chair delivered | 100% supply
A | 3 | 12 | A312 | 02 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE | Meeting Room Tables |  | A3.12.02 | SOW 4.6 | Cl 29.2 | A4 Furniture | 3.12.03 | Meeting Room Tables | No. | LS |  |  | 0 |  | Per table complete | 90% supply, 10% install
A | 3 | 12 | A312 | 03 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE | Lockers |  | A3.12.03 | SOW 4.6 | Cl 29.2 | A4 Furniture | 3.12.04 | Lockers | No. | LS |  |  | 0 |  | Per bank complete | 80% supply, 20% install & anchor
A | 3 | 12 | A312 | 04 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE | Whiteboards & Pinboards |  | A3.12.04 | SOW 4.6 | Cl 29.2 | A4 Furniture | 3.12.05 | Whiteboards & Pinboards | No. | LS |  |  | 0 |  | Per board installed | 80% supply, 20% install
A | 3 | 12 | A312 | 05 | 1 | 06 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | FFE | Kitchen Appliances |  | A3.12.05 | SOW 4.6 | Cl 29.2 | A4 Furniture | 3.12.06 | Kitchen Appliances | Lot | LS | 1 |  | 0 |  | Per appliance installed | 90% supply, 10% install & commission
A | 3 | 13 | A313 | 00 | 0 | 03 | 00 | 3 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS |  |  | A3.13 |  |  |  |  | EXTERNAL WORKS |  |  |  |  | 0
A | 3 | 13 | A313 | 00 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | New Office Parking Area - Subbase |  | A3.13.00 | SOW 9.5 | Cl 29.2 | A0/01-02, A4/01 | 3.13.01 | New Office Parking Area - Subbase | m² | LS |  |  | 0 |  | Per m² complete | Subbase compacted, tested
A | 3 | 13 | A313 | 01 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | New Office Parking Area - Paving |  | A3.13.01 | SOW 9.5 | Cl 29.2 | A0/01-02, A4/01 | 3.13.02 | New Office Parking Area - Paving | m² | LS |  |  | 0 |  | Per m² complete | Paving/concrete surface complete
A | 3 | 13 | A313 | 02 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Carpark Line Marking & Signage |  | A3.13.02 | SOW 9.5 | Cl 29.2 | A0/01-02 | 3.13.03 | Carpark Line Marking & Signage | Lot | LS | 1 |  | 0 |  | Lump sum | Line marking and signage complete
A | 3 | 13 | A313 | 03 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Wheel Stops & Bollards |  | A3.13.03 | SOW 9.5 | Cl 29.2 | A0/01-02 | 3.13.04 | Wheel Stops & Bollards | No. | LS |  |  | 0 |  | Per item installed | Supply and fix complete
A | 3 | 13 | A313 | 04 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Concrete Footpaths |  | A3.13.04 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A4/01 | 3.13.05 | Concrete Footpaths | m² | LS |  |  | 0 |  | Per m² complete | Formwork, pour, finish
A | 3 | 13 | A313 | 05 | 1 | 07 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Feature Paver Footpaths - Entry |  | A3.13.05 | SOW 9.5.1, 9.6.1 | Cl 29.2 | A0/01-02, A4/01 | 3.13.06 | Feature Paver Footpaths - Entry | m² | LS |  |  | 0 |  | Per m² complete | Bedding, pavers laid, sealed
A | 3 | 13 | A313 | 06 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Access Ramps (DDA Compliant) |  | A3.13.06 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A4/01 | 3.13.07 | Access Ramps (DDA Compliant) | No. | LS |  |  | 0 |  | Per ramp complete | Structure, handrails, TGSIs
A | 3 | 13 | A313 | 07 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | External Stairs & Landings |  | A3.13.07 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A4/01 | 3.13.08 | External Stairs & Landings | No. | LS |  |  | 0 |  | Per flight complete | Structure, treads, handrails
A | 3 | 13 | A313 | 08 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Courtyard Retaining Wall |  | A3.13.08 | SOW 9.5.3 | Cl 29.2 | 25-595_A4, A0/02 | 3.13.09 | Courtyard Retaining Wall | Lm | LS |  |  | 0 |  | Per Lm complete | Footing, wall, drainage, backfill
A | 3 | 13 | A313 | 09 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Security Fencing |  | A3.13.09 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 3.13.10 | Security Fencing | Lm | LS |  |  | 0 |  | Per Lm installed | Posts, rails, mesh complete
A | 3 | 13 | A313 | 10 | 1 | 03 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Pedestrian & Vehicle Gates |  | A3.13.10 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 3.13.11 | Pedestrian & Vehicle Gates | No. | LS |  |  | 0 |  | Per gate installed | Gate supplied, installed, operational
A | 3 | 13 | A313 | 11 | 1 | 02 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | External Handrails & Balustrades |  | A3.13.11 | SOW 9.5.2 | Cl 29.2 | A0/01-02, A4/01 | 3.13.12 | External Handrails & Balustrades | Lm | LS |  |  | 0 |  | Per Lm installed | Posts, rails, infill complete
A | 3 | 13 | A313 | 12 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Courtyard Hardscape Paving |  | A3.13.12 | SOW 9.6.1 | Cl 29.2 | A0/01-02, A4/01 | 3.13.13 | Courtyard Hardscape Paving | m² | LS |  |  | 0 |  | Per m² complete | Paving, edging, integration
A | 3 | 13 | A313 | 13 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Turf Areas |  | A3.13.13 | SOW 9.6.2 | Cl 29.2 | A0/01-02 | 3.13.14 | Turf Areas | m² | LS |  |  | 0 |  | Per m² laid | Soil prep, turf supply, laying
A | 3 | 13 | A313 | 14 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Garden Beds - Shrubs & Groundcover |  | A3.13.14 | SOW 9.6.2 | Cl 29.2 | A0/01-02 | 3.13.15 | Garden Beds - Shrubs & Groundcover | m² | LS |  |  | 0 |  | Per m² complete | Soil, plants, mulch complete
A | 3 | 13 | A313 | 15 | 1 | 05 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Feature Trees |  | A3.13.15 | SOW 9.6.2 | Cl 29.2 | A0/01-02 | 3.13.16 | Feature Trees | No. | LS |  |  | 0 |  | Per tree planted | Tree supply, planting, staking
A | 3 | 13 | A313 | 16 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Irrigation System |  | A3.13.16 | SOW 9.6.2 | Cl 29.2 | 690a-d | 3.13.17 | Irrigation System | Lot | LS | 1 |  | 0 |  | Lump sum | Pipes, heads, controller complete
A | 3 | 13 | A313 | 17 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | External & Landscape Lighting |  | A3.13.17 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 3.13.18 | External & Landscape Lighting | No. | LS |  |  | 0 |  | Per light installed | Pole, fixture, cabling complete
A | 3 | 13 | A313 | 18 | 1 | 04 | 00 | 4 | Section A - Lump Sum | NEW OFFICE BUILDING | EXTERNAL WORKS | Shade Structures - Courtyard |  | A3.13.18 | SOW 9.5.4 | Cl 29.2 | A0/01-02, A4/01 | 3.13.19 | Shade Structures - Courtyard | No. | LS |  |  | 0 |  | Per structure installed | Footings, structure, membrane
A | 4 | 0 | A40 | 05 | 0 | 00 | 00 | 2 | Section A - Lump Sum | REGISTRY BUILDING |  |  |  | A4 |  |  |  |  | REGISTRY BUILDING |  |  |  |  | 0
A | 4 | 01 | A401 | 44 | 0 | 00 | 00 | 3 | Section A - Lump Sum | REGISTRY BUILDING | DEMOLITION |  |  | A4.01 |  |  |  |  | DEMOLITION |  |  |  |  | 0
A | 4 | 01 | A401 | 44 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | DEMOLITION | Strip Out Existing Finishes |  | A4.01.44 | SOW 4.1 | Cl 29.1 | 25-595_A1/02 | 4.01.01 | Strip Out Existing Finishes | m² | LS |  |  | 0 |  | Per m² demolished | Per m² complete, waste removed
A | 4 | 01 | A401 | 45 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | DEMOLITION | Hazardous Materials Removal |  | A4.01.45 | SOW 4.1.2 | Cl 29.3 | 25-595_A1/02 | 4.01.02 | Hazardous Materials Removal | Lot | LS | 1 |  | 0 |  | Milestone | Per clearance certificate
A | 4 | 02 | A402 | 21 | 0 | 00 | 00 | 3 | Section A - Lump Sum | REGISTRY BUILDING | STRUCTURE |  |  | A4.02 |  |  |  |  | STRUCTURE |  |  |  |  | 0
A | 4 | 02 | A402 | 21 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | STRUCTURE | Structural Assessment & Repairs |  | A4.02.21 | SOW 4.2.1 | Cl 29.2 | 25-595_A1/01-04 | 4.02.01 | Structural Assessment & Repairs | Lot | LS | 1 |  | 0 |  | Milestone | 30% assessment, 70% repairs complete
A | 4 | 02 | A402 | 22 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | STRUCTURE | Concrete Slab Repairs |  | A4.02.22 | SOW 4.2.1 | Cl 29.2 | 25-595_A1/01-04 | 4.02.02 | Concrete Slab Repairs | m² | LS |  |  | 0 |  | Per m² repaired | 30% prep, 70% repair & finish
A | 4 | 03 | A403 | 20 | 0 | 00 | 00 | 3 | Section A - Lump Sum | REGISTRY BUILDING | ROOF |  |  | A4.03 |  |  |  |  | ROOF |  |  |  |  | 0
A | 4 | 03 | A403 | 20 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | ROOF | Roof Refurbishment Package |  | A4.03.20 | SOW 4.2.2 | Cl 29.2 | 25-595_A1/03-04 | 4.03.01 | Roof Refurbishment Package | Lot | LS | 1 |  | 0 |  | Milestone | 40% materials, 60% install complete
A | 4 | 04 | A404 | 17 | 0 | 00 | 00 | 3 | Section A - Lump Sum | REGISTRY BUILDING | SERVICES |  |  | A4.04 |  |  |  |  | SERVICES |  |  |  |  | 0
A | 4 | 04 | A404 | 17 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | SERVICES | Mechanical Services Package |  | A4.04.17 | SOW 4.3 | Cl 29.2 | M-02 | 4.04.01 | Mechanical Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 60% supply, 40% install & commission
A | 4 | 04 | A404 | 18 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | SERVICES | Electrical Services Package |  | A4.04.18 | SOW 4.4 | Cl 29.2 | E-02 | 4.04.02 | Electrical Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 50% supply, 50% install & test
A | 4 | 04 | A404 | 19 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | SERVICES | Hydraulic Services Package |  | A4.04.19 | SOW 4.5 | Cl 29.2 | 690c | 4.04.03 | Hydraulic Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 40% supply, 60% install & test
A | 4 | 04 | A404 | 20 | 1 | 02 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | SERVICES | Fire Services Package |  | A4.04.20 | SOW 4.5 | Cl 29.2 | 690c | 4.04.04 | Fire Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 60% supply, 40% install & commission
A | 4 | 05 | A405 | 22 | 0 | 01 | 00 | 3 | Section A - Lump Sum | REGISTRY BUILDING | FITOUT |  |  | A4.05 |  |  |  |  | FITOUT |  |  |  |  | 0
A | 4 | 05 | A405 | 22 | 1 | 02 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | FITOUT | Partitions & Ceilings Package |  | A4.05.22 | SOW 4.2.3 | Cl 29.2 | A1/03-04 | 4.05.01 | Partitions & Ceilings Package | Lot | LS | 1 |  | 0 |  | Milestone | 40% frame, 60% line & finish
A | 4 | 05 | A405 | 23 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | FITOUT | Floor & Wall Finishes Package |  | A4.05.23 | SOW 4.2.3 | Cl 29.2 | A1/03-04 | 4.05.02 | Floor & Wall Finishes Package | Lot | LS | 1 |  | 0 |  | Per m² complete | 50% supply, 50% install
A | 4 | 05 | A405 | 24 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | FITOUT | Joinery Package |  | A4.05.24 | SOW 4.2.3 | Cl 29.2 | A1/03-04 | 4.05.03 | Joinery Package | Lot | LS | 1 |  | 0 |  | Per item complete | 70% fabricate, 30% install
A | 4 | 05 | A405 | 25 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY BUILDING | FITOUT | FFE Package |  | A4.05.25 | SOW 4.6 | Cl 29.2 | A1 Furniture | 4.05.04 | FFE Package | Lot | LS | 1 |  | 0 |  | Per item delivered | 90% supply, 10% install
A | 0 | 13 | A013 | 20 | 0 | 00 | 00 | 3 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS |  |  | A0.13 |  |  |  |  | EXTERNAL WORKS |  |  |  |  | 0
A | 0 | 13 | A013 | 20 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry Parking Area |  | A0.13.20 | SOW 9.5 | Cl 29.2 | A0/01-02, A1/01-02 | 0.13.01 | Registry Parking Area | m² | LS |  |  | 0 |  | Per m² complete | Subbase + paving complete
A | 0 | 13 | A013 | 21 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry Footpaths & Entry |  | A0.13.21 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A1/01-02 | 0.13.02 | Registry Footpaths & Entry | m² | LS |  |  | 0 |  | Per m² complete | Formwork, concrete, finish
A | 0 | 13 | A013 | 22 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry Access Ramps (DDA) |  | A0.13.22 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A1/01-02 | 0.13.03 | Registry Access Ramps (DDA) | No. | LS |  |  | 0 |  | Per ramp complete | Structure, handrails, TGSIs
A | 0 | 13 | A013 | 23 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry Landscaping - Hardscape |  | A0.13.23 | SOW 9.6 | Cl 29.2 | A0/01-02 | 0.13.04 | Registry Landscaping - Hardscape | m² | LS |  |  | 0 |  | Per m² complete | Paving, edging complete
A | 0 | 13 | A013 | 24 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry Landscaping - Softscape |  | A0.13.24 | SOW 9.6.2 | Cl 29.2 | A0/01-02 | 0.13.05 | Registry Landscaping - Softscape | m² | LS |  |  | 0 |  | Per m² complete | Turf/planting, mulch complete
A | 0 | 13 | A013 | 25 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry External Lighting |  | A0.13.25 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 0.13.06 | Registry External Lighting | No. | LS |  |  | 0 |  | Per light installed | Pole, fixture, cabling complete
A | 0 | 13 | A013 | 26 | 1 | 01 | 00 | 4 | Section A - Lump Sum | REGISTRY (Bldg 101) | EXTERNAL WORKS | Registry Perimeter Works |  | A0.13.26 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 0.13.07 | Registry Perimeter Works | Lot | LS | 1 |  | 0 |  | Provisional Sum | Fencing, gates as required
A | 5 | 0 | A50 | 06 | 0 | 00 | 00 | 2 | Section A - Lump Sum | WORKSHOP BUILDING |  |  |  | A5 |  |  |  |  | WORKSHOP BUILDING |  |  |  |  | 0
A | 5 | 01 | A501 | 47 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WORKSHOP BUILDING | DEMOLITION |  |  | A5.01 |  |  |  |  | DEMOLITION |  |  |  |  | 0
A | 5 | 01 | A501 | 47 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | DEMOLITION | Strip Out & Hazmat Removal |  | A5.01.47 | SOW 4.1 | Cl 29.1 | 25-595_A2/02 | 5.01.01 | Strip Out & Hazmat Removal | Lot | LS | 1 |  | 0 |  | Milestone | Per clearance certificate
A | 5 | 02 | A502 | 24 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WORKSHOP BUILDING | STRUCTURE |  |  | A5.02 |  |  |  |  | STRUCTURE |  |  |  |  | 0
A | 5 | 02 | A502 | 24 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | STRUCTURE | Structural Assessment & Repairs Package |  | A5.02.24 | SOW 4.2.1 | Cl 29.2 | 25-595_A2/01-04 | 5.02.01 | Structural Assessment & Repairs Package | Lot | LS | 1 |  | 0 |  | Milestone | 30% assessment, 70% repairs
A | 5 | 02 | A502 | 25 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | STRUCTURE | Roof Refurbishment Package |  | A5.02.25 | SOW 4.2.2 | Cl 29.2 | 25-595_A2/03-04 | 5.02.02 | Roof Refurbishment Package | Lot | LS | 1 |  | 0 |  | Milestone | 40% supply, 60% install
A | 5 | 04 | A504 | 22 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WORKSHOP BUILDING | SERVICES |  |  | A5.04 |  |  |  |  | SERVICES |  |  |  |  | 0
A | 5 | 04 | A504 | 22 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | SERVICES | Mechanical Services Package |  | A5.04.22 | SOW 4.3 | Cl 29.2 | M-03 | 5.04.01 | Mechanical Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 60% supply, 40% install & commission
A | 5 | 04 | A504 | 23 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | SERVICES | Electrical Services Package |  | A5.04.23 | SOW 4.4 | Cl 29.2 | E-03 | 5.04.02 | Electrical Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 50% supply, 50% install & test
A | 5 | 04 | A504 | 24 | 1 | 02 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | SERVICES | Hydraulic & Fire Services Package |  | A5.04.24 | SOW 4.5 | Cl 29.2 | 690d | 5.04.03 | Hydraulic & Fire Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 50% supply, 50% install & test
A | 5 | 05 | A505 | 27 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WORKSHOP BUILDING | FITOUT |  |  | A5.05 |  |  |  |  | FITOUT |  |  |  |  | 0
A | 5 | 05 | A505 | 27 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | FITOUT | Internal Fitout Package |  | A5.05.27 | SOW 4.2.3 | Cl 29.2 | A2/03-04 | 5.05.01 | Internal Fitout Package | Lot | LS | 1 |  | 0 |  | Milestone | 50% supply, 50% install
A | 5 | 05 | A505 | 28 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | FITOUT | Finishes & Joinery Package |  | A5.05.28 | SOW 4.2.3 | Cl 29.2 | A2/03-04 | 5.05.02 | Finishes & Joinery Package | Lot | LS | 1 |  | 0 |  | Milestone | 60% supply, 40% install
A | 5 | 05 | A505 | 29 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP BUILDING | FITOUT | FFE Package |  | A5.05.29 | SOW 4.6 | Cl 29.2 | A2 Furniture | 5.05.03 | FFE Package | Lot | LS | 1 |  | 0 |  | Per item delivered | 90% supply, 10% install
A | 0 | 13 | A013 | 28 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS |  |  | A0.13 |  |  |  |  | EXTERNAL WORKS |  |  |  |  | 0
A | 0 | 13 | A013 | 28 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop Parking Area |  | A0.13.28 | SOW 9.5 | Cl 29.2 | A0/01-02, A2/01 | 0.13.09 | Workshop Parking Area | m² | LS |  |  | 0 |  | Per m² complete | Subbase + paving complete
A | 0 | 13 | A013 | 29 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop Hardstand & Aprons |  | A0.13.29 | SOW 9.5 | Cl 29.2 | A0/01-02, A2/01 | 0.13.10 | Workshop Hardstand & Aprons | m² | LS |  |  | 0 |  | Per m² complete | Concrete poured and finished
A | 0 | 13 | A013 | 30 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop Footpaths & Access |  | A0.13.30 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A2/01 | 0.13.11 | Workshop Footpaths & Access | m² | LS |  |  | 0 |  | Per m² complete | Formwork, concrete, finish
A | 0 | 13 | A013 | 31 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop Compound Fencing |  | A0.13.31 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 0.13.12 | Workshop Compound Fencing | Lm | LS |  |  | 0 |  | Per Lm installed | Posts, rails, mesh complete
A | 0 | 13 | A013 | 32 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop Gates |  | A0.13.32 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 0.13.13 | Workshop Gates | No. | LS |  |  | 0 |  | Per gate installed | Gate supplied, installed, operational
A | 0 | 13 | A013 | 33 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop External Lighting |  | A0.13.33 | SOW 4.4 | Cl 29.2 | E-01 to E-05 | 0.13.14 | Workshop External Lighting | No. | LS |  |  | 0 |  | Per light installed | Pole, fixture, cabling complete
A | 0 | 13 | A013 | 34 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WORKSHOP (Bldg 102) | EXTERNAL WORKS | Workshop Landscaping Allowance |  | A0.13.34 | SOW 9.6 | Cl 29.2 | A0/01-02 | 0.13.15 | Workshop Landscaping Allowance | Lot | LS | 1 |  | 0 |  | Provisional Sum | Turf, planting as required
A | 6 | 0 | A60 | 07 | 0 | 00 | 00 | 2 | Section A - Lump Sum | WAREHOUSE BUILDING |  |  |  | A6 |  |  |  |  | WAREHOUSE BUILDING |  |  |  |  | 0
A | 6 | 07 | A607 | 14 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WAREHOUSE BUILDING | WORKS |  |  | A6.07 |  |  |  |  | WORKS |  |  |  |  | 0
A | 6 | 07 | A607 | 14 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE BUILDING | WORKS | Demolition & Hazmat Package |  | A6.07.14 | SOW 4.1 | Cl 29.1 | 25-595_A3/01-02 | 6.07.01 | Demolition & Hazmat Package | Lot | LS | 1 |  | 0 |  | Milestone | Per clearance certificate
A | 6 | 07 | A607 | 15 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE BUILDING | WORKS | Structural & Roof Package |  | A6.07.15 | SOW 4.2.1 | Cl 29.2 | 25-595_A3/01-02 | 6.07.02 | Structural & Roof Package | Lot | LS | 1 |  | 0 |  | Milestone | 40% supply, 60% install
A | 6 | 07 | A607 | 16 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE BUILDING | WORKS | Building Services Package |  | A6.07.16 | SOW 4.3-4.5 | Cl 29.2 | M-04, E-04, 690a | 6.07.03 | Building Services Package | Lot | LS | 1 |  | 0 |  | Milestone | 50% supply, 50% install & commission
A | 6 | 07 | A607 | 17 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE BUILDING | WORKS | Internal Fitout & Finishes |  | A6.07.17 | SOW 4.2.3 | Cl 29.2 | A3/01-02 | 6.07.04 | Internal Fitout & Finishes | Lot | LS | 1 |  | 0 |  | Milestone | 50% supply, 50% install
A | 6 | 07 | A607 | 18 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE BUILDING | WORKS | FFE Package |  | A6.07.18 | SOW 4.6 | Cl 29.2 | A3 Furniture | 6.07.05 | FFE Package | Lot | LS | 1 |  | 0 |  | Per item delivered | 90% supply, 10% install
A | 0 | 13 | A013 | 36 | 0 | 00 | 00 | 3 | Section A - Lump Sum | WAREHOUSE (Bldg 103) | EXTERNAL WORKS |  |  | A0.13 |  |  |  |  | EXTERNAL WORKS |  |  |  |  | 0
A | 0 | 13 | A013 | 36 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE (Bldg 103) | EXTERNAL WORKS | Warehouse Parking Area |  | A0.13.36 | SOW 9.5 | Cl 29.2 | A0/01-02, A3/01 | 0.13.17 | Warehouse Parking Area | m² | LS |  |  | 0 |  | Per m² complete | Subbase + paving complete
A | 0 | 13 | A013 | 37 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE (Bldg 103) | EXTERNAL WORKS | Loading Dock Aprons |  | A0.13.37 | SOW 9.5 | Cl 29.2 | A0/01-02, A3/01 | 0.13.18 | Loading Dock Aprons | m² | LS |  |  | 0 |  | Per m² complete | Concrete poured and finished
A | 0 | 13 | A013 | 38 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE (Bldg 103) | EXTERNAL WORKS | Warehouse Footpaths & Access |  | A0.13.38 | SOW 9.5.1 | Cl 29.2 | A0/01-02, A3/01 | 0.13.19 | Warehouse Footpaths & Access | m² | LS |  |  | 0 |  | Per m² complete | Formwork, concrete, finish
A | 0 | 13 | A013 | 39 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE (Bldg 103) | EXTERNAL WORKS | Warehouse Security Fencing |  | A0.13.39 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 0.13.20 | Warehouse Security Fencing | Lm | LS |  |  | 0 |  | Per Lm installed | Posts, rails, mesh complete
A | 0 | 13 | A013 | 40 | 1 | 01 | 00 | 4 | Section A - Lump Sum | WAREHOUSE (Bldg 103) | EXTERNAL WORKS | Warehouse Gates |  | A0.13.40 | SOW 9.5.2 | Cl 29.2 | A0/01-02 | 0.13.21 | Warehouse Gates | No. | LS |  |  | 0 |  | Per gate installed | Gate supplied, installed, operational
A | 7 | 0 | A70 | 08 | 0 | 00 | 00 | 2 | Section A - Lump Sum | TRAVEL & ACCOMMODATION |  |  |  | A7 |  |  |  |  | TRAVEL & ACCOMMODATION |  |  |  |  | 0
A | 7 | 01 | A701 | 49 | 0 | 00 | 00 | 3 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | TRAVEL ALLOWANCES |  |  | A7.01 |  |  |  |  | TRAVEL ALLOWANCES |  |  |  |  | 0
A | 7 | 01 | A701 | 49 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | TRAVEL ALLOWANCES | Vehicle Allowance (Site Vehicle) |  | A7.01.49 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.01.01 | Vehicle Allowance (Site Vehicle) | Week | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 01 | A701 | 50 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | TRAVEL ALLOWANCES | Flights Allowance (Key Personnel) |  | A7.01.50 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.01.02 | Flights Allowance (Key Personnel) | Trip | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 01 | A701 | 51 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | TRAVEL ALLOWANCES | Mileage / Fuel Reimbursement |  | A7.01.51 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.01.03 | Mileage / Fuel Reimbursement | Lot | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 02 | A702 | 27 | 0 | 00 | 00 | 3 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | ACCOMMODATION |  |  | A7.02 |  |  |  |  | ACCOMMODATION |  |  |  |  | 0
A | 7 | 02 | A702 | 27 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | ACCOMMODATION | Management Personnel Accommodation |  | A7.02.27 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.02.01 | Management Personnel Accommodation | Night | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 02 | A702 | 28 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | ACCOMMODATION | Supervision Personnel Accommodation |  | A7.02.28 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.02.02 | Supervision Personnel Accommodation | Night | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 02 | A702 | 29 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | ACCOMMODATION | Workforce Accommodation Allowance |  | A7.02.29 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.02.03 | Workforce Accommodation Allowance | Night | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 03 | A703 | 22 | 0 | 00 | 00 | 3 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | MEALS & INCIDENTALS |  |  | A7.03 |  |  |  |  | MEALS & INCIDENTALS |  |  |  |  | 0
A | 7 | 03 | A703 | 22 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | MEALS & INCIDENTALS | Meals Allowance (Per Diem) |  | A7.03.22 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.03.01 | Meals Allowance (Per Diem) | Day | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 03 | A703 | 23 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | MEALS & INCIDENTALS | Incidental Expenses Allowance |  | A7.03.23 | SOW 7.2.2, 11.0 | Cl 22, 23 |  | 7.03.02 | Incidental Expenses Allowance | Lot | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 04 | A704 | 26 | 0 | 00 | 00 | 3 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | REMOTE AREA ALLOWANCES |  |  | A7.04 |  |  |  |  | REMOTE AREA ALLOWANCES |  |  |  |  | 0
A | 7 | 04 | A704 | 26 | 1 | 01 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | REMOTE AREA ALLOWANCES | Site Disability / Remote Area Allowance |  | A7.04.26 | SOW 11.0 | Cl 22, 23 |  | 7.04.01 | Site Disability / Remote Area Allowance | Day | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
A | 7 | 04 | A704 | 27 | 1 | 02 | 00 | 4 | Section A - Lump Sum | TRAVEL & ACCOMMODATION | REMOTE AREA ALLOWANCES | Living Away from Home Allowance (LAFHA) |  | A7.04.27 | SOW 11.0 | Cl 22, 23 |  | 7.04.02 | Living Away from Home Allowance (LAFHA) | Week | LS |  |  | 0 |  | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
P | 0 | 0 | P00 | 09 | 0 | 00 | 00 | 1 | Section B - Provisional Sum |  |  |  |  | P |  |  |  |  | Section B - Provisional Sum |  |  |  |  | 0
P | 1 | 0 | P10 | 09 | 0 | 00 | 00 | 2 | Section B - Provisional Sum | PROVISIONAL SUMS |  |  |  | P1 |  |  |  |  | PROVISIONAL SUMS |  |  |  |  | 0
P | 1 | 01 | P101 | 53 | 0 | 00 | 00 | 3 | Section B - Provisional Sum | PROVISIONAL SUMS | SITE CONDITIONS |  |  | P1.01 |  |  |  |  | SITE CONDITIONS |  |  |  |  | 0
P | 1 | 01 | P101 | 53 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | SITE CONDITIONS | Latent Conditions Allowance |  | P1.01.53 | SOW 2.1 | Cl 25.2 |  | 1.01.01 | Latent Conditions Allowance | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 01 | P101 | 54 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | SITE CONDITIONS | Rock Excavation Allowance |  | P1.01.54 | SOW 2.1 | Cl 25.2 |  | 1.01.02 | Rock Excavation Allowance | m³ | PS |  |  | 0 |  | Per m³ rock | Per approved Variation
P | 1 | 01 | P101 | 55 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | SITE CONDITIONS | Contaminated Soil Allowance |  | P1.01.55 | SOW 2.1 | Cl 25.2 |  | 1.01.03 | Contaminated Soil Allowance | m³ | PS |  |  | 0 |  | Per m³ disposed | Per approved Variation
P | 1 | 02 | P102 | 31 | 0 | 00 | 00 | 3 | Section B - Provisional Sum | PROVISIONAL SUMS | HAZMAT |  |  | P1.02 |  |  |  |  | HAZMAT |  |  |  |  | 0
P | 1 | 02 | P102 | 31 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | HAZMAT | Additional Asbestos Removal |  | P1.02.31 | SOW 4.1.2 | Cl 25.2, WHS |  | 1.02.01 | Additional Asbestos Removal | m² | PS |  |  | 0 |  | Per m² removed | Per approved Variation
P | 1 | 02 | P102 | 32 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | HAZMAT | Lead Paint Removal |  | P1.02.32 | SOW 4.1.2 | Cl 25.2, WHS |  | 1.02.02 | Lead Paint Removal | m² | PS |  |  | 0 |  | Per m² removed | Per approved Variation
P | 1 | 02 | P102 | 33 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | HAZMAT | Synthetic Mineral Fibre Removal |  | P1.02.33 | SOW 4.1.2 | Cl 25.2, WHS |  | 1.02.03 | Synthetic Mineral Fibre Removal | m² | PS |  |  | 0 |  | Per m² removed | Per approved Variation
P | 1 | 04 | P104 | 29 | 0 | 00 | 00 | 3 | Section B - Provisional Sum | PROVISIONAL SUMS | SERVICES |  |  | P1.04 |  |  |  |  | SERVICES |  |  |  |  | 0
P | 1 | 04 | P104 | 29 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | SERVICES | Electrical Services Diversion |  | P1.04.29 | SOW 3.3 | Cl 25.2 |  | 1.04.01 | Electrical Services Diversion | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 04 | P104 | 30 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | SERVICES | Hydraulic Services Diversion |  | P1.04.30 | SOW 3.3 | Cl 25.2 |  | 1.04.02 | Hydraulic Services Diversion | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 04 | P104 | 31 | 1 | 02 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | SERVICES | Communications/Data Diversion |  | P1.04.31 | SOW 3.3 | Cl 25.2 |  | 1.04.03 | Communications/Data Diversion | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 04 | P104 | 32 | 0 | 01 | 00 | 3 | Section B - Provisional Sum | PROVISIONAL SUMS | DESIGN |  |  | P1.04 |  |  |  |  | DESIGN |  |  |  |  | 0
P | 1 | 04 | P104 | 33 | 1 | 02 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | DESIGN | Architectural Design Development |  | P1.04.33 | SOW 5.0 | Cl 25.2, 7A |  | 1.04.05 | Architectural Design Development | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 04 | P104 | 34 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | DESIGN | Structural Design Development |  | P1.04.34 | SOW 5.0 | Cl 25.2, 7A |  | 1.04.06 | Structural Design Development | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 04 | P104 | 35 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | DESIGN | Services Design Development |  | P1.04.35 | SOW 5.0 | Cl 25.2, 7A |  | 1.04.07 | Services Design Development | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 05 | P105 | 31 | 0 | 02 | 00 | 3 | Section B - Provisional Sum | PROVISIONAL SUMS | CONTINGENCY |  |  | P1.05 |  |  |  |  | CONTINGENCY |  |  |  |  | 0
P | 1 | 05 | P105 | 31 | 1 | 03 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | CONTINGENCY | General Contingency Allowance |  | P1.05.31 | SOW 3.0 | Cl 25.2 |  | 1.05.01 | General Contingency Allowance | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 05 | P105 | 32 | 1 | 02 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | CONTINGENCY | Interface Coordination Allowance |  | P1.05.32 | SOW 3.4 | Cl 25.2 |  | 1.05.02 | Interface Coordination Allowance | Lot | PS | 1 |  | 0 |  | As directed | Per approved Variation
P | 1 | 05 | P105 | 33 | 1 | 03 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | CONTINGENCY | Inclement Weather Allowance |  | P1.05.33 | SOW 2.2 | Cl 25.2, 34.8 |  | 1.05.03 | Inclement Weather Allowance | Days | PS |  |  | 0 |  | Per qualifying day | Per approved Variation
P | 1 | 06 | P106 | 12 | 0 | 00 | 00 | 3 | Section B - Provisional Sum | PROVISIONAL SUMS | AV WORKS |  |  | P1.06 |  |  |  |  | AV WORKS |  |  |  |  | 0
P | 1 | 06 | P106 | 12 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | AV WORKS | AV Contractor Attendance |  | P1.06.12 | SOW 3.4.2 | Cl 25.2 |  | 1.06.01 | AV Contractor Attendance | Weeks | PS |  |  | 0 |  | Per week attendance | Per approved Variation
P | 1 | 06 | P106 | 13 | 1 | 01 | 00 | 4 | Section B - Provisional Sum | PROVISIONAL SUMS | AV WORKS | AV Power & Data Points |  | P1.06.13 | SOW 3.4.2 | Cl 25.2 |  | 1.06.02 | AV Power & Data Points | No. | PS |  |  | 0 |  | Per point installed | Per approved Variation
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Variation Table
RFT # [To be added] SPS Annex
VariationTable Template
|  |  | Revision: | A
Cost Type | Category | Sub-Category | Item No. | Description | UOM | Pricing Type | Normal Rate | OT 1.5x | OT 2.0x | OT 2.5x | Allowances | Mob Rate | Demob Rate | Dry Hire | Wet Hire | Supply Rate | Install Rate | All-in Rate | Method of Measure | Rule of Credit | Min Charge | Increment | Valid From | Valid To | Notes
VARIATION | PERSONNEL DAYWORK RATES |  | V1 | PERSONNEL DAYWORK RATES
VARIATION | PERSONNEL DAYWORK RATES | Management | V1.01 | MANAGEMENT PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Management | V1.01.01 | Project Director | Day | SOR | [12 empty] | Per 8-hr day on site/office | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Management | V1.01.02 | Project Manager | Day | SOR | [12 empty] | Per 8-hr day on site/office | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Management | V1.01.03 | Site Manager / Superintendent | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Management | V1.01.04 | Construction Manager | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Management | V1.01.05 | Assistant Site Manager | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Engineering | V1.02 | ENGINEERING PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Engineering | V1.02.01 | Project Engineer | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Engineering | V1.02.02 | Senior Engineer | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Engineering | V1.02.03 | Graduate Engineer | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Engineering | V1.02.04 | Design Engineer | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Engineering | V1.02.05 | Services Engineer (M/E/H) | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Supervision | V1.03 | SUPERVISION PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Supervision | V1.03.01 | Site Foreman / Supervisor | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Supervision | V1.03.02 | Leading Hand | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Supervision | V1.03.03 | Works Coordinator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Supervision | V1.03.04 | Night Shift Supervisor | Day | SOR | [12 empty] | Per 10-hr night shift | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Supervision | V1.03.05 | Subcontractor Coordinator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | HSE | V1.04 | HSE PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | HSE | V1.04.01 | HSE Manager | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | HSE | V1.04.02 | WHS Advisor / Safety Officer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | HSE | V1.04.03 | Traffic Controller | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | HSE | V1.04.04 | First Aid Officer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | HSE | V1.04.05 | Environmental Officer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Quality | V1.05 | QUALITY PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Quality | V1.05.01 | Quality Manager | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Quality | V1.05.02 | Quality Coordinator | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Quality | V1.05.03 | Quality Inspector | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Administration | V1.06 | ADMINISTRATION PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Administration | V1.06.01 | Document Controller | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Administration | V1.06.02 | Contract Administrator | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Administration | V1.06.03 | Cost Controller / Estimator | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Administration | V1.06.04 | Scheduler / Planner | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Administration | V1.06.05 | Project Administrator | Day | SOR | [12 empty] | Per 8-hr day | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07 | TRADE PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.01 | Skilled Tradesperson (General) | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.02 | Electrician - A Grade | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.03 | Electrician - Apprentice | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.04 | Plumber / Drainer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.05 | Carpenter / Joiner | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.06 | Steel Fixer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.07 | Concreter | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.08 | Welder / Boilermaker | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.09 | Painter | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.10 | Tiler | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.11 | Plasterer / Renderer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.12 | Glazier | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.13 | Roofer / Metal Worker | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.14 | HVAC Mechanic / Fitter | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Trades | V1.07.15 | Fire Services Technician | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Labour | V1.08 | LABOUR PERSONNEL
VARIATION | PERSONNEL DAYWORK RATES | Labour | V1.08.01 | General Labourer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Labour | V1.08.02 | Skilled Labourer | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Labour | V1.08.03 | Rigger / Dogman | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Labour | V1.08.04 | Scaffolder | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Labour | V1.08.05 | Cleaner | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PERSONNEL DAYWORK RATES | Plant Operator | V1.09 | PLANT OPERATORS
VARIATION | PERSONNEL DAYWORK RATES | Plant Operator | V1.09.01 | Excavator Operator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. tickets
VARIATION | PERSONNEL DAYWORK RATES | Plant Operator | V1.09.02 | Crane Operator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. tickets
VARIATION | PERSONNEL DAYWORK RATES | Plant Operator | V1.09.03 | EWP Operator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. tickets
VARIATION | PERSONNEL DAYWORK RATES | Plant Operator | V1.09.04 | Forklift Operator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. tickets
VARIATION | PERSONNEL DAYWORK RATES | Plant Operator | V1.09.05 | Telehandler Operator | Day | SOR | [12 empty] | Per 8-hr day on site | Timesheet signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. tickets
VARIATION | PLANT & EQUIPMENT RATES |  | V2 | PLANT & EQUIPMENT RATES
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01 | EARTHMOVING EQUIPMENT
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.01 | Backhoe Loader | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.02 | Excavator - Mini (up to 5T) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.03 | Excavator - Medium (5-15T) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.04 | Excavator - Large (15T+) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.05 | Wheel Loader (up to 5T) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.06 | Wheel Loader (5T+) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.07 | Grader | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.08 | Bulldozer (up to D6) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.09 | Trencher | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Earthmoving | V2.01.10 | Skid Steer Loader | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Compaction | V2.02 | COMPACTION EQUIPMENT
VARIATION | PLANT & EQUIPMENT RATES | Compaction | V2.02.01 | Plate Compactor (Hand) | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Compaction | V2.02.02 | Rammer / Jumping Jack | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Compaction | V2.02.03 | Vibrating Roller - Walk Behind | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Compaction | V2.02.04 | Vibrating Roller - Ride-on (up to 5T) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Compaction | V2.02.05 | Vibrating Roller - Ride-on (5T+) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03 | LIFTING EQUIPMENT
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.01 | Mobile Crane - Franna (up to 20T) | Hour | SOR | [12 empty] | Per operating hour | Crane log signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. rigging gear
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.02 | Mobile Crane - All Terrain (25-50T) | Hour | SOR | [12 empty] | Per operating hour | Crane log signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. rigging gear
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.03 | Mobile Crane - All Terrain (50T+) | Hour | SOR | [12 empty] | Per operating hour | Crane log signed by Supt, min 4hrs | 4 hrs | 1 hr |  |  | Incl. rigging gear
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.04 | Forklift - 2.5T | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.05 | Forklift - 5T | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.06 | Telehandler (up to 4T) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Lifting | V2.03.07 | Telehandler (4T+) | Hour | SOR | [12 empty] | Per operating hour | Plant log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04 | ACCESS EQUIPMENT
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.01 | Scissor Lift - Electric (up to 6m) | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.02 | Scissor Lift - Rough Terrain (8-12m) | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.03 | Boom Lift - Articulating (up to 15m) | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.04 | Boom Lift - Straight (15m+) | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.05 | Scaffolding - Standard (per m²) | m²/wk | SOR | [12 empty] | Per m² per week | Scaffold register updated | 1 wk | 1 wk |  |  | Incl. erect/dismantle
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.06 | Mobile Scaffold Tower | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Access | V2.04.07 | Ladder - Extension (per unit) | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Concrete | V2.05 | CONCRETE EQUIPMENT
VARIATION | PLANT & EQUIPMENT RATES | Concrete | V2.05.01 | Concrete Pump - Line Pump | Hour | SOR | [12 empty] | Per operating hour | Pump dockets signed by Supt | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Concrete | V2.05.02 | Concrete Pump - Boom Pump | Hour | SOR | [12 empty] | Per operating hour | Pump dockets signed by Supt | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Concrete | V2.05.03 | Concrete Mixer - 2.5m³ | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Concrete | V2.05.04 | Power Trowel | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Concrete | V2.05.05 | Concrete Vibrator - Poker | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Vehicles | V2.06 | VEHICLES & TRANSPORT
VARIATION | PLANT & EQUIPMENT RATES | Vehicles | V2.06.01 | Utility Vehicle (Ute) | Day | SOR | [12 empty] | Per calendar day | Vehicle log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Vehicles | V2.06.02 | Light Commercial Vehicle | Day | SOR | [12 empty] | Per calendar day | Vehicle log signed by Supt | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Vehicles | V2.06.03 | Truck - Rigid (up to 8T) | Hour | SOR | [12 empty] | Per operating hour | Vehicle log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Vehicles | V2.06.04 | Truck - Tipper (10T+) | Hour | SOR | [12 empty] | Per operating hour | Vehicle log signed by Supt, min 4hrs | 4 hrs | 1 hr
VARIATION | PLANT & EQUIPMENT RATES | Vehicles | V2.06.05 | Semi-Trailer | Load | SOR | [12 empty] | Per load delivered | Delivery docket signed by Supt | 1 load | 1 load
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07 | POWER TOOLS & HAND EQUIPMENT
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.01 | Rotary Hammer Drill | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.02 | Demolition Breaker - Electric | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.03 | Angle Grinder (230mm) | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.04 | Circular Saw | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.05 | Reciprocating Saw | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.06 | Welding Machine - MIG | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.07 | Welding Machine - Stick/Arc | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Tools | V2.07.08 | Air Compressor - Portable | Day | SOR | [12 empty] | Per calendar day | Tool register updated | 1 day | 1 day
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08 | GENERATORS & TEMPORARY POWER
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08.01 | Generator - 10kVA | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day |  |  | Excl. fuel
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08.02 | Generator - 25kVA | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day |  |  | Excl. fuel
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08.03 | Generator - 50kVA | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day |  |  | Excl. fuel
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08.04 | Generator - 100kVA+ | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day |  |  | Excl. fuel
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08.05 | Distribution Board - Temp | Wk | SOR | [12 empty] | Per week on site | Weekly site inspection | 1 wk | 1 wk
VARIATION | PLANT & EQUIPMENT RATES | Power Supply | V2.08.06 | Site Lighting - Tower | Day | SOR | [12 empty] | Per calendar day | Equipment daily log signed by Supt | 1 day | 1 day
VARIATION | MATERIALS RATES |  | V3 | MATERIALS RATES (COMMON ITEMS)
VARIATION | MATERIALS RATES | Concrete | V3.01 | CONCRETE & AGGREGATES
VARIATION | MATERIALS RATES | Concrete | V3.01.01 | Ready-Mix Concrete N20 | m³ | SOR | [12 empty] | Per m³ delivered to site | Delivery docket, slump test | 1 m³ | 0.5 m³
VARIATION | MATERIALS RATES | Concrete | V3.01.02 | Ready-Mix Concrete N25 | m³ | SOR | [12 empty] | Per m³ delivered to site | Delivery docket, slump test | 1 m³ | 0.5 m³
VARIATION | MATERIALS RATES | Concrete | V3.01.03 | Ready-Mix Concrete N32 | m³ | SOR | [12 empty] | Per m³ delivered to site | Delivery docket, slump test | 1 m³ | 0.5 m³
VARIATION | MATERIALS RATES | Concrete | V3.01.04 | Ready-Mix Concrete N40 | m³ | SOR | [12 empty] | Per m³ delivered to site | Delivery docket, slump test | 1 m³ | 0.5 m³
VARIATION | MATERIALS RATES | Concrete | V3.01.05 | Grout - Non-Shrink Cementitious | kg | SOR | [12 empty] | Per kg supplied | Delivery docket | 25 kg | 1 kg
VARIATION | MATERIALS RATES | Concrete | V3.01.06 | Aggregate - Road Base | Tonne | SOR | [12 empty] | Per tonne delivered | Delivery docket | 1 T | 0.5 T
VARIATION | MATERIALS RATES | Concrete | V3.01.07 | Sand - Bedding / Fill | Tonne | SOR | [12 empty] | Per tonne delivered | Delivery docket | 1 T | 0.5 T
VARIATION | MATERIALS RATES | Steel | V3.02 | STEEL & REINFORCEMENT
VARIATION | MATERIALS RATES | Steel | V3.02.01 | Reinforcement Bar - N12 | Tonne | SOR | [12 empty] | Per tonne supplied | Mill cert, delivery docket | 0.5 T | 0.1 T
VARIATION | MATERIALS RATES | Steel | V3.02.02 | Reinforcement Bar - N16 | Tonne | SOR | [12 empty] | Per tonne supplied | Mill cert, delivery docket | 0.5 T | 0.1 T
VARIATION | MATERIALS RATES | Steel | V3.02.03 | Reinforcement Bar - N20 | Tonne | SOR | [12 empty] | Per tonne supplied | Mill cert, delivery docket | 0.5 T | 0.1 T
VARIATION | MATERIALS RATES | Steel | V3.02.04 | Reinforcement Mesh - SL82 | m² | SOR | [12 empty] | Per m² supplied | Mill cert, delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Steel | V3.02.05 | Structural Steel - Hot Rolled | Tonne | SOR | [12 empty] | Per tonne supplied | Mill cert, delivery docket | 0.5 T | 0.1 T
VARIATION | MATERIALS RATES | Steel | V3.02.06 | Structural Steel - SHS/RHS | Tonne | SOR | [12 empty] | Per tonne supplied | Mill cert, delivery docket | 0.5 T | 0.1 T
VARIATION | MATERIALS RATES | Steel | V3.02.07 | Metal Decking - Bondek/equiv | m² | SOR | [12 empty] | Per m² supplied | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Masonry | V3.03 | MASONRY & BLOCKWORK
VARIATION | MATERIALS RATES | Masonry | V3.03.01 | Concrete Block - 190mm Standard | Each | SOR | [12 empty] | Per block supplied | Delivery docket | 100 units | 10 units
VARIATION | MATERIALS RATES | Masonry | V3.03.02 | Concrete Block - 290mm Core-Fill | Each | SOR | [12 empty] | Per block supplied | Delivery docket | 100 units | 10 units
VARIATION | MATERIALS RATES | Masonry | V3.03.03 | Fire-Rated Block - FRL 120/120/120 | Each | SOR | [12 empty] | Per block supplied | Delivery docket, fire cert | 100 units | 10 units
VARIATION | MATERIALS RATES | Masonry | V3.03.04 | Mortar - Pre-mixed M3 | m³ | SOR | [12 empty] | Per m³ supplied | Delivery docket | 0.5 m³ | 0.1 m³
VARIATION | MATERIALS RATES | Timber | V3.04 | TIMBER & FRAMING
VARIATION | MATERIALS RATES | Timber | V3.04.01 | Framing Timber - 90x45 Treated | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 50 Lm | 1 Lm
VARIATION | MATERIALS RATES | Timber | V3.04.02 | Framing Timber - 90x35 Treated | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 50 Lm | 1 Lm
VARIATION | MATERIALS RATES | Timber | V3.04.03 | LVL Beam (per m³) | m³ | SOR | [12 empty] | Per m³ | Delivery docket | 0.5 m³ | 0.1 m³
VARIATION | MATERIALS RATES | Timber | V3.04.04 | Plywood - Structural 17mm | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05 | LININGS & INSULATION
VARIATION | MATERIALS RATES | Linings | V3.05.01 | Plasterboard - 10mm Standard | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05.02 | Plasterboard - 13mm Fire-Rated | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05.03 | Plasterboard - 16mm Acoustic | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05.04 | Fibre Cement Sheet - 6mm External | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05.05 | Insulation - Glasswool R2.5 Batts | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05.06 | Insulation - Glasswool R4.0 Batts | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Linings | V3.05.07 | Duct Insulation - 25mm Foil Faced | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Finishes | V3.06 | FLOOR & WALL FINISHES
VARIATION | MATERIALS RATES | Finishes | V3.06.01 | Carpet Tile - Commercial | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Finishes | V3.06.02 | Vinyl Sheet - 2mm Commercial | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Finishes | V3.06.03 | Ceramic Tile - Floor 300x300 | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Finishes | V3.06.04 | Ceramic Tile - Wall 200x200 | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Finishes | V3.06.05 | Paint - Interior Acrylic (per L) | Litre | SOR | [12 empty] | Per litre | Delivery docket | 10 L | 1 L
VARIATION | MATERIALS RATES | Finishes | V3.06.06 | Paint - Exterior Acrylic (per L) | Litre | SOR | [12 empty] | Per litre | Delivery docket | 10 L | 1 L
VARIATION | MATERIALS RATES | Roofing | V3.07 | ROOFING & CLADDING
VARIATION | MATERIALS RATES | Roofing | V3.07.01 | Metal Roofing - Colorbond Custom Orb | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Roofing | V3.07.02 | Metal Roofing - Klip-Lok | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Roofing | V3.07.03 | Wall Cladding - Colorbond | m² | SOR | [12 empty] | Per m² | Delivery docket | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Roofing | V3.07.04 | Gutter - Quad 115mm Colorbond | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Roofing | V3.07.05 | Downpipe - 100mm Round Colorbond | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Roofing | V3.07.06 | Roof Sarking - Sisalation | m² | SOR | [12 empty] | Per m² | Delivery docket | 50 m² | 1 m²
VARIATION | MATERIALS RATES | Mechanical | V3.08 | MECHANICAL MATERIALS
VARIATION | MATERIALS RATES | Mechanical | V3.08.01 | Ductwork - Galvanised Sheet | kg | SOR | [12 empty] | Per kg fabricated | Workshop cert, delivery docket | 50 kg | 1 kg
VARIATION | MATERIALS RATES | Mechanical | V3.08.02 | Flexible Duct - Insulated 150dia | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Mechanical | V3.08.03 | Copper Pipe - 15mm Type B | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Mechanical | V3.08.04 | Refrigerant Pipe Set (pair) | Lm | SOR | [12 empty] | Per lineal metre pair | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Mechanical | V3.08.05 | Diffuser - 4-Way 300x300 | Each | SOR | [12 empty] | Per unit | Delivery docket | 1 unit | 1 unit
VARIATION | MATERIALS RATES | Mechanical | V3.08.06 | VAV Box - Complete (specify size) | Each | SOR | [12 empty] | Per unit | Delivery docket, data sheet | 1 unit | 1 unit
VARIATION | MATERIALS RATES | Electrical | V3.09 | ELECTRICAL MATERIALS
VARIATION | MATERIALS RATES | Electrical | V3.09.01 | Cable - 2.5mm² TPS | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 100 Lm | 1 Lm
VARIATION | MATERIALS RATES | Electrical | V3.09.02 | Cable - 4mm² TPS | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 100 Lm | 1 Lm
VARIATION | MATERIALS RATES | Electrical | V3.09.03 | Cable - 16mm² 4C+E Armoured | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 50 Lm | 1 Lm
VARIATION | MATERIALS RATES | Electrical | V3.09.04 | Cable Tray - 300W Perforated | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Electrical | V3.09.05 | Conduit - 25mm Heavy Duty PVC | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 50 Lm | 1 Lm
VARIATION | MATERIALS RATES | Electrical | V3.09.06 | LED Panel Light - 600x600 | Each | SOR | [12 empty] | Per unit | Delivery docket, data sheet | 1 unit | 1 unit
VARIATION | MATERIALS RATES | Electrical | V3.09.07 | GPO - Double 10A | Each | SOR | [12 empty] | Per unit | Delivery docket | 10 units | 1 unit
VARIATION | MATERIALS RATES | Electrical | V3.09.08 | Data Outlet - Cat6A | Each | SOR | [12 empty] | Per unit | Delivery docket | 10 units | 1 unit
VARIATION | MATERIALS RATES | Hydraulic | V3.10 | HYDRAULIC & FIRE MATERIALS
VARIATION | MATERIALS RATES | Hydraulic | V3.10.01 | PVC Pipe - 100mm DWV | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Hydraulic | V3.10.02 | HDPE Pipe - 100mm Stormwater | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Hydraulic | V3.10.03 | Copper Pipe - 20mm Type B | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Hydraulic | V3.10.04 | Pex Pipe - 16mm Hot/Cold | Lm | SOR | [12 empty] | Per lineal metre | Delivery docket | 50 Lm | 1 Lm
VARIATION | MATERIALS RATES | Hydraulic | V3.10.05 | Floor Waste - 100mm SS Grate | Each | SOR | [12 empty] | Per unit | Delivery docket | 1 unit | 1 unit
VARIATION | MATERIALS RATES | Hydraulic | V3.10.06 | Fire Sprinkler Head - Pendant | Each | SOR | [12 empty] | Per unit | Delivery docket, cert | 10 units | 1 unit
VARIATION | MATERIALS RATES | Hydraulic | V3.10.07 | Fire Hose Reel - Complete | Each | SOR | [12 empty] | Per unit | Delivery docket, cert | 1 unit | 1 unit
VARIATION | MATERIALS RATES | Hydraulic | V3.10.08 | Fire Extinguisher - 4.5kg ABE | Each | SOR | [12 empty] | Per unit | Delivery docket, cert | 1 unit | 1 unit
VARIATION | OVERHEAD, PROFIT & MARGIN |  | V4 | OVERHEAD, PROFIT & MARGIN RATES
VARIATION | OVERHEAD, PROFIT & MARGIN | Overhead | V4.01 | OVERHEAD ALLOWANCES
VARIATION | OVERHEAD, PROFIT & MARGIN | Overhead | V4.01.01 | Site Overhead - Per Week | Week | SOR | [12 empty] | Per calendar week | Weekly variation register | 1 wk | 1 wk |  |  | Office, amenities, services
VARIATION | OVERHEAD, PROFIT & MARGIN | Overhead | V4.01.02 | Head Office Overhead (%) | % | SOR | [12 empty] | % of variation direct cost | Applied to variation total | N/A | N/A |  |  | Typically 5-8%
VARIATION | OVERHEAD, PROFIT & MARGIN | Overhead | V4.01.03 | Insurance & Bonds (%) | % | SOR | [12 empty] | % of variation value | Applied to variation total | N/A | N/A |  |  | Per contract terms
VARIATION | OVERHEAD, PROFIT & MARGIN | Margin | V4.02 | MARGIN & PROFIT
VARIATION | OVERHEAD, PROFIT & MARGIN | Margin | V4.02.01 | Margin on Labour (%) | % | SOR | [12 empty] | % of labour costs | Applied to daywork labour | N/A | N/A
VARIATION | OVERHEAD, PROFIT & MARGIN | Margin | V4.02.02 | Margin on Plant (%) | % | SOR | [12 empty] | % of plant costs | Applied to plant hire | N/A | N/A
VARIATION | OVERHEAD, PROFIT & MARGIN | Margin | V4.02.03 | Margin on Materials (%) | % | SOR | [12 empty] | % of material costs | Applied to materials | N/A | N/A
VARIATION | OVERHEAD, PROFIT & MARGIN | Margin | V4.02.04 | Margin on Subcontractors (%) | % | SOR | [12 empty] | % of subcontract costs | Applied to subcontract work | N/A | N/A
VARIATION | OVERHEAD, PROFIT & MARGIN | Time-Related | V4.03 | TIME-RELATED COSTS
VARIATION | OVERHEAD, PROFIT & MARGIN | Time-Related | V4.03.01 | Delay Costs - Per Week | Week | SOR | [12 empty] | Per calendar week delay | EOT claim approved by Supt | 1 wk | 1 day |  |  | Prelims extension
VARIATION | OVERHEAD, PROFIT & MARGIN | Time-Related | V4.03.02 | Acceleration Premium (%) | % | SOR | [12 empty] | % premium on accelerated work | Acceleration direction issued | N/A | N/A |  |  | As agreed per direction
VARIATION | OVERHEAD, PROFIT & MARGIN | Time-Related | V4.03.03 | Standby / Waiting Time - Labour | Hour | SOR | [12 empty] | Per hour standby | Standby record signed by Supt | 1 hr | 0.5 hr |  |  | 50% of normal rate
VARIATION | OVERHEAD, PROFIT & MARGIN | Time-Related | V4.03.04 | Standby / Waiting Time - Plant | Hour | SOR | [12 empty] | Per hour standby | Standby record signed by Supt | 1 hr | 0.5 hr |  |  | 50% of dry hire rate
VARIATION | MATERIALS RATES | Civil/External | V3.11 | CIVIL & EXTERNAL WORKS MATERIALS
VARIATION | MATERIALS RATES | Civil/External | V3.11.01 | Asphalt Paving (per m²) | m² | SOR | [12 empty] | Per m² laid | Delivery docket + install | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.02 | Concrete Paving - Plain | m² | SOR | [12 empty] | Per m² poured | Delivery docket + pour | 5 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.03 | Concrete Paving - Coloured | m² | SOR | [12 empty] | Per m² poured | Delivery docket + pour | 5 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.04 | Interlocking Pavers - Standard | m² | SOR | [12 empty] | Per m² laid | Supply + install complete | 5 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.05 | Interlocking Pavers - Premium | m² | SOR | [12 empty] | Per m² laid | Supply + install complete | 5 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.06 | Kerb & Channel - Concrete | Lm | SOR | [12 empty] | Per lineal metre | Supply + install complete | 5 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.07 | Concrete Edging | Lm | SOR | [12 empty] | Per lineal metre | Supply + install complete | 5 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.08 | Chain Wire Fence - 1.8m | Lm | SOR | [12 empty] | Per lineal metre | Supply + install complete | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.09 | Chain Wire Fence - 2.4m Security | Lm | SOR | [12 empty] | Per lineal metre | Supply + install complete | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.10 | Steel Tubular Fence - PC | Lm | SOR | [12 empty] | Per lineal metre | Supply + install complete | 5 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.11 | Swing Gate - Single Pedestrian | No. | SOR | [12 empty] | Per gate | Supply + install complete | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.12 | Swing Gate - Double Vehicle | No. | SOR | [12 empty] | Per gate | Supply + install complete | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.13 | Sliding Gate - Motorised | No. | SOR | [12 empty] | Per gate | Supply + install + commission | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.14 | Decorative Gravel / Mulch | m² | SOR | [12 empty] | Per m² | Supply + spread complete | 10 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.15 | Garden Bed Edging - Steel | Lm | SOR | [12 empty] | Per lineal metre | Supply + install complete | 5 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.16 | Retaining Wall Block | m² | SOR | [12 empty] | Per m² face area | Supply + install complete | 5 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.17 | Turf - Supply & Lay | m² | SOR | [12 empty] | Per m² | Supply + lay complete | 20 m² | 1 m²
VARIATION | MATERIALS RATES | Civil/External | V3.11.18 | Topsoil - Imported | m³ | SOR | [12 empty] | Per m³ | Delivery docket + spread | 1 m³ | 0.5 m³
VARIATION | MATERIALS RATES | Civil/External | V3.11.19 | Shrubs - 200mm pot | No. | SOR | [12 empty] | Per plant | Supply + plant complete | 5 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.20 | Groundcover - 140mm pot | No. | SOR | [12 empty] | Per plant | Supply + plant complete | 10 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.21 | Feature Tree - 45L | No. | SOR | [12 empty] | Per tree | Supply + plant + stake | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.22 | Feature Tree - 100L | No. | SOR | [12 empty] | Per tree | Supply + plant + stake | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.23 | Irrigation - Pop-up Sprinkler | No. | SOR | [12 empty] | Per head | Supply + install + test | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.24 | Irrigation - Drip Line | Lm | SOR | [12 empty] | Per lineal metre | Supply + install + test | 10 Lm | 1 Lm
VARIATION | MATERIALS RATES | Civil/External | V3.11.25 | Irrigation Controller | No. | SOR | [12 empty] | Per controller | Supply + install + commission | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.26 | Wheel Stop - Concrete | No. | SOR | [12 empty] | Per wheel stop | Supply + fix complete | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.27 | Bollard - Steel Fixed | No. | SOR | [12 empty] | Per bollard | Supply + install complete | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.28 | Shade Structure - Cantilever | No. | SOR | [12 empty] | Per structure | Supply + install complete | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.29 | External Bench Seat | No. | SOR | [12 empty] | Per seat | Supply + install complete | 1 No. | 1 No.
VARIATION | MATERIALS RATES | Civil/External | V3.11.30 | Bike Rack - 5 Capacity | No. | SOR | [12 empty] | Per rack | Supply + install complete | 1 No. | 1 No.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## WBS
RFT # [To be added]
SPS Annex Refurbishment Project
WORK BREAKDOWN STRUCTURE (WBS)
WBS Code | L1 | L2 | L3 | L4 | L5 | Level | Cost Type | Category | WBS Description | SOW Ref | Contract Ref | Drawing Ref | Pay Table Item | Variation Item | Responsibility | Predecessor | Successor | Duration (Days) | Start Milestone | End Milestone | Deliverable | Method of Measure | Rule of Credit | Notes
1 | INDIRECT COSTS |  |  |  |  | 2 | INDIRECT | INDIRECT COSTS | INDIRECT COSTS |  |  |  | A1 |  | Cost
1.01 |  | PROJECT MANAGEMENT |  |  |  | 3 | INDIRECT | PROJECT MANAGEMENT | PROJECT MANAGEMENT |  |  |  | A1.01 |  | Contractor
1.01.01 |  |  | Project Manager |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Project Manager | SOW 7.0, 7.1 | Cl 22, 23 |  | A1.01.01 | V1.01 | PM |  |  |  | NTP | PC | Monthly Progress Reports, Meeting Minutes, Programme Updates | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.02 |  |  | Site Manager / Superintendent |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Site Manager / Superintendent | SOW 7.0, 7.1 | Cl 22, 23 |  | A1.01.02 | V1.01 | SM |  |  |  | NTP | PC | Daily Site Reports, Site Diaries, Resource Reports | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.03 |  |  | Project Engineer |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Project Engineer | SOW 7.0, 7.1 | Cl 22, 23 |  | A1.01.03 | V1.02 | PE |  |  |  | NTP | PC | RFIs, Technical Reports, Engineering Reviews, Design Coordination | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.04 |  |  | Site Foreman / Supervisor |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Site Foreman / Supervisor | SOW 7.0, 7.1 | Cl 22, 23 |  | A1.01.04 | V1.03 | Supervisor |  |  |  | NTP | PC | Daily Work Records, Labour Reports, Task Allocation Sheets | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.05 |  |  | WHS Advisor / Safety Officer |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | WHS Advisor / Safety Officer | SOW 7.0, 9.0 | Cl 12, 22, 23 |  | A1.01.05 | V1.04 | HSE |  |  |  | NTP | PC | Safety Reports, Toolbox Talks, Hazard Registers, Incident Reports | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.06 |  |  | Quality Manager / Coordinator |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Quality Manager / Coordinator | SOW 7.0, 10.0 | Cl 29, 22, 23 |  | A1.01.06 | V1.01 | QM |  |  |  | NTP | PC | Quality Reports, Audit Reports, NCR Register | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.07 |  |  | Document Controller |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Document Controller | SOW 7.0, 7.4 | Cl 8, 22, 23 |  | A1.01.07 |  | DC |  |  |  | NTP | PC | Document Register, Transmittals, Filing System, MDR Tracking | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.08 |  |  | Contract Administrator |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Contract Administrator | SOW 7.0 | Cl 22, 23, 37 |  | A1.01.08 |  | CA |  |  |  | NTP | PC | Contract Correspondence, Variation Registers, Payment Claims | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.09 |  |  | Cost Controller / Estimator |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Cost Controller / Estimator | SOW 7.0 | Cl 37, 22, 23 |  | A1.01.09 |  | Cost |  |  |  | NTP | PC | Cost Reports, Forecasts, Budget Tracking, EVM Reports | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.01.10 |  |  | Scheduler / Planner |  |  | 4 | INDIRECT | PROJECT MANAGEMENT | Scheduler / Planner | SOW 7.0, 7.3 | Cl 32, 22, 23 |  | A1.01.10 |  | Planner |  |  |  | NTP | PC | Programme Updates, Look-Ahead Schedules, Delay Analysis | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.02 |  | HSE |  |  |  | 3 | INDIRECT | HSE | HSE |  |  |  | A1.02 |  | HSE
1.02.01 |  |  | WHS Management System |  |  | 4 | INDIRECT | HSE | WHS Management System | SOW 9.1, 9.2 | Cl 12.3, 12.5 |  | A1.02.01 | V1.04 | HSE |  |  |  | NTP | PC | WHSMP, HSE Procedures Manual, Safety System Documentation | Milestone + Pro-rata | 25% WHSMP accepted, 75% Monthly pro-rata
1.02.02 |  |  | Permits and Controls |  |  | 4 | INDIRECT | HSE | Permits and Controls | SOW 9.3 | Cl 12.4 |  | A1.02.02 |  | Contractor |  |  |  | NTP | PC | Permit Register, Active Permits, Permit Closure Records | Pro-rata monthly | Pro-rata monthly, all permits maintained current
1.02.03 |  |  | Environmental Management |  |  | 4 | INDIRECT | HSE | Environmental Management | SOW 9.4 | Cl 12.3 |  | A1.02.03 |  | HSE |  |  |  | NTP | PC | CEMP, Environmental Monitoring Reports, Waste Records | Milestone + Pro-rata | 25% CEMP accepted, 75% Monthly pro-rata
1.02.04 |  |  | SWMS Development & Approvals |  |  | 4 | INDIRECT | HSE | SWMS Development & Approvals | SOW 9.2 | Cl 12.3 |  | A1.02.04 |  | Contractor |  |  |  | NTP | PC | Approved SWMS Register, Safe Work Method Statements | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1.02.05 |  |  | Site Inductions & Competency Verification |  |  | 4 | INDIRECT | HSE | Site Inductions & Competency Verification | SOW 9.2 | Cl 12.3, 12.4 |  | A1.02.05 |  | Contractor |  |  |  | NTP | PC | Induction Records, Competency Matrix, Training Register | Pro-rata monthly | Pro-rata monthly, records maintained
1.02.06 |  |  | Incident Management & Reporting |  |  | 4 | INDIRECT | HSE | Incident Management & Reporting | SOW 9.5 | Cl 12.9 |  | A1.02.06 |  | Contractor |  |  |  | NTP | PC | Incident Reports, Investigation Records, Corrective Actions | Pro-rata monthly | Pro-rata monthly, incident reports submitted within 24hrs
1.02.07 |  |  | Traffic Management Plan & Implementation |  |  | 4 | INDIRECT | HSE | Traffic Management Plan & Implementation | SOW 9.3, 3.4.5 | Cl 12.6 |  | A1.02.07 |  | Contractor |  |  |  | NTP | PC | TMP, Traffic Control Plans, VMS Schedules | Milestone + Pro-rata | 30% TMP accepted, 70% Monthly pro-rata
1.03 |  | QUALITY |  |  |  | 3 | INDIRECT | QUALITY | QUALITY |  |  |  | A1.03 | V1.05 | QM
1.03.01 |  |  | Quality Management Plan (QMP) |  |  | 4 | INDIRECT | QUALITY | Quality Management Plan (QMP) | SOW 10.1 | Cl 29.2 |  | A1.03.01 | V1.05 | QM |  |  |  | NTP | PC | Approved QMP Document | Milestone | 100% QMP accepted prior to works commencing
1.03.02 |  |  | Inspection & Test Plans (ITPs) |  |  | 4 | INDIRECT | QUALITY | Inspection & Test Plans (ITPs) | SOW 10.2 | Cl 29.2, 30 |  | A1.03.02 |  | Contractor |  |  |  | NTP | PC | Approved ITPs per Discipline, ITP Checklists | Milestone + Per ITP | 30% ITPs approved, 70% Per ITP completed
1.03.03 |  |  | Non-Conformance & Corrective Actions |  |  | 4 | INDIRECT | QUALITY | Non-Conformance & Corrective Actions | SOW 10.3, 10.4 | Cl 29.3 |  | A1.03.03 |  | Contractor |  |  |  | NTP | PC | NCR Register, Corrective Action Reports, Close-out Records | Pro-rata monthly | Pro-rata monthly, NCR register maintained
1.03.04 |  |  | Witness & Hold Point Inspections |  |  | 4 | INDIRECT | QUALITY | Witness & Hold Point Inspections | SOW 10.5 | Cl 30 |  | A1.03.04 |  | Contractor |  |  |  | NTP | PC | Signed Inspection Records, Hold Point Sign-offs | Per inspection | Per inspection completed and signed off
1.03.05 |  |  | Manufacturer's Data Records (MDR) |  |  | 4 | INDIRECT | QUALITY | Manufacturer's Data Records (MDR) | SOW 10.6, SDRL | Cl 30.6 |  | A1.03.05 |  | Contractor |  |  |  | NTP | PC | MDR Packages, Test Certificates, Material Certificates | Milestone | 100% MDR submitted and accepted at PC
1.04 |  | DESIGN |  |  |  | 3 | INDIRECT | DESIGN | DESIGN |  |  |  | A1.04 |  | Design
1.04.01 |  |  | Design Management and Coordination |  |  | 4 | INDIRECT | DESIGN | Design Management and Coordination | SOW 5.0, 3.5 | Cl 7A |  | A1.04.01 |  | Design |  |  |  | NTP | PC | Design Programme, Design Reports, Coordination Meeting Minutes | Milestone | 30% Design kickoff, 40% IFC, 30% As-built accepted
1.04.02 |  |  | Contractor Design Deliverables |  |  | 4 | INDIRECT | DESIGN | Contractor Design Deliverables | SOW 5.0, 3.5 | Cl 7A.2 |  | A1.04.02 |  | Design |  |  |  | NTP | PC | IFC Drawings, Design Documentation, Design Certificates | Milestone | 40% IFC approved, 30% Form 15, 30% Form 12
1.04.03 |  |  | Shop Drawings - All Disciplines |  |  | 4 | INDIRECT | DESIGN | Shop Drawings - All Disciplines | SOW 3.5, 7.4 | Cl 7A.3, 8.3 |  | A1.04.03 |  | Contractor |  |  |  | NTP | PC | Approved Shop Drawings, Fabrication Drawings | Milestone by discipline | 40% Model, 40% IFC accepted, 20% As-built
1.05 |  | APPROVALS |  |  |  | 3 | INDIRECT | APPROVALS | APPROVALS |  |  |  | A1.05 |  | Contractor
1.05.01 |  |  | Building Approval Coordination |  |  | 4 | INDIRECT | APPROVALS | Building Approval Coordination | SOW 6.1 | Cl 11 |  | A1.05.01 |  | Contractor |  |  |  | NTP | PC | Building Approval Certificate, BA Documentation | Milestone | 100% Building approval obtained
1.05.02 |  |  | Authority Inspections & Certifications |  |  | 4 | INDIRECT | APPROVALS | Authority Inspections & Certifications | SOW 6.2 | Cl 11 |  | A1.05.02 |  | Contractor |  |  |  | NTP | PC | Inspection Certificates, Authority Sign-offs | Per inspection | 100% per inspection passed
1.05.03 |  |  | Council / Local Authority Coordination |  |  | 4 | INDIRECT | APPROVALS | Council / Local Authority Coordination | SOW 6.3 | Cl 11 |  | A1.05.03 |  | Contractor |  |  |  | NTP | PC | Council Approvals, DA Documentation | Pro-rata | Pro-rata over approval period
1.05.04 |  |  | Utility Authority Coordination (Power/Water/Comms) |  |  | 4 | INDIRECT | APPROVALS | Utility Authority Coordination (Power/Water/Comms) | SOW 6.4 | Cl 11 |  | A1.05.04 |  | Contractor |  |  |  | NTP | PC | Utility Connection Certificates, Service Agreements | Per utility | 100% per utility connected
1.05.05 |  |  | Fire Authority Approval (QFES) |  |  | 4 | INDIRECT | APPROVALS | Fire Authority Approval (QFES) | SOW 6.5 | Cl 11 |  | A1.05.05 |  | Fire SC |  |  |  | NTP | PC | QFES Approval, Fire Safety Certificate | Milestone | 100% QFES approval obtained
1.05.06 |  |  | Occupancy Certificate / Final Inspection |  |  | 4 | INDIRECT | APPROVALS | Occupancy Certificate / Final Inspection | SOW 6.6 | Cl 11, 34.6 |  | A1.05.06 |  | Contractor |  |  |  | NTP | PC | Occupancy Certificate, Final Inspection Certificate | Milestone | 100% Occupancy certificate issued
1.05.07 |  |  | Form 21 / Final Certificate Coordination |  |  | 4 | INDIRECT | APPROVALS | Form 21 / Final Certificate Coordination | SOW 6.7 | Cl 11 |  | A1.05.07 |  | Contractor |  |  |  | NTP | PC | Form 21 Lodgement, Final Certificate | Milestone | 100% Form 21 lodged
2 | SITE WIDE |  |  |  |  | 2 | DIRECT | SITE WIDE | SITE WIDE |  |  |  | A2 |  | Contractor
2.01 |  | SITE ESTABLISHMENT |  |  |  | 3 | DIRECT | SITE ESTABLISHMENT | SITE ESTABLISHMENT |  |  |  | A2.01 |  | Contractor
2.01.01 |  |  | Site Mobilisation |  |  | 4 | DIRECT | SITE ESTABLISHMENT | Site Mobilisation | SOW 3.1, 3.2 | Cl 27, 32 | A0/01-03 | A2.01.01 |  | Contractor | [5 empty] | Site Establishment Complete, Mobilisation Report | Milestone | 100% Site establishment complete
2.01.02 |  |  | Site Offices & Amenities |  |  | 4 | DIRECT | SITE ESTABLISHMENT | Site Offices & Amenities | SOW 3.1 | Cl 27.1 | A0/01-03 | A2.01.02 |  | Contractor | [5 empty] | Site Office Operational, Amenities Setup Complete | Milestone | 100% Offices operational
2.01.03 |  |  | Temporary Services (Power/Water) |  |  | 4 | DIRECT | SITE ESTABLISHMENT | Temporary Services (Power/Water) | SOW 3.1 | Cl 27 |  | A2.01.03 |  | Contractor | [5 empty] | Temporary Power/Water Connected, Services Certificates | Milestone | 100% Services connected
2.01.04 |  |  | Temporary Fencing & Hoarding |  |  | 4 | DIRECT | SITE ESTABLISHMENT | Temporary Fencing & Hoarding | SOW 3.1 | Cl 27 | A0/01-03 | A2.01.04 |  | Contractor | [5 empty] | Security Fencing Installed, Hoarding Complete | Per linear metre installed | Pro-rata per metre installed
2.01.05 |  |  | Site Signage & Safety Barriers |  |  | 4 | DIRECT | SITE ESTABLISHMENT | Site Signage & Safety Barriers | SOW 3.1 | Cl 27 |  | A2.01.05 | V1.04 | HSE | [5 empty] | Site Signage Installed, Safety Barriers in Place | Milestone | 100% Signage installed
2.01.06 |  |  | Waste Management Setup |  |  | 4 | DIRECT | SITE ESTABLISHMENT | Waste Management Setup | SOW 3.1, 9.4 | Cl 27 |  | A2.01.06 |  | Contractor | [5 empty] | Waste Management System Operational, Bin Setup | Milestone + Pro-rata | 30% Setup, 70% Monthly pro-rata
2.02 |  | DEMOBILISATION |  |  |  | 3 | DIRECT | DEMOBILISATION | DEMOBILISATION |  |  |  | A2.02 |  | Contractor
2.02.01 |  |  | Demobilisation |  |  | 4 | DIRECT | DEMOBILISATION | Demobilisation | SOW 3.12.1 | Cl 27, 40B |  | A2.02.01 |  | Contractor | [5 empty] | Site Establishment Complete, Mobilisation Report | Milestone | 100% Site demobilised post PC
2.02.02 |  |  | Make-good and Reinstatement |  |  | 4 | DIRECT | DEMOBILISATION | Make-good and Reinstatement | SOW 3.12.2 | Cl 27 |  | A2.02.02 |  | Contractor | [5 empty] | Site Reinstatement Complete, Make-good Certificate | Milestone | 100% Site reinstated to pre-works condition
2.02.03 |  |  | Defects Liability & Close-out |  |  | 4 | DIRECT | DEMOBILISATION | Defects Liability & Close-out | SOW 3.11.6, 3.12.6 | Cl 35 |  | A2.02.03 |  | Contractor | [5 empty] | Defects Register, DLP Support Documentation | Pro-rata over DLP | Pro-rata over 12-month DLP
2.03 |  | PROCUREMENT |  |  |  | 3 | DIRECT | PROCUREMENT | PROCUREMENT |  |  |  | A2.03 |  | Contractor
2.03.01 |  |  | Long Lead Items - HVAC Equipment |  |  | 4 | DIRECT | PROCUREMENT | Long Lead Items - HVAC Equipment | SOW 5.2, SDRL | Cl 9.1 | M-01 to M-05 | A2.03.01 |  | Mech SC | [5 empty] | Equipment Delivered & Inspected, Delivery Dockets | Milestone on delivery | 100% Equipment delivered to site
2.03.02 |  |  | Long Lead Items - Switchboards |  |  | 4 | DIRECT | PROCUREMENT | Long Lead Items - Switchboards | SOW 5.2, SDRL | Cl 9.1 | E-01 to E-05 | A2.03.02 |  | Contractor | [5 empty] | Equipment Delivered & Inspected, Delivery Dockets | Milestone on delivery | 100% Switchboards delivered to site
2.03.03 |  |  | Long Lead Items - Fire Services Equipment |  |  | 4 | DIRECT | PROCUREMENT | Long Lead Items - Fire Services Equipment | SOW 5.2 | Cl 9.2 | 690a-d | A2.03.03 |  | Fire SC | [5 empty] | Equipment Delivered & Inspected, Delivery Dockets | Milestone on delivery | 100% Fire equipment delivered to site
2.03.04 |  |  | Architectural Materials Supply |  |  | 4 | DIRECT | PROCUREMENT | Architectural Materials Supply | SOW 4.2.3 | Cl 9.2 | A1-A4 | A2.03.04 |  | Contractor | [5 empty] | Materials Delivered, Quality Certificates | Pro-rata on delivery | Pro-rata per material category delivered
2.03.05 |  |  | Structural Materials Supply |  |  | 4 | DIRECT | PROCUREMENT | Structural Materials Supply | SOW 4.2.1 | Cl 9.2 | 25-595_A1-A4 | A2.03.05 |  | Struct SC | [5 empty] | Materials Delivered, Quality Certificates | Milestone on delivery | 100% Steel/concrete materials delivered
2.04 |  | COMMISSIONING |  |  |  | 3 | DIRECT | COMMISSIONING | COMMISSIONING |  |  |  | A2.04 |  | Contractor
2.04.01 |  |  | Pre-Commissioning Checks - All Services |  |  | 4 | DIRECT | COMMISSIONING | Pre-Commissioning Checks - All Services | SOW 5.1 | Cl 34, 35 |  | A2.04.01 |  | Contractor |  |  |  | Services Complete | Commissioning Complete | Pre-Commissioning Checklists Complete | Milestone | 100% Pre-comm checklists complete
2.04.02 |  |  | HVAC Commissioning & Balancing |  |  | 4 | DIRECT | COMMISSIONING | HVAC Commissioning & Balancing | SOW 5.1 | Cl 34.3 | M-01 to M-05 | A2.04.02 |  | Mech SC |  |  |  | Services Complete | Commissioning Complete | HVAC Commissioning Certificate, Air Balance Reports | Milestone | 100% TAB report accepted
2.04.03 |  |  | Electrical Testing & Certification |  |  | 4 | DIRECT | COMMISSIONING | Electrical Testing & Certification | SOW 5.1 | Cl 34.4 | E-01 to E-05 | A2.04.03 |  | Elec SC |  |  |  | Services Complete | Commissioning Complete | Electrical Test Certificates, Compliance Docs | Milestone | 100% CCEW issued
2.04.04 |  |  | Fire Services Commissioning & Certification |  |  | 4 | DIRECT | COMMISSIONING | Fire Services Commissioning & Certification | SOW 5.1 | Cl 34.5 | 690a-d | A2.04.04 |  | Fire SC |  |  |  | Services Complete | Commissioning Complete | Fire Equipment Delivered, Compliance Certificates | Milestone | 100% Form 80/81 issued
2.04.05 |  |  | Hydraulic Testing |  |  | 4 | DIRECT | COMMISSIONING | Hydraulic Testing | SOW 5.1 | Cl 34.6 | 690a-d | A2.04.05 |  | Hyd SC |  |  |  | Services Complete | Commissioning Complete | Hydraulic Test Certificates, Pressure Test Results | Milestone | 100% Pressure tests passed
2.04.06 |  |  | BMS Integration & Commissioning |  |  | 4 | DIRECT | COMMISSIONING | BMS Integration & Commissioning | SOW 5.1 | Cl 35 |  | A2.04.06 |  | Contractor |  |  |  | Services Complete | Commissioning Complete | BMS Commissioning Certificate, Points List Verified | Milestone | 100% BMS functional, integrated with HVAC
2.04.07 |  |  | Integrated Systems Testing |  |  | 4 | DIRECT | COMMISSIONING | Integrated Systems Testing | SOW 5.1 | Cl 35.2 |  | A2.04.07 |  | Contractor |  |  |  | Services Complete | Commissioning Complete | IST Report, Systems Integration Complete | Milestone | 100% All systems functional together
2.05 |  | CLOSEOUT |  |  |  | 3 | DIRECT | CLOSEOUT | CLOSEOUT |  |  |  | A2.05 |  | Contractor
2.05.01 |  |  | As-Built Documentation |  |  | 4 | DIRECT | CLOSEOUT | As-Built Documentation | SOW 5.2, SDRL | Cl 8.4, 42 |  | A2.05.01 |  | DC |  |  |  | PC | Final Completion | As-Built Drawings Package, Final Documentation | Milestone | 100% As-builts accepted at PC
2.05.02 |  |  | O&M Manuals |  |  | 4 | DIRECT | CLOSEOUT | O&M Manuals | SOW 5.2 | Cl 42 |  | A2.05.02 |  | Contractor |  |  |  | PC | Final Completion | O&M Manuals per System, Digital Handover Package | Milestone | 100% O&M manuals accepted at PC
2.05.03 |  |  | Training Delivery |  |  | 4 | DIRECT | CLOSEOUT | Training Delivery | SOW 5.3 | Cl 42 |  | A2.05.03 |  | Contractor |  |  |  | PC | Final Completion | Training Completion Records, Attendee Sign-off Sheets | Per session | Per training session delivered
2.05.04 |  |  | Practical Completion Requirements |  |  | 4 | DIRECT | CLOSEOUT | Practical Completion Requirements | SOW 5.4 | Cl 42.1 |  | A2.05.04 |  | Contractor |  |  |  | PC | Final Completion | PC Certificate, PC Documentation Package | Milestone | 100% PC achieved
2.05.05 |  |  | Defects Liability Period Support |  |  | 4 | DIRECT | CLOSEOUT | Defects Liability Period Support | SOW 5.5 | Cl 42.5 |  | A2.05.05 |  | Contractor |  |  |  | PC | Final Completion | Defects Register, DLP Support Documentation | Pro-rata over DLP | Pro-rata over 12-month DLP
2.05.06 |  |  | Demobilisation & Site Restoration |  |  | 4 | DIRECT | CLOSEOUT | Demobilisation & Site Restoration | SOW 3.12 | Cl 27 |  | A2.05.06 |  | Contractor |  |  |  | PC | Final Completion | Site Establishment Complete, Mobilisation Report | Milestone | 100% Site restored post PC
2.06 |  | EARTHWORKS |  |  |  | 3 | DIRECT | EARTHWORKS | EARTHWORKS |  |  |  | A2.06 |  | Civil SC
2.06.01 |  |  | Site Clearing & Stripping |  |  | 4 | DIRECT | EARTHWORKS | Site Clearing & Stripping | SOW 4.1, 9.2 | Cl 29.2 | A0/01-02 | A2.06.01 |  | Contractor | [5 empty] | Earthworks Complete, Survey Confirmation, Compaction Tests | Per m² of area cleared | Payment upon completion of clearing, stripping and stockpiling of topsoil
2.06.02 |  |  | Bulk Earthworks - Cut & Fill |  |  | 4 | DIRECT | EARTHWORKS | Bulk Earthworks - Cut & Fill | SOW 9.2 | Cl 29.2 | A0/01-02, 25-595_A4 | A2.06.02 |  | Civil SC | [5 empty] | Earthworks Complete, Survey Confirmation, Compaction Tests | Per m³ of material moved | Payment upon compaction testing passed
2.06.03 |  |  | Subgrade Compaction & Proof Rolling |  |  | 4 | DIRECT | EARTHWORKS | Subgrade Compaction & Proof Rolling | SOW 9.2 | Cl 29.2 | A0/01-02 | A2.06.03 |  | Contractor | [5 empty] | Roof Complete, Weathertight Certificate | Per m² of area compacted | Payment upon compaction certificate issued
2.06.04 |  |  | Import of Approved Fill Material |  |  | 4 | DIRECT | EARTHWORKS | Import of Approved Fill Material | SOW 9.2 | Cl 29.2 | A0/01-02 | A2.06.04 |  | Contractor | [5 empty] | Earthworks Complete, Survey Confirmation, Compaction Tests | Per m³ delivered and placed | Delivery dockets, compaction tests
2.07 |  | STORMWATER |  |  |  | 3 | DIRECT | STORMWATER | STORMWATER |  |  |  | A2.07 |  | Contractor
2.07.01 |  |  | Stormwater Pipes & Fittings |  |  | 4 | DIRECT | STORMWATER | Stormwater Pipes & Fittings | SOW 4.5, 9.4 | Cl 29.2 | 690a-d, A0/02 | A2.07.01 |  | Contractor | [5 empty] | Stormwater Complete, CCTV Inspection, Test Certificates | Per linear metre installed | 60% supply delivered, 40% installed & tested
2.07.02 |  |  | Stormwater Pits & Grates |  |  | 4 | DIRECT | STORMWATER | Stormwater Pits & Grates | SOW 4.5, 9.4 | Cl 29.2 | 690a-d, A0/02 | A2.07.02 |  | Contractor | [5 empty] | Stormwater Complete, CCTV Inspection, Test Certificates | Per pit complete | 50% supply, 50% installed with lid/grate
2.07.03 |  |  | Headwalls & Outlet Structures |  |  | 4 | DIRECT | STORMWATER | Headwalls & Outlet Structures | SOW 9.4 | Cl 29.2 | A0/02 | A2.07.03 |  | Contractor | [5 empty] | Stormwater Complete, CCTV Inspection, Test Certificates | Per structure complete | Per structure complete including erosion protection
2.07.04 |  |  | Stormwater Testing & CCTV |  |  | 4 | DIRECT | STORMWATER | Stormwater Testing & CCTV | SOW 9.4, 5.1 | Cl 34.5 | 690a-d | A2.07.04 |  | Contractor | [5 empty] | Stormwater Complete, CCTV Inspection, Test Certificates | Lump sum upon completion | Test certificates and CCTV report submitted
2.08 |  | TRENCHING |  |  |  | 3 | DIRECT | TRENCHING | TRENCHING |  |  |  | A2.08 |  | Contractor
2.08.01 |  |  | Electrical Service Trenching & Conduits |  |  | 4 | DIRECT | TRENCHING | Electrical Service Trenching & Conduits | SOW 4.4, 9.3 | Cl 29.2 | E-01 to E-05 | A2.08.01 |  | Elec SC | [5 empty] | Electrical Services Complete, Test Certificates | Per linear metre complete | Trench, conduit, backfill, compaction
2.08.02 |  |  | Communications Service Trenching |  |  | 4 | DIRECT | TRENCHING | Communications Service Trenching | SOW 4.4, 9.3 | Cl 29.2 | E-01 to E-05 | A2.08.02 |  | Contractor | [5 empty] | Comms Services Complete, Test Results | Per linear metre complete | Trench, conduit, pit, backfill
2.08.03 |  |  | Hydraulic Service Trenching |  |  | 4 | DIRECT | TRENCHING | Hydraulic Service Trenching | SOW 4.5, 9.3 | Cl 29.2 | 690a-d | A2.08.03 |  | Hyd SC | [5 empty] | Hydraulic Services Complete, Test Certificates | Per linear metre complete | Trench, pipe, backfill, testing
2.08.04 |  |  | Service Pits & Duct Banks |  |  | 4 | DIRECT | TRENCHING | Service Pits & Duct Banks | SOW 9.3 | Cl 29.2 | E-01 to E-05 | A2.08.04 |  | Contractor | [5 empty] | Trenching Complete, Bedding & Backfill Records | Per pit complete | Pit installed with lids and frames
2.09 |  | ROADS |  |  |  | 3 | DIRECT | ROADS | ROADS |  |  |  | A2.09 |  | Contractor
2.09.01 |  |  | Road Subbase Preparation |  |  | 4 | DIRECT | ROADS | Road Subbase Preparation | SOW 9.5 | Cl 29.2 | A0/01-02 | A2.09.01 |  | Contractor | [5 empty] | Roads Complete, Level Survey, Compaction Tests | Per m² of subbase prepared | Compaction test certificates
2.09.02 |  |  | Road Base Course |  |  | 4 | DIRECT | ROADS | Road Base Course | SOW 9.5 | Cl 29.2 | A0/01-02 | A2.09.02 |  | Contractor | [5 empty] | Roads Complete, Level Survey, Compaction Tests | Per m² of base laid | Material delivery, compaction tests
2.09.03 |  |  | Asphalt Wearing Course |  |  | 4 | DIRECT | ROADS | Asphalt Wearing Course | SOW 9.5 | Cl 29.2 | A0/01-02 | A2.09.03 |  | Contractor | [5 empty] | Roads Complete, Level Survey, Compaction Tests | Per m² of asphalt laid | Material delivered, surface complete
2.09.04 |  |  | Road Line Marking & Signage |  |  | 4 | DIRECT | ROADS | Road Line Marking & Signage | SOW 9.5 | Cl 29.2 | A0/01-02 | A2.09.04 |  | Contractor | [5 empty] | Site Signage Installed, Safety Barriers in Place | Lump sum upon completion | Line marking and signage complete
3 | NEW OFFICE BUILDING |  |  |  |  | 2 | DIRECT | NEW OFFICE BUILDING | NEW OFFICE BUILDING |  |  |  | A3 |  | Contractor
3.01 |  | DEMOLITION |  |  |  | 3 | DIRECT | DEMOLITION | DEMOLITION |  |  |  | A3.01 |  | Contractor
3.01.01 |  |  | Strip Out Existing Finishes |  |  | 4 | DIRECT | DEMOLITION | Strip Out Existing Finishes | SOW 4.1.1 | Cl 29.1 | A4/01-02 | A3.01.01 |  | Contractor |  |  |  | NTP | Demo Complete | Strip Out Complete, Waste Disposal Records | Per m² demolished | Per m² complete, waste removed
3.01.02 |  |  | Asbestos Survey |  |  | 4 | DIRECT | DEMOLITION | Asbestos Survey | SOW 4.1.2 | Cl 29.3, WHS Reg | A4/01-02 | A3.01.02 |  | Contractor |  |  |  | NTP | Demo Complete | Asbestos Clearance Certificate, Air Monitoring Reports | Milestone | 100% Survey report accepted
3.01.03 |  |  | Asbestos Removal (Licensed) |  |  | 4 | DIRECT | DEMOLITION | Asbestos Removal (Licensed) | SOW 4.1.2 | Cl 29.3, WHS Reg | A4/01-02 | A3.01.03 |  | Contractor |  |  |  | NTP | Demo Complete | Asbestos Clearance Certificate, Air Monitoring Reports | Per m² removed | Per clearance certificate issued
3.01.04 |  |  | Ceiling & Wall Demolition |  |  | 4 | DIRECT | DEMOLITION | Ceiling & Wall Demolition | SOW 4.1.1 | Cl 29.1 | A4/01-02 | A3.01.04 |  | Contractor |  |  |  | NTP | Demo Complete | Demolition Complete, Clearance Certificate | Per m² demolished | Per m² complete, waste removed
3.01.05 |  |  | Floor Covering Removal |  |  | 4 | DIRECT | DEMOLITION | Floor Covering Removal | SOW 4.1.1 | Cl 29.1 | A4/01-02 | A3.01.05 |  | Contractor |  |  |  | NTP | Demo Complete | Demolition Complete, Clearance Certificate | Per m² removed | Per m² complete, waste removed
3.01.06 |  |  | Services Strip Out (Mech/Elec/Hyd) |  |  | 4 | DIRECT | DEMOLITION | Services Strip Out (Mech/Elec/Hyd) | SOW 4.1.1 | Cl 29.1 | A4/01-02 | A3.01.06 |  | Contractor |  |  |  | NTP | Demo Complete | Strip Out Complete, Waste Disposal Records | Per discipline complete | Per discipline isolated and removed
3.01.07 |  |  | Waste Removal & Disposal |  |  | 4 | DIRECT | DEMOLITION | Waste Removal & Disposal | SOW 4.1.1 | Cl 29.1 |  | A3.01.07 |  | Contractor |  |  |  | NTP | Demo Complete | Demolition Complete, Clearance Certificate | Milestone | 100% Waste disposed lawfully
3.02 |  | STRUCTURE |  |  |  | 3 | DIRECT | STRUCTURE | STRUCTURE |  |  |  | A3.02 |  | Contractor
3.02.01 |  |  | Structural Assessment Report |  |  | 4 | DIRECT | STRUCTURE | Structural Assessment Report | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-06 | A3.02.01 |  | Struct SC |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Engineer's Certificate | Milestone | 100% Report accepted
3.02.02 |  |  | Bored Piers (BP1: 450Ø, 3.0m deep) |  |  | 4 | DIRECT | STRUCTURE | Bored Piers (BP1: 450Ø, 3.0m deep) | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-02 | A3.02.02 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Inspection Certificate | Per pier complete | 40% reo fixed, 60% concrete poured & cured
3.02.03 |  |  | Ground Beams |  |  | 4 | DIRECT | STRUCTURE | Ground Beams | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-02 | A3.02.03 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Inspection Certificate | Per linear metre | 40% reo fixed, 60% concrete poured & cured
3.02.04 |  |  | Concrete Slab on Ground |  |  | 4 | DIRECT | STRUCTURE | Concrete Slab on Ground | SOW 4.2.1 | Cl 29.2 | 25-595_A4/01-02 | A3.02.04 |  | Struct SC |  |  |  | Demo Complete | Structure Complete | Slab Pour Complete, Concrete Test Certificates | Per m² complete | 30% prep/reo, 70% pour & finish
3.02.05 |  |  | SHS Columns (C1: 150x150x6, C2: 125x125x5, C3: 100x100x4) |  |  | 4 | DIRECT | STRUCTURE | SHS Columns (C1: 150x150x6, C2: 125x125x5, C3: 100x100x4) | SOW 4.2.1 | Cl 29.2 | 25-595_A4/03-04 | A3.02.05 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Inspection Certificate | Per column installed | 60% supply, 40% install & connect
3.02.06 |  |  | Roof Beams (B1-B4) |  |  | 4 | DIRECT | STRUCTURE | Roof Beams (B1-B4) | SOW 4.2.1 | Cl 29.2 | 25-595_A4/03-05 | A3.02.06 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Roof Complete, Weathertight Certificate | Per linear metre | 60% supply, 40% install & connect
3.02.07 |  |  | Blockwork - 200 Series (Mech Stores) |  |  | 4 | DIRECT | STRUCTURE | Blockwork - 200 Series (Mech Stores) | SOW 4.2.1 | Cl 29.2 | 25-595_A4/04 | A3.02.07 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Inspection Certificate | Per m² laid | 50% blocks delivered, 50% laid & grouted
3.02.08 |  |  | Lintels (L1, L2) |  |  | 4 | DIRECT | STRUCTURE | Lintels (L1, L2) | SOW 4.2.1 | Cl 29.2 | 25-595_A4/04 | A3.02.08 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Inspection Certificate | Per lintel installed | 60% supply, 40% install
3.03 |  | ROOF |  |  |  | 3 | DIRECT | ROOF | ROOF |  |  |  | A3.03 |  | Contractor
3.03.01 |  |  | Roof Trusses (T1) |  |  | 4 | DIRECT | ROOF | Roof Trusses (T1) | SOW 4.2.2 | Cl 29.2 | 25-595_A4/05 | A3.03.01 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Complete, Weathertight Certificate | Per truss installed | 60% fabricated/delivered, 40% installed
3.03.02 |  |  | Purlins (P1) |  |  | 4 | DIRECT | ROOF | Purlins (P1) | SOW 4.2.2 | Cl 29.2 | 25-595_A4/05 | A3.03.02 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Works Complete, Weathertight Certificate | Per linear metre | 50% supply, 50% fix
3.03.03 |  |  | Roof Sheeting - Strammit Monoclad |  |  | 4 | DIRECT | ROOF | Roof Sheeting - Strammit Monoclad | SOW 4.2.2 | Cl 29.2 | A4/05 | A3.03.03 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Sheeting Complete, Waterproof Inspection | Per m² installed | 50% supply, 50% fix complete
3.03.04 |  |  | Roof Insulation |  |  | 4 | DIRECT | ROOF | Roof Insulation | SOW 4.2.2 | Cl 29.2 | A4/05 | A3.03.04 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Complete, Weathertight Certificate | Per m² installed | 50% supply, 50% fix complete
3.03.05 |  |  | Gutters & Downpipes |  |  | 4 | DIRECT | ROOF | Gutters & Downpipes | SOW 4.2.2 | Cl 29.2 | A4/05, 690b | A3.03.05 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Works Complete, Weathertight Certificate | Per linear metre | 40% supply, 60% fix & connect
3.03.06 |  |  | Flashings & Penetrations |  |  | 4 | DIRECT | ROOF | Flashings & Penetrations | SOW 4.2.2 | Cl 29.2 | A4/05 | A3.03.06 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Works Complete, Weathertight Certificate | Per linear metre | 40% supply, 60% fix & seal
3.03.07 |  |  | Awnings - Bondor Metecnospan |  |  | 4 | DIRECT | ROOF | Awnings - Bondor Metecnospan | SOW 4.2.2 | Cl 29.2 | A4/05 | A3.03.07 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Works Complete, Weathertight Certificate | Per m² installed | 50% supply, 50% fix complete
3.04 |  | EXTERNAL |  |  |  | 3 | DIRECT | EXTERNAL | EXTERNAL |  |  |  | A3.04 |  | Contractor
3.04.01 |  |  | External Cladding |  |  | 4 | DIRECT | EXTERNAL | External Cladding | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.04.01 |  | Contractor | [5 empty] | Cladding Complete, Weatherseal Inspection | Per m² installed | 50% supply, 50% fix complete
3.04.02 |  |  | Windows - G.James 475 Series (24 No.) |  |  | 4 | DIRECT | EXTERNAL | Windows - G.James 475 Series (24 No.) | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.04.02 |  | Contractor | [5 empty] | Windows Installed, Glazing Certificate | Per window installed | 60% supply, 40% install & flash
3.04.03 |  |  | External Doors (Types A-K) |  |  | 4 | DIRECT | EXTERNAL | External Doors (Types A-K) | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.04.03 |  | Contractor | [5 empty] | External Doors Installed, Hardware Complete | Per door installed | 60% supply, 40% install complete
3.04.04 |  |  | External Painting & Finishes |  |  | 4 | DIRECT | EXTERNAL | External Painting & Finishes | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.04.04 |  | Contractor | [5 empty] | Painting Complete, Final Inspection | Per m² complete | 30% prep, 70% paint system complete
3.05 |  | FITOUT |  |  |  | 3 | DIRECT | FITOUT | FITOUT |  |  |  | A3.05 |  | Contractor
3.05.01 |  |  | Partitions - Steel Stud/Plasterboard |  |  | 4 | DIRECT | FITOUT | Partitions - Steel Stud/Plasterboard | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.05.01 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Steel Frame Erected, Structural Inspection Certificate | Per m² complete | 40% frame, 60% line & finish
3.05.02 |  |  | Suspended Ceilings - 1200x600 Acoustic |  |  | 4 | DIRECT | FITOUT | Suspended Ceilings - 1200x600 Acoustic | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.05.02 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Ceilings Complete, Inspection Sign-off | Per m² complete | 40% grid, 60% tiles installed
3.05.03 |  |  | Ceiling Insulation |  |  | 4 | DIRECT | FITOUT | Ceiling Insulation | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.05.03 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Fitout Works Complete, Inspection Sign-off | Per m² installed | 50% supply, 50% install
3.05.04 |  |  | Internal Doors (24 No.) |  |  | 4 | DIRECT | FITOUT | Internal Doors (24 No.) | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.05.04 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | External Doors Installed, Hardware Complete | Per door complete | 60% supply, 40% install & hardware
3.05.05 |  |  | Internal Glazing & Screens |  |  | 4 | DIRECT | FITOUT | Internal Glazing & Screens | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.05.05 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Fitout Works Complete, Inspection Sign-off | Per m² installed | 60% supply, 40% install
3.05.06 |  |  | Bulkheads & Soffits |  |  | 4 | DIRECT | FITOUT | Bulkheads & Soffits | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.05.06 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Fitout Works Complete, Inspection Sign-off | Per m² complete | 40% frame, 60% line & finish
3.06 |  | MECHANICAL |  |  |  | 3 | DIRECT | MECHANICAL | MECHANICAL |  |  |  | A3.06 |  | Mech SC
3.06.01 |  |  | Air Conditioning Units (AC-1 to AC-5) |  |  | 4 | DIRECT | MECHANICAL | Air Conditioning Units (AC-1 to AC-5) | SOW 4.3 | Cl 29.2 | M-01, M-05 | A3.06.01 |  | Contractor | [5 empty] | Mechanical Services Complete, Test Certificates | Per unit complete | 70% supply, 30% install & commission
3.06.02 |  |  | VAV Boxes (VAV-1 to VAV-7) |  |  | 4 | DIRECT | MECHANICAL | VAV Boxes (VAV-1 to VAV-7) | SOW 4.3 | Cl 29.2 | M-01, M-05 | A3.06.02 |  | Contractor | [5 empty] | Mechanical Services Complete, Test Certificates | Per unit complete | 70% supply, 30% install & balance
3.06.03 |  |  | Ductwork - Supply & Return |  |  | 4 | DIRECT | MECHANICAL | Ductwork - Supply & Return | SOW 4.3 | Cl 29.2 | M-01 to M-05 | A3.06.03 |  | Contractor | [5 empty] | Mechanical Services Complete, Test Certificates | Per m² duct face | 50% fabricate, 50% install
3.06.04 |  |  | Diffusers & Grilles |  |  | 4 | DIRECT | MECHANICAL | Diffusers & Grilles | SOW 4.3 | Cl 29.2 | M-01 to M-05 | A3.06.04 |  | Contractor | [5 empty] | Mechanical Services Complete, Test Certificates | Per diffuser installed | 60% supply, 40% install & balance
3.06.05 |  |  | Controls & BMS Integration |  |  | 4 | DIRECT | MECHANICAL | Controls & BMS Integration | SOW 4.3 | Cl 29.2 | M-01 to M-05 | A3.06.05 |  | Contractor | [5 empty] | BMS Commissioning Certificate, Points List Verified | Milestone | 40% hardware, 60% commission
3.06.06 |  |  | Refrigerant Pipework |  |  | 4 | DIRECT | MECHANICAL | Refrigerant Pipework | SOW 4.3 | Cl 29.2 | M-01 to M-05 | A3.06.06 |  | Contractor | [5 empty] | Mechanical Services Complete, Test Certificates | Per linear metre | 40% supply, 60% install & pressure test
3.07 |  | ELECTRICAL |  |  |  | 3 | DIRECT | ELECTRICAL | ELECTRICAL |  |  |  | A3.07 |  | Elec SC
3.07.01 |  |  | Main Switchboard (MSB) |  |  | 4 | DIRECT | ELECTRICAL | Main Switchboard (MSB) | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.01 |  | Contractor | [5 empty] | Switchboards Delivered, Factory Test Certificates | Per board complete | 70% supply, 30% install & connect
3.07.02 |  |  | Distribution Boards |  |  | 4 | DIRECT | ELECTRICAL | Distribution Boards | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.02 |  | Contractor | [5 empty] | Electrical Services Complete, Test Certificates | Per board complete | 70% supply, 30% install & connect
3.07.03 |  |  | Submains Cabling |  |  | 4 | DIRECT | ELECTRICAL | Submains Cabling | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.03 |  | Contractor | [5 empty] | Electrical Services Complete, Test Certificates | Per linear metre | 50% supply, 50% install & terminate
3.07.04 |  |  | General Power Outlets |  |  | 4 | DIRECT | ELECTRICAL | General Power Outlets | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.04 |  | Contractor | [5 empty] | Electrical Services Complete, Test Certificates | Per outlet complete | 40% supply, 60% install & test
3.07.05 |  |  | Lighting Installation |  |  | 4 | DIRECT | ELECTRICAL | Lighting Installation | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.05 |  | Contractor | [5 empty] | Electrical Services Complete, Test Certificates | Per fitting complete | 50% supply, 50% install & commission
3.07.06 |  |  | Emergency Lighting |  |  | 4 | DIRECT | ELECTRICAL | Emergency Lighting | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.06 |  | Contractor | [5 empty] | Electrical Services Complete, Test Certificates | Per fitting complete | 50% supply, 50% install & test
3.07.07 |  |  | Data/Communications Cabling |  |  | 4 | DIRECT | ELECTRICAL | Data/Communications Cabling | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.07 |  | Contractor | [5 empty] | Comms Services Complete, Test Results | Per outlet complete | 50% supply/cable, 50% terminate & test
3.07.08 |  |  | Earthing System |  |  | 4 | DIRECT | ELECTRICAL | Earthing System | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.07.08 |  | Contractor | [5 empty] | Electrical Services Complete, Test Certificates | Milestone | 40% materials, 60% install & test
3.08 |  | HYDRAULIC |  |  |  | 3 | DIRECT | HYDRAULIC | HYDRAULIC |  |  |  | A3.08 |  | Hyd SC
3.08.01 |  |  | Cold Water Reticulation |  |  | 4 | DIRECT | HYDRAULIC | Cold Water Reticulation | SOW 4.5 | Cl 29.2 | 690b | A3.08.01 |  | Contractor | [5 empty] | Hydraulic Services Complete, Test Certificates | Per linear metre | 40% supply, 60% install & pressure test
3.08.02 |  |  | Hot Water System & Reticulation |  |  | 4 | DIRECT | HYDRAULIC | Hot Water System & Reticulation | SOW 4.5 | Cl 29.2 | 690b | A3.08.02 |  | Contractor | [5 empty] | Hydraulic Services Complete, Test Certificates | Per system complete | 60% supply, 40% install & commission
3.08.03 |  |  | Sanitary Plumbing |  |  | 4 | DIRECT | HYDRAULIC | Sanitary Plumbing | SOW 4.5 | Cl 29.2 | 690b | A3.08.03 |  | Hyd SC | [5 empty] | Hydraulic Services Complete, Test Certificates | Per fixture connected | 40% rough-in, 60% fit-off & test
3.08.04 |  |  | Sewer Drainage |  |  | 4 | DIRECT | HYDRAULIC | Sewer Drainage | SOW 4.5 | Cl 29.2 | 690b | A3.08.04 |  | Contractor | [5 empty] | Drainage Complete, Test Certificates | Per linear metre | 40% supply, 60% install & CCTV
3.08.05 |  |  | Stormwater Drainage |  |  | 4 | DIRECT | HYDRAULIC | Stormwater Drainage | SOW 4.5 | Cl 29.2 | 690b | A3.08.05 |  | Contractor | [5 empty] | Stormwater Complete, CCTV Inspection, Test Certificates | Per linear metre | 40% supply, 60% install & test
3.09 |  | FIRE |  |  |  | 3 | DIRECT | FIRE | FIRE |  |  |  | A3.09 |  | Fire SC
3.09.01 |  |  | Fire Hydrants |  |  | 4 | DIRECT | FIRE | Fire Hydrants | SOW 4.5 | Cl 29.2 | 690b | A3.09.01 |  | Fire SC | [5 empty] | Fire Services Complete, Compliance Certificate | Per hydrant complete | 60% supply, 40% install & commission
3.09.02 |  |  | Fire Hose Reels |  |  | 4 | DIRECT | FIRE | Fire Hose Reels | SOW 4.5 | Cl 29.2 | 690b | A3.09.02 |  | Fire SC | [5 empty] | Fire Services Complete, Compliance Certificate | Per hose reel complete | 60% supply, 40% install & commission
3.09.03 |  |  | Fire Indicator Panel (FIP) |  |  | 4 | DIRECT | FIRE | Fire Indicator Panel (FIP) | SOW 4.5 | Cl 29.2 | 690b | A3.09.03 |  | Fire SC | [5 empty] | Fire Services Complete, Compliance Certificate | Per FIP complete | 70% supply, 30% install & commission
3.09.04 |  |  | Smoke/Heat Detectors |  |  | 4 | DIRECT | FIRE | Smoke/Heat Detectors | SOW 4.5 | Cl 29.2 | 690b | A3.09.04 |  | Contractor | [5 empty] | Fire Services Complete, Compliance Certificate | Per detector installed | 50% supply, 50% install & commission
3.09.05 |  |  | Fire Extinguishers & Blankets |  |  | 4 | DIRECT | FIRE | Fire Extinguishers & Blankets | SOW 4.5 | Cl 29.2 | 690b | A3.09.05 |  | Fire SC | [5 empty] | Fire Services Complete, Compliance Certificate | Per unit installed | 80% supply, 20% install & tag
3.1 |  | FINISHES |  |  |  | 3 | DIRECT | FINISHES | FINISHES |  |  |  | A3.10 |  | Contractor
3.10.01 |  |  | Floor Tiles - Amenities |  |  | 4 | DIRECT | FINISHES | Floor Tiles - Amenities | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.10.01 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Finishes Complete, Inspection Sign-off | Per m² complete | 50% supply, 50% lay & grout
3.10.02 |  |  | Carpet Tiles - Office Areas |  |  | 4 | DIRECT | FINISHES | Carpet Tiles - Office Areas | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.10.02 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Finishes Complete, Inspection Sign-off | Per m² complete | 50% supply, 50% install
3.10.03 |  |  | Vinyl - Wet Areas |  |  | 4 | DIRECT | FINISHES | Vinyl - Wet Areas | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.10.03 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Finishes Complete, Inspection Sign-off | Per m² complete | 50% supply, 50% install
3.10.04 |  |  | Wall Tiles - Amenities |  |  | 4 | DIRECT | FINISHES | Wall Tiles - Amenities | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.10.04 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Finishes Complete, Inspection Sign-off | Per m² complete | 50% supply, 50% lay & grout
3.10.05 |  |  | Internal Painting |  |  | 4 | DIRECT | FINISHES | Internal Painting | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.10.05 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Painting Complete, Final Inspection | Per m² complete | 30% prep, 70% paint system complete
3.10.06 |  |  | Skirtings & Architraves |  |  | 4 | DIRECT | FINISHES | Skirtings & Architraves | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.10.06 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Finishes Complete, Inspection Sign-off | Per linear metre | 40% supply, 60% install & finish
3.11 |  | JOINERY |  |  |  | 3 | DIRECT | JOINERY | JOINERY |  |  |  | A3.11 |  | Contractor
3.11.01 |  |  | Kitchenette Joinery |  |  | 4 | DIRECT | JOINERY | Kitchenette Joinery | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.11.01 |  | Contractor | [5 empty] | Joinery Installed, Inspection Sign-off | Per kitchenette complete | 70% fabricate, 30% install & connect
3.11.02 |  |  | Reception Counter |  |  | 4 | DIRECT | JOINERY | Reception Counter | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.11.02 |  | Contractor | [5 empty] | Joinery Installed, QA Inspection Complete | Per item complete | 70% fabricate, 30% install
3.11.03 |  |  | Storage Cupboards |  |  | 4 | DIRECT | JOINERY | Storage Cupboards | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.11.03 |  | Contractor | [5 empty] | Joinery Installed, QA Inspection Complete | Per cupboard complete | 70% fabricate, 30% install
3.11.04 |  |  | Vanity Units - Amenities |  |  | 4 | DIRECT | JOINERY | Vanity Units - Amenities | SOW 4.2.3 | Cl 29.2 | A4/03-04 | A3.11.04 |  | Contractor | [5 empty] | Joinery Installed, QA Inspection Complete | Per vanity complete | 70% fabricate, 30% install & connect
3.12 |  | FFE |  |  |  | 3 | DIRECT | FFE | FFE |  |  |  | A3.12 |  | Contractor
3.12.01 |  |  | Workstations |  |  | 4 | DIRECT | FFE | Workstations | SOW 4.6 | Cl 29.2 | A4 Furniture | A3.12.01 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per workstation complete | 90% supply, 10% install
3.12.02 |  |  | Task Chairs |  |  | 4 | DIRECT | FFE | Task Chairs | SOW 4.6 | Cl 29.2 | A4 Furniture | A3.12.02 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per chair delivered | 100% supply
3.12.03 |  |  | Meeting Room Tables |  |  | 4 | DIRECT | FFE | Meeting Room Tables | SOW 4.6 | Cl 29.2 | A4 Furniture | A3.12.03 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per table complete | 90% supply, 10% install
3.12.04 |  |  | Lockers |  |  | 4 | DIRECT | FFE | Lockers | SOW 4.6 | Cl 29.2 | A4 Furniture | A3.12.04 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per bank complete | 80% supply, 20% install & anchor
3.12.05 |  |  | Whiteboards & Pinboards |  |  | 4 | DIRECT | FFE | Whiteboards & Pinboards | SOW 4.6 | Cl 29.2 | A4 Furniture | A3.12.05 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per board installed | 80% supply, 20% install
3.12.06 |  |  | Kitchen Appliances |  |  | 4 | DIRECT | FFE | Kitchen Appliances | SOW 4.6 | Cl 29.2 | A4 Furniture | A3.12.06 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per appliance installed | 90% supply, 10% install & commission
3.13 |  | EXTERNAL WORKS |  |  |  | 3 | DIRECT | EXTERNAL WORKS | EXTERNAL WORKS |  |  |  | A3.13 |  | Contractor
3.13.01 |  |  | New Office Parking Area - Subbase |  |  | 4 | DIRECT | EXTERNAL WORKS | New Office Parking Area - Subbase | SOW 9.5 | Cl 29.2 | A0/01-02, A4/01 | A3.13.01 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Subbase compacted, tested
3.13.02 |  |  | New Office Parking Area - Paving |  |  | 4 | DIRECT | EXTERNAL WORKS | New Office Parking Area - Paving | SOW 9.5 | Cl 29.2 | A0/01-02, A4/01 | A3.13.02 |  | Contractor | [5 empty] | Paving Complete, Inspection Sign-off | Per m² complete | Paving/concrete surface complete
3.13.03 |  |  | Carpark Line Marking & Signage |  |  | 4 | DIRECT | EXTERNAL WORKS | Carpark Line Marking & Signage | SOW 9.5 | Cl 29.2 | A0/01-02 | A3.13.03 |  | Contractor | [5 empty] | Site Signage Installed, Safety Barriers in Place | Lump sum | Line marking and signage complete
3.13.04 |  |  | Wheel Stops & Bollards |  |  | 4 | DIRECT | EXTERNAL WORKS | Wheel Stops & Bollards | SOW 9.5 | Cl 29.2 | A0/01-02 | A3.13.04 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per item installed | Supply and fix complete
3.13.05 |  |  | Concrete Footpaths |  |  | 4 | DIRECT | EXTERNAL WORKS | Concrete Footpaths | SOW 9.5.1 | Cl 29.2 | A0/01-02, A4/01 | A3.13.05 |  | Struct SC | [5 empty] | Concrete Works Complete, Strength Test Results | Per m² complete | Formwork, pour, finish
3.13.06 |  |  | Feature Paver Footpaths - Entry |  |  | 4 | DIRECT | EXTERNAL WORKS | Feature Paver Footpaths - Entry | SOW 9.5.1, 9.6.1 | Cl 29.2 | A0/01-02, A4/01 | A3.13.06 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Bedding, pavers laid, sealed
3.13.07 |  |  | Access Ramps (DDA Compliant) |  |  | 4 | DIRECT | EXTERNAL WORKS | Access Ramps (DDA Compliant) | SOW 9.5.1 | Cl 29.2 | A0/01-02, A4/01 | A3.13.07 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per ramp complete | Structure, handrails, TGSIs
3.13.08 |  |  | External Stairs & Landings |  |  | 4 | DIRECT | EXTERNAL WORKS | External Stairs & Landings | SOW 9.5.1 | Cl 29.2 | A0/01-02, A4/01 | A3.13.08 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per flight complete | Structure, treads, handrails
3.13.09 |  |  | Courtyard Retaining Wall |  |  | 4 | DIRECT | EXTERNAL WORKS | Courtyard Retaining Wall | SOW 9.5.3 | Cl 29.2 | 25-595_A4, A0/02 | A3.13.09 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per Lm complete | Footing, wall, drainage, backfill
3.13.10 |  |  | Security Fencing |  |  | 4 | DIRECT | EXTERNAL WORKS | Security Fencing | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A3.13.10 |  | Contractor | [5 empty] | Security Fencing Installed, Hoarding Complete | Per Lm installed | Posts, rails, mesh complete
3.13.11 |  |  | Pedestrian & Vehicle Gates |  |  | 4 | DIRECT | EXTERNAL WORKS | Pedestrian & Vehicle Gates | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A3.13.11 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per gate installed | Gate supplied, installed, operational
3.13.12 |  |  | External Handrails & Balustrades |  |  | 4 | DIRECT | EXTERNAL WORKS | External Handrails & Balustrades | SOW 9.5.2 | Cl 29.2 | A0/01-02, A4/01 | A3.13.12 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per Lm installed | Posts, rails, infill complete
3.13.13 |  |  | Courtyard Hardscape Paving |  |  | 4 | DIRECT | EXTERNAL WORKS | Courtyard Hardscape Paving | SOW 9.6.1 | Cl 29.2 | A0/01-02, A4/01 | A3.13.13 |  | Contractor | [5 empty] | Paving Complete, Inspection Sign-off | Per m² complete | Paving, edging, integration
3.13.14 |  |  | Turf Areas |  |  | 4 | DIRECT | EXTERNAL WORKS | Turf Areas | SOW 9.6.2 | Cl 29.2 | A0/01-02 | A3.13.14 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² laid | Soil prep, turf supply, laying
3.13.15 |  |  | Garden Beds - Shrubs & Groundcover |  |  | 4 | DIRECT | EXTERNAL WORKS | Garden Beds - Shrubs & Groundcover | SOW 9.6.2 | Cl 29.2 | A0/01-02 | A3.13.15 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Soil, plants, mulch complete
3.13.16 |  |  | Feature Trees |  |  | 4 | DIRECT | EXTERNAL WORKS | Feature Trees | SOW 9.6.2 | Cl 29.2 | A0/01-02 | A3.13.16 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per tree planted | Tree supply, planting, staking
3.13.17 |  |  | Irrigation System |  |  | 4 | DIRECT | EXTERNAL WORKS | Irrigation System | SOW 9.6.2 | Cl 29.2 | 690a-d | A3.13.17 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Lump sum | Pipes, heads, controller complete
3.13.18 |  |  | External & Landscape Lighting |  |  | 4 | DIRECT | EXTERNAL WORKS | External & Landscape Lighting | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A3.13.18 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per light installed | Pole, fixture, cabling complete
3.13.19 |  |  | Shade Structures - Courtyard |  |  | 4 | DIRECT | EXTERNAL WORKS | Shade Structures - Courtyard | SOW 9.5.4 | Cl 29.2 | A0/01-02, A4/01 | A3.13.19 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per structure installed | Footings, structure, membrane
4 | REGISTRY BUILDING |  |  |  |  | 2 | DIRECT | REGISTRY BUILDING | REGISTRY BUILDING |  |  |  | A4 |  | Contractor
4.01 |  | DEMOLITION |  |  |  | 3 | DIRECT | DEMOLITION | DEMOLITION |  |  |  | A4.01 |  | Contractor
4.01.01 |  |  | Strip Out Existing Finishes |  |  | 4 | DIRECT | DEMOLITION | Strip Out Existing Finishes | SOW 4.1 | Cl 29.1 | 25-595_A1/02 | A4.01.01 |  | Contractor |  |  |  | NTP | Demo Complete | Strip Out Complete, Waste Disposal Records | Per m² demolished | Per m² complete, waste removed
4.01.02 |  |  | Hazardous Materials Removal |  |  | 4 | DIRECT | DEMOLITION | Hazardous Materials Removal | SOW 4.1.2 | Cl 29.3 | 25-595_A1/02 | A4.01.02 |  | Contractor |  |  |  | NTP | Demo Complete | Demolition Complete, Clearance Certificate | Milestone | Per clearance certificate
4.02 |  | STRUCTURE |  |  |  | 3 | DIRECT | STRUCTURE | STRUCTURE |  |  |  | A4.02 |  | Contractor
4.02.01 |  |  | Structural Assessment & Repairs |  |  | 4 | DIRECT | STRUCTURE | Structural Assessment & Repairs | SOW 4.2.1 | Cl 29.2 | 25-595_A1/01-04 | A4.02.01 |  | Struct SC |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Engineer's Certificate | Milestone | 30% assessment, 70% repairs complete
4.02.02 |  |  | Concrete Slab Repairs |  |  | 4 | DIRECT | STRUCTURE | Concrete Slab Repairs | SOW 4.2.1 | Cl 29.2 | 25-595_A1/01-04 | A4.02.02 |  | Struct SC |  |  |  | Demo Complete | Structure Complete | Slab Pour Complete, Concrete Test Certificates | Per m² repaired | 30% prep, 70% repair & finish
4.03 |  | ROOF |  |  |  | 3 | DIRECT | ROOF | ROOF |  |  |  | A4.03 |  | Contractor
4.03.01 |  |  | Roof Refurbishment Package |  |  | 4 | DIRECT | ROOF | Roof Refurbishment Package | SOW 4.2.2 | Cl 29.2 | 25-595_A1/03-04 | A4.03.01 |  | Contractor |  |  |  | Structure Complete | Roof Complete | Roof Complete, Weathertight Certificate | Milestone | 40% materials, 60% install complete
4.04 |  | SERVICES |  |  |  | 3 | DIRECT | SERVICES | SERVICES |  |  |  | A4.04 |  | Contractor
4.04.01 |  |  | Mechanical Services Package |  |  | 4 | DIRECT | SERVICES | Mechanical Services Package | SOW 4.3 | Cl 29.2 | M-02 | A4.04.01 |  | Mech SC | [5 empty] | Mechanical Services Complete, Test Certificates | Milestone | 60% supply, 40% install & commission
4.04.02 |  |  | Electrical Services Package |  |  | 4 | DIRECT | SERVICES | Electrical Services Package | SOW 4.4 | Cl 29.2 | E-02 | A4.04.02 |  | Elec SC | [5 empty] | Electrical Services Complete, Test Certificates | Milestone | 50% supply, 50% install & test
4.04.03 |  |  | Hydraulic Services Package |  |  | 4 | DIRECT | SERVICES | Hydraulic Services Package | SOW 4.5 | Cl 29.2 | 690c | A4.04.03 |  | Hyd SC | [5 empty] | Hydraulic Services Complete, Test Certificates | Milestone | 40% supply, 60% install & test
4.04.04 |  |  | Fire Services Package |  |  | 4 | DIRECT | SERVICES | Fire Services Package | SOW 4.5 | Cl 29.2 | 690c | A4.04.04 |  | Fire SC | [5 empty] | Fire Equipment Delivered, Compliance Certificates | Milestone | 60% supply, 40% install & commission
4.05 |  | FITOUT |  |  |  | 3 | DIRECT | FITOUT | FITOUT |  |  |  | A4.05 |  | Contractor
4.05.01 |  |  | Partitions & Ceilings Package |  |  | 4 | DIRECT | FITOUT | Partitions & Ceilings Package | SOW 4.2.3 | Cl 29.2 | A1/03-04 | A4.05.01 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Partitions Complete, Inspection Sign-off | Milestone | 40% frame, 60% line & finish
4.05.02 |  |  | Floor & Wall Finishes Package |  |  | 4 | DIRECT | FITOUT | Floor & Wall Finishes Package | SOW 4.2.3 | Cl 29.2 | A1/03-04 | A4.05.02 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Internal Finishes Complete | Per m² complete | 50% supply, 50% install
4.05.03 |  |  | Joinery Package |  |  | 4 | DIRECT | FITOUT | Joinery Package | SOW 4.2.3 | Cl 29.2 | A1/03-04 | A4.05.03 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Joinery Installed, Inspection Sign-off | Per item complete | 70% fabricate, 30% install
4.05.04 |  |  | FFE Package |  |  | 4 | DIRECT | FITOUT | FFE Package | SOW 4.6 | Cl 29.2 | A1 Furniture | A4.05.04 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Furniture & Equipment Installed, Asset Register | Per item delivered | 90% supply, 10% install
0.13 |  | EXTERNAL WORKS |  |  |  | 3 | DIRECT | EXTERNAL WORKS | EXTERNAL WORKS |  |  |  | A0.13 |  | Contractor
0.13.01 |  |  | Registry Parking Area |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry Parking Area | SOW 9.5 | Cl 29.2 | A0/01-02, A1/01-02 | A0.13.01 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Subbase + paving complete
0.13.02 |  |  | Registry Footpaths & Entry |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry Footpaths & Entry | SOW 9.5.1 | Cl 29.2 | A0/01-02, A1/01-02 | A0.13.02 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Formwork, concrete, finish
0.13.03 |  |  | Registry Access Ramps (DDA) |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry Access Ramps (DDA) | SOW 9.5.1 | Cl 29.2 | A0/01-02, A1/01-02 | A0.13.03 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per ramp complete | Structure, handrails, TGSIs
0.13.04 |  |  | Registry Landscaping - Hardscape |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry Landscaping - Hardscape | SOW 9.6 | Cl 29.2 | A0/01-02 | A0.13.04 |  | Contractor | [5 empty] | Landscaping Complete, Planting Schedule Confirmed | Per m² complete | Paving, edging complete
0.13.05 |  |  | Registry Landscaping - Softscape |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry Landscaping - Softscape | SOW 9.6.2 | Cl 29.2 | A0/01-02 | A0.13.05 |  | Contractor | [5 empty] | Landscaping Complete, Planting Schedule Confirmed | Per m² complete | Turf/planting, mulch complete
0.13.06 |  |  | Registry External Lighting |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry External Lighting | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A0.13.06 |  | Contractor | [5 empty] | External Lighting Operational, Test Certificates | Per light installed | Pole, fixture, cabling complete
0.13.07 |  |  | Registry Perimeter Works |  |  | 4 | DIRECT | EXTERNAL WORKS | Registry Perimeter Works | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A0.13.07 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Provisional Sum | Fencing, gates as required
5 | WORKSHOP BUILDING |  |  |  |  | 2 | DIRECT | WORKSHOP BUILDING | WORKSHOP BUILDING |  |  |  | A5 |  | Contractor
5.01 |  | DEMOLITION |  |  |  | 3 | DIRECT | DEMOLITION | DEMOLITION |  |  |  | A5.01 |  | Contractor
5.01.01 |  |  | Strip Out & Hazmat Removal |  |  | 4 | DIRECT | DEMOLITION | Strip Out & Hazmat Removal | SOW 4.1 | Cl 29.1 | 25-595_A2/02 | A5.01.01 |  | Contractor |  |  |  | NTP | Demo Complete | Strip Out Complete, Waste Disposal Records | Milestone | Per clearance certificate
5.02 |  | STRUCTURE |  |  |  | 3 | DIRECT | STRUCTURE | STRUCTURE |  |  |  | A5.02 |  | Contractor
5.02.01 |  |  | Structural Assessment & Repairs Package |  |  | 4 | DIRECT | STRUCTURE | Structural Assessment & Repairs Package | SOW 4.2.1 | Cl 29.2 | 25-595_A2/01-04 | A5.02.01 |  | Struct SC |  |  |  | Demo Complete | Structure Complete | Structural Works Complete, Engineer's Certificate | Milestone | 30% assessment, 70% repairs
5.02.02 |  |  | Roof Refurbishment Package |  |  | 4 | DIRECT | STRUCTURE | Roof Refurbishment Package | SOW 4.2.2 | Cl 29.2 | 25-595_A2/03-04 | A5.02.02 |  | Contractor |  |  |  | Demo Complete | Structure Complete | Roof Complete, Weathertight Certificate | Milestone | 40% supply, 60% install
5.04 |  | SERVICES |  |  |  | 3 | DIRECT | SERVICES | SERVICES |  |  |  | A5.04 |  | Contractor
5.04.01 |  |  | Mechanical Services Package |  |  | 4 | DIRECT | SERVICES | Mechanical Services Package | SOW 4.3 | Cl 29.2 | M-03 | A5.04.01 |  | Mech SC | [5 empty] | Mechanical Services Complete, Test Certificates | Milestone | 60% supply, 40% install & commission
5.04.02 |  |  | Electrical Services Package |  |  | 4 | DIRECT | SERVICES | Electrical Services Package | SOW 4.4 | Cl 29.2 | E-03 | A5.04.02 |  | Elec SC | [5 empty] | Electrical Services Complete, Test Certificates | Milestone | 50% supply, 50% install & test
5.04.03 |  |  | Hydraulic & Fire Services Package |  |  | 4 | DIRECT | SERVICES | Hydraulic & Fire Services Package | SOW 4.5 | Cl 29.2 | 690d | A5.04.03 |  | Hyd SC | [5 empty] | Fire Equipment Delivered, Compliance Certificates | Milestone | 50% supply, 50% install & test
5.05 |  | FITOUT |  |  |  | 3 | DIRECT | FITOUT | FITOUT |  |  |  | A5.05 |  | Contractor
5.05.01 |  |  | Internal Fitout Package |  |  | 4 | DIRECT | FITOUT | Internal Fitout Package | SOW 4.2.3 | Cl 29.2 | A2/03-04 | A5.05.01 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Fitout Works Complete, Inspection Sign-off | Milestone | 50% supply, 50% install
5.05.02 |  |  | Finishes & Joinery Package |  |  | 4 | DIRECT | FITOUT | Finishes & Joinery Package | SOW 4.2.3 | Cl 29.2 | A2/03-04 | A5.05.02 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Joinery Installed, Inspection Sign-off | Milestone | 60% supply, 40% install
5.05.03 |  |  | FFE Package |  |  | 4 | DIRECT | FITOUT | FFE Package | SOW 4.6 | Cl 29.2 | A2 Furniture | A5.05.03 |  | Contractor |  |  |  | Roof Complete | Fitout Complete | Furniture & Equipment Installed, Asset Register | Per item delivered | 90% supply, 10% install
0.13 |  | EXTERNAL WORKS |  |  |  | 3 | DIRECT | EXTERNAL WORKS | EXTERNAL WORKS |  |  |  | A0.13 |  | Contractor
0.13.09 |  |  | Workshop Parking Area |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop Parking Area | SOW 9.5 | Cl 29.2 | A0/01-02, A2/01 | A0.13.09 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Subbase + paving complete
0.13.10 |  |  | Workshop Hardstand & Aprons |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop Hardstand & Aprons | SOW 9.5 | Cl 29.2 | A0/01-02, A2/01 | A0.13.10 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Concrete poured and finished
0.13.11 |  |  | Workshop Footpaths & Access |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop Footpaths & Access | SOW 9.5.1 | Cl 29.2 | A0/01-02, A2/01 | A0.13.11 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Formwork, concrete, finish
0.13.12 |  |  | Workshop Compound Fencing |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop Compound Fencing | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A0.13.12 |  | Contractor | [5 empty] | Security Fencing Installed, Hoarding Complete | Per Lm installed | Posts, rails, mesh complete
0.13.13 |  |  | Workshop Gates |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop Gates | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A0.13.13 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per gate installed | Gate supplied, installed, operational
0.13.14 |  |  | Workshop External Lighting |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop External Lighting | SOW 4.4 | Cl 29.2 | E-01 to E-05 | A0.13.14 |  | Contractor | [5 empty] | External Lighting Operational, Test Certificates | Per light installed | Pole, fixture, cabling complete
0.13.15 |  |  | Workshop Landscaping Allowance |  |  | 4 | DIRECT | EXTERNAL WORKS | Workshop Landscaping Allowance | SOW 9.6 | Cl 29.2 | A0/01-02 | A0.13.15 |  | Contractor | [5 empty] | Landscaping Complete, Planting Schedule Confirmed | Provisional Sum | Turf, planting as required
6 | WAREHOUSE BUILDING |  |  |  |  | 2 | DIRECT | WAREHOUSE BUILDING | WAREHOUSE BUILDING |  |  |  | A6 |  | Contractor
6.07 |  | WORKS |  |  |  | 3 | DIRECT | WORKS | WORKS |  |  |  | A6.07 |  | Contractor
6.07.01 |  |  | Demolition & Hazmat Package |  |  | 4 | DIRECT | WORKS | Demolition & Hazmat Package | SOW 4.1 | Cl 29.1 | 25-595_A3/01-02 | A6.07.01 |  | Contractor | [5 empty] | Demolition Complete, Clearance Certificate | Milestone | Per clearance certificate
6.07.02 |  |  | Structural & Roof Package |  |  | 4 | DIRECT | WORKS | Structural & Roof Package | SOW 4.2.1 | Cl 29.2 | 25-595_A3/01-02 | A6.07.02 |  | Struct SC | [5 empty] | Structural Works Complete, Engineer's Certificate | Milestone | 40% supply, 60% install
6.07.03 |  |  | Building Services Package |  |  | 4 | DIRECT | WORKS | Building Services Package | SOW 4.3-4.5 | Cl 29.2 | M-04, E-04, 690a | A6.07.03 |  | Contractor | [5 empty] | Refurbishment Works Complete, Inspection Sign-off | Milestone | 50% supply, 50% install & commission
6.07.04 |  |  | Internal Fitout & Finishes |  |  | 4 | DIRECT | WORKS | Internal Fitout & Finishes | SOW 4.2.3 | Cl 29.2 | A3/01-02 | A6.07.04 |  | Contractor | [5 empty] | Internal Finishes Complete | Milestone | 50% supply, 50% install
6.07.05 |  |  | FFE Package |  |  | 4 | DIRECT | WORKS | FFE Package | SOW 4.6 | Cl 29.2 | A3 Furniture | A6.07.05 |  | Contractor | [5 empty] | Furniture & Equipment Installed, Asset Register | Per item delivered | 90% supply, 10% install
0.13 |  | EXTERNAL WORKS |  |  |  | 3 | DIRECT | EXTERNAL WORKS | EXTERNAL WORKS |  |  |  | A0.13 |  | Contractor
0.13.17 |  |  | Warehouse Parking Area |  |  | 4 | DIRECT | EXTERNAL WORKS | Warehouse Parking Area | SOW 9.5 | Cl 29.2 | A0/01-02, A3/01 | A0.13.17 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Subbase + paving complete
0.13.18 |  |  | Loading Dock Aprons |  |  | 4 | DIRECT | EXTERNAL WORKS | Loading Dock Aprons | SOW 9.5 | Cl 29.2 | A0/01-02, A3/01 | A0.13.18 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Concrete poured and finished
0.13.19 |  |  | Warehouse Footpaths & Access |  |  | 4 | DIRECT | EXTERNAL WORKS | Warehouse Footpaths & Access | SOW 9.5.1 | Cl 29.2 | A0/01-02, A3/01 | A0.13.19 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per m² complete | Formwork, concrete, finish
0.13.20 |  |  | Warehouse Security Fencing |  |  | 4 | DIRECT | EXTERNAL WORKS | Warehouse Security Fencing | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A0.13.20 |  | Contractor | [5 empty] | Security Fencing Installed, Hoarding Complete | Per Lm installed | Posts, rails, mesh complete
0.13.21 |  |  | Warehouse Gates |  |  | 4 | DIRECT | EXTERNAL WORKS | Warehouse Gates | SOW 9.5.2 | Cl 29.2 | A0/01-02 | A0.13.21 |  | Contractor | [5 empty] | External Works Complete, Inspection Certificate | Per gate installed | Gate supplied, installed, operational
7 | TRAVEL & ACCOMMODATION |  |  |  |  | 2 | T&A | TRAVEL & ACCOMMODATION | TRAVEL & ACCOMMODATION |  |  |  | A7 |  | Contractor
7.01 |  | TRAVEL ALLOWANCES |  |  |  | 3 | T&A | TRAVEL ALLOWANCES | TRAVEL ALLOWANCES |  |  |  | A7.01 |  | Contractor
7.01.01 |  |  | Vehicle Allowance (Site Vehicle) |  |  | 4 | T&A | TRAVEL ALLOWANCES | Vehicle Allowance (Site Vehicle) | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.01.01 |  | Contractor | [5 empty] | Travel Records & Claim Documentation | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.01.02 |  |  | Flights Allowance (Key Personnel) |  |  | 4 | T&A | TRAVEL ALLOWANCES | Flights Allowance (Key Personnel) | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.01.02 |  | Contractor | [5 empty] | Travel Records & Claim Documentation | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.01.03 |  |  | Mileage / Fuel Reimbursement |  |  | 4 | T&A | TRAVEL ALLOWANCES | Mileage / Fuel Reimbursement | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.01.03 |  | Contractor | [5 empty] | Travel Records & Claim Documentation | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.02 |  | ACCOMMODATION |  |  |  | 3 | T&A | ACCOMMODATION | ACCOMMODATION |  |  |  | A7.02 |  | Contractor
7.02.01 |  |  | Management Personnel Accommodation |  |  | 4 | T&A | ACCOMMODATION | Management Personnel Accommodation | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.02.01 |  | Contractor | [5 empty] | Accommodation Records, Booking Confirmations | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.02.02 |  |  | Supervision Personnel Accommodation |  |  | 4 | T&A | ACCOMMODATION | Supervision Personnel Accommodation | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.02.02 |  | Contractor | [5 empty] | Accommodation Records, Booking Confirmations | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.02.03 |  |  | Workforce Accommodation Allowance |  |  | 4 | T&A | ACCOMMODATION | Workforce Accommodation Allowance | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.02.03 |  | Contractor | [5 empty] | Accommodation Records, Booking Confirmations | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.03 |  | MEALS & INCIDENTALS |  |  |  | 3 | T&A | MEALS & INCIDENTALS | MEALS & INCIDENTALS |  |  |  | A7.03 |  | Contractor
7.03.01 |  |  | Meals Allowance (Per Diem) |  |  | 4 | T&A | MEALS & INCIDENTALS | Meals Allowance (Per Diem) | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.03.01 |  | Contractor | [5 empty] | Meal Allowance Records | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.03.02 |  |  | Incidental Expenses Allowance |  |  | 4 | T&A | MEALS & INCIDENTALS | Incidental Expenses Allowance | SOW 7.2.2, 11.0 | Cl 22, 23 |  | A7.03.02 |  | Contractor | [5 empty] | Incident Reports, Investigation Records, Corrective Actions | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.04 |  | REMOTE AREA ALLOWANCES |  |  |  | 3 | T&A | REMOTE AREA ALLOWANCES | REMOTE AREA ALLOWANCES |  |  |  | A7.04 |  | Contractor
7.04.01 |  |  | Site Disability / Remote Area Allowance |  |  | 4 | T&A | REMOTE AREA ALLOWANCES | Site Disability / Remote Area Allowance | SOW 11.0 | Cl 22, 23 |  | A7.04.01 |  | Contractor | [5 empty] | Remote Area Allowance Records | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
7.04.02 |  |  | Living Away from Home Allowance (LAFHA) |  |  | 4 | T&A | REMOTE AREA ALLOWANCES | Living Away from Home Allowance (LAFHA) | SOW 11.0 | Cl 22, 23 |  | A7.04.02 |  | Contractor | [5 empty] | Remote Area Allowance Documentation | Pro-rata monthly over contract period | Pro-rata monthly, provided management plans & reports accepted by Principal
1 | PROVISIONAL SUMS |  |  |  |  | 2 | PROVISIONAL | PROVISIONAL SUMS | PROVISIONAL SUMS |  |  |  | P1 |  | Contractor
1.01 |  | SITE CONDITIONS |  |  |  | 3 | PROVISIONAL | SITE CONDITIONS | SITE CONDITIONS |  |  |  | P1.01 |  | Contractor
1.01.01 |  |  | Latent Conditions Allowance |  |  | 4 | PROVISIONAL | SITE CONDITIONS | Latent Conditions Allowance | SOW 2.1 | Cl 25.2 |  | P1.01.01 |  | Contractor | [5 empty] | Latent Conditions Report, Assessment Documentation | As directed | Expended as directed by Superintendent
1.01.02 |  |  | Rock Excavation Allowance |  |  | 4 | PROVISIONAL | SITE CONDITIONS | Rock Excavation Allowance | SOW 2.1 | Cl 25.2 |  | P1.01.02 |  | Contractor | [5 empty] | Rock Excavation Records, Volume Measurements | Per m³ rock | Per m³ rock encountered
1.01.03 |  |  | Contaminated Soil Allowance |  |  | 4 | PROVISIONAL | SITE CONDITIONS | Contaminated Soil Allowance | SOW 2.1 | Cl 25.2 |  | P1.01.03 |  | Contractor | [5 empty] | Latent Conditions Report, Site Assessment | Per m³ disposed | Per m³ contaminated material disposed
1.02 |  | HAZMAT |  |  |  | 3 | PROVISIONAL | HAZMAT | HAZMAT |  |  |  | P1.02 |  | Contractor
1.02.01 |  |  | Additional Asbestos Removal |  |  | 4 | PROVISIONAL | HAZMAT | Additional Asbestos Removal | SOW 4.1.2 | Cl 25.2, WHS |  | P1.02.01 |  | Contractor | [5 empty] | Asbestos Clearance Certificate, Air Monitoring Reports | Per m² removed | Per clearance certificate issued
1.02.02 |  |  | Lead Paint Removal |  |  | 4 | PROVISIONAL | HAZMAT | Lead Paint Removal | SOW 4.1.2 | Cl 25.2, WHS |  | P1.02.02 |  | Contractor | [5 empty] | Painting Complete, Final Inspection | Per m² removed | Per clearance certificate issued
1.02.03 |  |  | Synthetic Mineral Fibre Removal |  |  | 4 | PROVISIONAL | HAZMAT | Synthetic Mineral Fibre Removal | SOW 4.1.2 | Cl 25.2, WHS |  | P1.02.03 |  | Contractor | [5 empty] | Hazmat Clearance Certificate, Disposal Records | Per m² removed | Per clearance certificate issued
1.04 |  | SERVICES |  |  |  | 3 | PROVISIONAL | SERVICES | SERVICES |  |  |  | P1.04 |  | Contractor
1.04.01 |  |  | Electrical Services Diversion |  |  | 4 | PROVISIONAL | SERVICES | Electrical Services Diversion | SOW 3.3 | Cl 25.2 |  | P1.04.01 |  | Elec SC | [5 empty] | Electrical Services Complete, Test Certificates | As directed | Per Superintendent direction
1.04.02 |  |  | Hydraulic Services Diversion |  |  | 4 | PROVISIONAL | SERVICES | Hydraulic Services Diversion | SOW 3.3 | Cl 25.2 |  | P1.04.02 |  | Hyd SC | [5 empty] | Hydraulic Services Complete, Test Certificates | As directed | Per Superintendent direction
1.04.03 |  |  | Communications/Data Diversion |  |  | 4 | PROVISIONAL | SERVICES | Communications/Data Diversion | SOW 3.3 | Cl 25.2 |  | P1.04.03 |  | Contractor | [5 empty] | Comms Services Complete, Test Results | As directed | Per Superintendent direction
1.04 |  | DESIGN |  |  |  | 3 | PROVISIONAL | DESIGN | DESIGN |  |  |  | P1.04 |  | Design
1.04.05 |  |  | Architectural Design Development |  |  | 4 | PROVISIONAL | DESIGN | Architectural Design Development | SOW 5.0 | Cl 25.2, 7A |  | P1.04.05 |  | Design | [5 empty] | Design Documentation & Drawings | As directed | Per design variation approved
1.04.06 |  |  | Structural Design Development |  |  | 4 | PROVISIONAL | DESIGN | Structural Design Development | SOW 5.0 | Cl 25.2, 7A |  | P1.04.06 |  | Design | [5 empty] | Structural Works Complete, Engineer's Certificate | As directed | Per design variation approved
1.04.07 |  |  | Services Design Development |  |  | 4 | PROVISIONAL | DESIGN | Services Design Development | SOW 5.0 | Cl 25.2, 7A |  | P1.04.07 |  | Design | [5 empty] | Design Documentation & Drawings | As directed | Per design variation approved
1.05 |  | CONTINGENCY |  |  |  | 3 | PROVISIONAL | CONTINGENCY | CONTINGENCY |  |  |  | P1.05 |  | Contractor
1.05.01 |  |  | General Contingency Allowance |  |  | 4 | PROVISIONAL | CONTINGENCY | General Contingency Allowance | SOW 3.0 | Cl 25.2 |  | P1.05.01 |  | Contractor | [5 empty] | Contingency Expenditure Records | As directed | Expended as directed by Superintendent
1.05.02 |  |  | Interface Coordination Allowance |  |  | 4 | PROVISIONAL | CONTINGENCY | Interface Coordination Allowance | SOW 3.4 | Cl 25.2 |  | P1.05.02 |  | Contractor | [5 empty] | Contingency Expenditure Records | As directed | Per interface issue resolved
1.05.03 |  |  | Inclement Weather Allowance |  |  | 4 | PROVISIONAL | CONTINGENCY | Inclement Weather Allowance | SOW 2.2 | Cl 25.2, 34.8 |  | P1.05.03 |  | Contractor | [5 empty] | Contingency Expenditure Records | Per qualifying day | Per qualifying inclement weather day
1.06 |  | AV WORKS |  |  |  | 3 | PROVISIONAL | AV WORKS | AV WORKS |  |  |  | P1.06 |  | Contractor
1.06.01 |  |  | AV Contractor Attendance |  |  | 4 | PROVISIONAL | AV WORKS | AV Contractor Attendance | SOW 3.4.2 | Cl 25.2 |  | P1.06.01 |  | Contractor | [5 empty] | AV Systems Installed, Commissioning Certificate | Per week attendance | Per week of AV contractor on site
1.06.02 |  |  | AV Power & Data Points |  |  | 4 | PROVISIONAL | AV WORKS | AV Power & Data Points | SOW 3.4.2 | Cl 25.2 |  | P1.06.02 |  | Contractor | [5 empty] | Data Cabling Complete, Certification | Per point installed | Per AV point installed

## Numbering
L1 | L1 Description (Cost Area) | L2 | L2 Description (Area) | L3 | L3 Description (Sub Area) | L4 | L4 Description (Activity / comoditity))
CS | Contract Sum | [6 empty] | V | Variations | 1 | PERSONNEL DAYWORK RATES
A | Section A - Lump Sum | 1 | INDIRECT COSTS
|  |  |  | 01 | PROJECT MANAGEMENT
|  |  |  | 02 | HSE
|  |  |  | 03 | QUALITY
|  |  |  | 04 | DESIGN
|  |  |  | 05 | APPROVALS
|  | 2 | SITE WIDE
|  |  |  | 01 | SITE ESTABLISHMENT
|  |  |  | 02 | DEMOBILISATION
|  |  |  | 03 | PROCUREMENT
|  |  |  | 04 | COMMISSIONING
|  |  |  | 05 | CLOSEOUT
|  |  |  | 06 | EARTHWORKS
|  |  |  | 07 | STORMWATER
|  |  |  | 08 | TRENCHING
|  |  |  | 09 | ROADS
|  | 3 | NEW OFFICE BUILDING
|  |  |  | 01 | DEMOLITION
|  |  |  | 02 | STRUCTURE
|  |  |  | 03 | ROOF
|  |  |  | 04 | EXTERNAL
|  |  |  | 05 | FITOUT
|  |  |  | 06 | MECHANICAL
|  |  |  | 07 | ELECTRICAL
|  |  |  | 08 | HYDRAULIC
|  |  |  | 09 | FIRE
|  |  |  | 10 | FINISHES
|  |  |  | 11 | JOINERY
|  |  |  | 12 | FFE
|  |  |  | 13 | EXTERNAL WORKS
|  | 4 | REGISTRY BUILDING
|  |  |  | 01 | DEMOLITION
|  |  |  | 02 | STRUCTURE
|  |  |  | 03 | ROOF
|  |  |  | 04 | SERVICES
|  |  |  | 05 | FITOUT
|  |  |  | 06 | EXTERNAL WORKS
|  | 5 | WORKSHOP BUILDING
|  |  |  | 01 | DEMOLITION
|  |  |  | 02 | STRUCTURE
|  |  |  | 03 | SERVICES
|  |  |  | 04 | FITOUT
|  |  |  | 05 | EXTERNAL WORKS
|  | 6 | WAREHOUSE BUILDING | 06
|  |  |  | 07 | WORKS
|  |  |  | 08 | EXTERNAL WORKS
|  | 7 | TRAVEL & ACCOMMODATION
|  |  |  | 01 | TRAVEL ALLOWANCES
|  |  |  | 02 | ACCOMMODATION
|  |  |  | 03 | MEALS & INCIDENTALS
|  |  |  | 04 | REMOTE AREA ALLOWANCES
P | Section B - Provisional Sum | 1 | PROVISIONAL SUMS
|  |  |  | 01 | SITE CONDITIONS
|  |  |  | 02 | HAZMAT
|  |  |  | 03 | SERVICES
|  |  |  | 04 | DESIGN
|  |  |  | 05 | CONTINGENCY
|  |  |  | 06 | AV WORKS
V | Variations | 1 | PERSONNEL DAYWORK RATES
Z | Tenderer Identified Items