## V1
SUMMARY
[9 empty] | Cost | 0 | Cost | 0
JOB DESCRIPTION: |  |  | 2026-05-14 | [5 empty] | Markup | 10% | Markup | 10%
SITE ADDRESS: |  |  | TCS Quote #: 2378 | [5 empty] | Charge = | 0 | Charge = | 0
[6 empty] | Cost | (Cost + O/H) + Profit
TOTALS
PART A | Stormwater Drainage (Civil & Hydraulic) |  | #DIV/0! |  |  | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
Manual Calc
|  | TOTAL ex GST | #DIV/0! | Prelim | 0.035 | 0 | of total cost | 0
|  |  |  | O/H | 0.155 | 0 | of total cost | 0
|  |  |  | Sub Total |  | 0 | total cost + Prelim + O/H
|  |  |  | Gross Profit | 10% | 0 | Exl equip & Fixt
|  |  |  | Grand Total |  | 0
|  |  |  | Total Markup | 29%
|  |  |  | Net Profit Incl Equip |  | 0

## Prelim_OH-Check
Project:
Tricore -
Stage 1 Version 1
Item
A | PRELIMINARIES
|  | Unit | REQ | Cost ex GST | Total ex GST
Labour
0
Contingencies; Wet Weather ?
| TRADESMAN_LEADING HAND | Day | 0 | 822.5 | 0
| TRADESMAN_PLUMBER_OPERATOR | Day | 0 | 400 | 0
| T/A & Apprentice | Day | 0 | 597.6276 | 0
| Crew #1 | Day | 0 | 1895.3002 | 0
| Crew #2 | Day | 0 | 1511.9133 | 0
Equipment, Hire, Subbies
| Dual CabUte | item | 0 | 0 | 0
| 10m3_Skip Bin | item | 0 | 0 | 0
| TCS Container; Ecl Freight | item | 0 | 0 | 0
| Fencing | item | 0 | 0 | 0
|  | item | 0 | 0 | 0
Misc.
| Site Admin, Stationary etc - GREENSTAR ADMINS | item | 0 | 1600 | 0
| Site PPE | item | 0 | 400 | 0
| Site Consumables- Paint, Tapes etc | item | 0 | 180 | 0
| Site Management - Bollards, Pickets, Barrier Mesh etc | item | 0 | 400 | 0
| Staff Refreshments - ONSITE | item | 0 | 50 | 0
| Staff Refreshments - Offsite | item | 0 | 50 | 0
| TOOLS - Roll Grover - S&M | item | 0 | 320 | 0
| TOOLS - Poly Welder - S&M | item | 0 | 320 | 0
| TOOLS - Wacker/Laser/Misc - S&M | item | 0 | 580 | 0
| TOOLS - Demo Saw Trolley - PURCHASE | item | 0 | 0 | 0
| TOOLS - Consumabls - Blades, etc | item | 0 | 420 | 0
|  |  |  | Total TCS Prelims | 0
A | OverHeads
|  | Unit | REQ | Cost ex GST | Total ex GST
| TriCore Overheads - COMPLETE…PER MONTH | item | 0 | 20000 | 0
|  | item | 0 | 0 | 0
|  | item | 0 | 0 | 0
|  |  |  | Total TCS O/H | 0

## SW Zone Sumry
Project:
Tricore -
Stage 1 Version 1
Item
B | Labour
TOTAL Labour
From Proposed Program
0
DAY
| TRADESMAN_LEADING HAND | Day |  | 822.5 | 0
| CREW - Fire & WAT | Day |  | 2222.5 | 0
| CREW - Drainage | Day |  | 2222.5 | 0
| CREW #3 | Day |  | 2222.5 | 0
| T/A & Apprentice | Day |  | 612.5 | 0
| TRADESMAN.1 | Day |  | 805 | 0
| TRADESMAN.2 | Day |  | 805 | 0
HOUR
| TRADESMAN_LEADING HAND | HR |  | 0 | 0
| TRADESMAN_PLUMBER_OPERATOR | HR |  | 0 | 0
| T/A & Apprentice | HR |  | 0 | 0
| Crew #1 | HR |  | 0 | 0
| Crew #2 | HR |  | 0 | 0
C | Equipment, Hire, Subbies |  |  |  |  | TOTAL Equip
| Skid Steer Loader_Wheeled | ea |  | 300 | 0 | 0
| Skid Steer Loader_Wheeled | ea |  | 300 | 0
| 8Ton_Excavator | ea |  | 300 | 0
| 20-24Ton_Excavator | ea |  | 450 | 0
| 14-16Ton_Excavator | ea |  | 440 | 0
| 6-12T_Tipper Truck | ea |  | 400 | 0
| <10T_Articulated Site Tipper | ea |  | 341 | 0
| Trench Roller_Dbl Drum_Remote | ea |  | 180 | 0
| Trench Roller_Dbl Drum_Remote | ea |  | 180 | 0
| <26Ft_Scissor Lift - Diesel | ea |  | 150 | 0
| Compaction Testing | ea |  | 122 | 0
| CCTV | ea |  | 1680 | 0
| Misc Hire/Tooling | ea |  | 1680 | 0
| Flushing, protections | ea |  | 1680 | 0
| Spoil removal | ea |  | 4200 | 0
| Maximesh to one pit | ea |  | 1680 | 0
| Pit customoziation | ea |  | 1680 | 0
| Carpark, fottpath demo & resto | ea |  | 2677 | 0
| Fuel - Diesel_Machinery & Equip/WEEK (Average) | ea |  | 2500 | 0
**Mini tankers Avg 6,000/Mnth
D | Material
| Material; | ea | 1 | 0 | 0
| Inground Quarry Products; Complete | ea | 1 | 0 | 0
| MANHOLE Concrete | ea | 1 | 0 | 0
| FILTER Install Inc Gravels & Crane | ea |  | 2120 | 0
| Lean mix stab sand etc - ROADS | ea |  | 1650 | 0
E | Misc
|  | M3 | 0 | 0 | 0
| Total Taken forward to Summary |  |  | Total | 0

## SW_Mataterial
SECTION A
STORMWATER DRAINAGE
Description | Qty | Unit | Rate | Total
rcp/frc
PIPE 675MM - RCP_C3 |  | m | 270 | 0
PIPE 600MM - RCP_C4 |  | m | 219.4833 | 0
PIPE 600MM - RCP_C2 |  | m | 203 | 0
PIPE 525MM - RCP_C4 |  | m | 187 | 0
PIPE 525MM - RCP_C3 |  | m | 140.91 | 0
PIPE 450MM - RCP_C4 |  | m | 133.4487 | 0
PIPE 375MM - RCP_C4 |  | m | 89.7909 | 0
PIPE 375MM - RCP_C3 |  | m | 87.11 | 0
PIPE 375MM - RCP_C2 |  | m | 87.11 | 0
SW_SN8 RIBBED (Blackmax or similar) |  | m
PIPE Ribbed RRJ 900MM |  | m
PIPE Ribbed RRJ 825MM |  | m
PIPE Ribbed RRJ 750MM |  | m | 232 | 0
PIPE Ribbed RRJ 675MM |  | m | 232 | 0
PIPE Ribbed RRJ 600MM |  | m | 120.08 | 0
PIPE Ribbed RRJ 525MM |  | m | 89 | 0
PIPE Ribbed RRJ 450MM |  | m | 62.05 | 0
PIPE Ribbed RRJ 375MM |  | m | 51.55 | 0
PIPE Ribbed RRJ 300MM |  | m | 41 | 0
PIPE Ribbed RRJ 225MM |  | m | 26 | 0
PIPE Ribbed RRJ 150MM |  | m | 9.72 | 0
SW_SN8 PVC Pipeline
PIPE DWV SN8 PVC S/WELD 375MM |  | m | 96.33 | 0
PIPE DWV SN8 PVC S/WELD 300MM |  | m | 54.33 | 0
PIPE DWV SN4 PVC S/WELD 300MM |  | m | 49.8333 | 0
PIPE SW H/D PVC S/WELD 300MM |  | m | 40 | 0
PIPE DWV SN8 PVC S/WELD 225MM |  | m | 39.7772 | 0
PIPE DWV SN4 PVC S/WELD 225MM |  | m | 31 | 0
50mm PVC Class 12 |  | m | 18 | 0
PIPE DWV SN8 PVC S/WELD 150MM |  | m | 14.1667 | 0
PIPE DWV SN4 PVC S/WELD 150MM |  | m | 11.6667 | 0
PIPE DWV SN4 PVC S/WELD 100MM |  | m | 12 | 0
SW Grade Option
300MM * 45D PVC SW JUNCTION |  | ea | 159 | 0
300X225X45D PVC SW JUNCTION |  | ea | 141.5 | 0
300MM X 225MM SW Reducer |  | ea | 45 | 0
300MM X 90Deg SW Bend |  | ea | 49 | 0
300MM X 45Deg SW Bend |  | ea | 44 | 0
225MM * 45D PVC SW JUNCTION |  | ea | 51 | 0
225X150X45D PVC SW JUNCTION |  | ea | 37 | 0
225MM X 90Deg SW Bend |  | ea | 23.5 | 0
225MM X 45Deg SW Bend |  | ea | 15 | 0
150 PVC SW 45Deg Junct |  | ea | 12.5 | 0
150MM X 90Deg SW Bend |  | ea | 5.5 | 0
150MM X 45Deg SW Bend |  | ea | 5.5 | 0
DWV Grade Option
600*225 Ribbed Saddle |  | ea | 490 | 0
600*45Deg RIBBED Bend |  | ea | 650 | 0
600*450 Ribbed Reducer |  | ea | 1100 | 0
450*375 Ribbed*PVC Reducer |  | ea | 460 | 0
450 45 Deg ribbed Bend |  | ea | 580 | 0
450 * 225 Ribbed Saddle |  | ea | 320 | 0
375mm X 45Deg Junction |  | ea | 420 | 0
375X300X45D PVC JUNCTION |  | ea | 562.39 | 0
375X225X45D PVC JUNCTION |  | ea | 563.39 | 0
375MM X 300MM Reducer |  | ea | 380 | 0
375MM X 225MM Reducer |  | ea | 360 | 0
375MM X 90Deg Bend |  | ea | 540 | 0
375MM X 45Deg Bend |  | ea | 450 | 0
300MM * 45D PVC JUNCTION |  | ea | 360 | 0
300X225X45D PVC JUNCTION |  | ea | 320 | 0
300MM X 225MM Reducer |  | ea | 190 | 0
300MM X 90Deg Bend |  | ea | 250 | 0
300MM X 45Deg Bend |  | ea | 190 | 0
300MM X 150 Junction
225MM * 45D PVC JUNCTION |  | ea | 85.25 | 0
225X150X45D PVC JUNCTION |  | ea | 210 | 0
225MM X 90Deg Bend |  | ea | 62 | 0
225MM X 45Deg Bend |  | ea | 61 | 0
225MM X 150MM Reducer |  | ea | 120 | 0
150MM X 100MM Reducer |  | ea | 85 | 0
150 PVC DWV 45Deg Junct |  | ea | 18 | 0
150MM X 90Deg Bend |  | ea | 16 | 0
150MM X 45Deg Bend |  | ea | 12 | 0
150X100X45D PVC JUNCTION |  | ea | 16 | 0
100MM X 90Deg Bend |  | ea | 12 | 0
100MM X 45Deg Bend |  | ea | 12 | 0
150mm PVC 10mm nut hanging clip |  | ea | 1.9 | 0
10mm Zinc Threaded Rod |  | m | 2 | 0
Glue - Blue - 4Ltr |  | ea | 26.4 | 0
Primer - Red - 4Ltr |  | ea | 23 | 0
600*600 pits |  | ea | 990 | 0
SW_Gully/Pit
Concrete/GRC - Class D - 450SQ Pit w/base - 450H |  | ea | 139 | 0
Concrete/GRC - Class D - 450SQ Pit w/base - 600H |  | ea | 190 | 0
Concrete/GRC - Class D - 450SQ Riser - 150H |  | ea | 102 | 0
Concrete/GRC - Class D - 450SQ Riser - 300H |  | ea | 124 | 0
Concrete/GRC - Class D - 450SQ Riser - 450H |  | ea | 135 | 0
Concrete/GRC - Class D - 600SQ Pit w/base - 450H |  | ea |  | 0
Concrete/GRC - Class D - 600SQ Pit w/base - 600H |  | ea | 168 | 0
Concrete/GRC - Class D - 900SQ Pit w/base - 450H |  | ea |  | 0
Concrete/GRC - Class D - 900SQ Pit w/base - 600H |  | ea | 355 | 0
Concrete/GRC - Class D - 900SQ Pit w/base - 900H |  | ea | 370 | 0
Concrete/GRC - Class D - 600SQ Riser - 150H |  | ea | 109 | 0
Concrete/GRC - Class D - 600SQ Riser - 300H |  | ea | 138 | 0
Concrete/GRC - Class D - 600SQ Riser - 600H |  | ea | 201.25 | 0
Concrete/GRC - Class D - 600SQ Riser - 900H |  | ea
Concrete/GRC - Class D - 900SQ Pit w/base - 900H |  | ea | 370 | 0
Concrete/GRC - Class D - 900SQ Riser - 150H |  | ea | 145 | 0
Concrete/GRC - Class D - 900SQ Riser - 300H |  | ea | 190 | 0
Concrete/GRC - Class D - 900SQ Riser - 450H |  | ea
Concrete/GRC - Class D - 900SQ Riser - 600H |  | ea | 285 | 0
Concrete/GRC - Class D - 900SQ Riser - 900H |  | ea | 375 | 0
Concrete Precast Base - Class D - 1050 dia |  | ea |  | 0
Concrete Precast Chamber/Shaft - Class D - 1200dia @ 150 Height |  | ea |  | 0
Concrete Precast Base - Class D - 1200dia |  | ea | 1000 | 0
Concrete Precast Chamber/Shaft - Class D - 1200dia @ 200 Height |  | ea | 330 | 0
Concrete Precast Chamber/Shaft - Class D - 1200dia @ 300 Height |  | ea | 410 | 0
Concrete/GRC - Class D - 1200*900*1200 PIT w/Base - 1200H |  | ea | 1082 | 0
Concrete/GRC - Class D - 1200*900* Riser - 150H |  | ea | 286.1 | 0
Concrete/GRC - Class D - 1200*900* Riser - 300H |  | ea | 409.4 | 0
Concrete/GRC - Class D - 1200*1200*1200 PIT w/Base - 1200H |  | ea | 966 | 0
Concrete/GRC - Class D - 1200*1200 Riser - 150H |  | ea | 286.1 | 0
Concrete/GRC - Class D - 1200*1200 Riser - 300H |  | ea | 409.4 | 0
Concrete/GRC - Class D - 1200*1200 Riser - 600H |  | ea | 662.4 | 0
Concrete/GRC - Class D - 1200*1200 Riser - 900H |  | ea | 828 | 0
Concrete/GRC - Class D - 1500*1500*1500 shaft |  | ea | 1810.1 | 0
Concrete/GRC - Class D - 1500*1500 Riser - 300H |  | ea | 637.1 | 0
Concrete/GRC - Class D - 1500*1500 Riser - 600H |  | ea | 841.25 | 0
Concrete/GRC - Class D - 1500*1500 Riser - 900H |  | ea | 1528.35 | 0
Concrete/GRC - Class D - 1500*1500 Riser - 900H |  | ea
Concrete/GRC - Class D - 600*900 Pit w/base - 600H |  | ea | 326 | 0
Concrete/GRC - Class D - 600*900 Pit w/base - 800-900H |  | ea | 355 | 0
Concrete/GRC - Class D - 600*900 Riser - 150H |  | ea | 132 | 0
Concrete/GRC - Class D - 600*900 Riser - 300H |  | ea | 150 | 0
Concrete/GRC - Class D - 600*900 Riser - 450H |  | ea | 197 | 0
Concrete/GRC - Class D - 600*900 Riser - 600H |  | ea | 275 | 0
Concrete/GRC - Class D - 600*900 Riser - 900H |  | ea | 350 | 0
PRECAST MANHOLE SHAFT 1050 X 300 |  | ea | 263 | 0
PRECAST MANHOLE SHAFT 1050 X 600 |  | ea | 293 | 0
PRECAST MANHOLE SHAFT 1050 X 900 |  | ea | 364 | 0
PRECAST MANHOLE SHAFT 1050 X 1200 |  | ea | 445 | 0
PRECAST MANHOLE SHAFT 1050 X 1200 with600mm extension |  | ea | 600 | 0
PRECAST MANHOLE SHAFT 1500 SQ |  | ea | 1810.1 | 0
PRECAST MANHOLE SHAFT 1500 SQ 150 RISER |  | ea | 637.1 | 0
PRECAST MANHOLE SHAFT 1500 DIA |  | ea
1200X300 PRECAST CONCRETE STORMWATER SHAFT |  | ea | 275 | 0
1200X600 PRECAST CONCRETE STORMWATER SHAFT |  | ea | 408 | 0
1200X900 PRECAST CONCRETE STORMWATER SHAFT |  | ea | 503 | 0
450x450 CL D Galv Heelguard Lockable |  | ea | 160 | 0
600x600 CL D Galv Heelguard Lockabl |  | ea | 286 | 0
Class D - Galv - Grate & Frame - 600SQ |  | ea | 195 | 0
900x900 CL D 2 Part Galv Heelguard |  | ea | 640 | 0
Class D - Galv - Grate & Frame - 900SQ |  | ea | 406 | 0
600x900 CL D Galv 2 Part Heelguard |  | ea | 390 | 0
Class D - Galv - Grate & Frame - 600*900 |  | ea | 298 | 0
600x900 Solid lid |  | ea | 572 | 0
Class D - Galv - Grate & Frame - 1200*900 |  | ea | 829 | 0
Class D - Galv - Grate & Frame - 1200*1200 |  | ea | 530.4 | 0
Class B - Galv - Grate & Frame - Concrete Surround - 450SQ |  |  |  | 0
Class B - Galv - Grate & Frame - Concrete Surround - 600SQ |  |  |  | 0
Class B - Galv - Grate & Frame - Concrete Surround - 900SQ |  |  |  | 0
Class B - Galv - Grate & Frame - Concrete Surround - 600*900 |  |  |  | 0
Class D - Galv - Grate & Frame - Concrete Surround - 450SQ |  |  |  | 0
Class D - Galv - Grate & Frame - Concrete Surround - 600SQ |  |  |  | 0
1200 x1200 surcharge grate |  | ea | 971 | 0
Class D - Galv - Grate & Frame - Concrete Surround - 600*900
2.4mt (1.8M C/O) kerb entry- Creek unit centre c/w 900x600 Class D Gully grate Creek |  | ea | 1299 | 0
Pit Base Unit 900 x 600 x 900mm |  | ea | 402 | 0
ASPRO S/W 1050 X 1350 X 175 600 - 600 ROUND HOLE |  | ea | 295 | 0
ASPRO S/W 1050 X 1350 X 175 600 - 900X900 ROUND HOLE |  | ea |  | 0
ASPRO S/W 1050 X 1350 X 175 600 - 600*900 HOLE |  | ea | 400 | 0
ASPRO S/W 1200 X 1650 X 175 9 X 9 - 600 ROUND HOLE |  | ea |  | 0
ASPRO S/W 1200 X 1650 X 175 9 X 9 - 900 X 900 HOLE |  | ea | 365 | 0
ASPRO S/W 1200 X 1650 X 175 9 X 9 - 600*900 HOLE |  | ea | 400 | 0
ASPRO S/W 2100 X 2600 X 250 - 600*900 HOLE |  | ea | 1800 | 0
HEADWALL TO SUIT 450MM RCP |  | ea | 380 | 0
HEADWALL TO SUIT 2 X 375MM RCP |  | ea | 1290 | 0
STORMWATER C&F 600 dia CLASS D - Bolt down (2 bolts) |  | ea | 240 | 0
600x900 CL D Gal Lockable Sump Grate & Frame |  | ea | 372 | 0
900x900 CL D 2 Part Gal Lockable Sump Grate & Frame |  | ea | 440 | 0
100mm socked ag pipe |  | m | 5 | 0
MH Step Irons (230mm Wide) |  | ea | 18.12 | 0 |  |  | 0
Kerb Adapter - Galv - SQ/Flat/Upright - |  | ea |  | 0
Kerb Adapter - Galv - Layback/Sloped - |  | ea |  | 0
PVC Round x Rectangle adapt - 90mm - 100*50 |  | ea |  | 0
PVC Round x Rectangle adapt - 90mm - 100*75 |  | ea |  | 0
Flexible Coupler - (flexseal/Fernco) - 225-250mm |  | ea | 110 | 0
Flexible Coupler - (flexseal/Fernco) - 750-200mm |  | ea |  | 0
Flexible Coupler - (flexseal/Fernco) - 140-165mm |  | ea |  | 0
Flexible Coupler - (flexseal/Fernco) - 125-150mm |  | ea |  | 0
Flexible Coupler - (flexseal/Fernco) - 110-115mm |  | ea |  | 0
MEGA Poxy (2 Part) - 4L |  | ea | 143.89 | 0
MEGA Poxy (2 Part) - 20L |  | ea | 381.11 | 0
Bidim Geofabric Roll = 2m x 50m+>? |  | ea | 78.67 | 0
Glue - Blue - 4Ltr |  | ea | 28.05 | 0
Primer - Red - 4Ltr |  | ea | 23.85 | 0
Manhole Sealant Mastic 3.6m |  | ea | 20 | 0
Concrete Bag - Rapid Set |  | ea | 9.68 | 0
Concrete Bag - Regular |  | ea | 9.35 | 0
Mortar Mix Bag - Regular |  | ea | 8.63 | 0
General Purpose Cement Bag |  | ea | 8.71 | 0
Sand & Cement Bag |  | ea | 9 | 0
Bitumen Cold Mix Bag |  | ea | 25.42 | 0
Detectable STORMWATER Marker Tape - 250m |  | ea | 75 | 0
Form Ply & Sand Bags |  | item | 2800 | 0
0
|  |  | Contingency | 14%
|  |  | Total Taken Forward | 0
TOTAL MATERIAL COST TAKEN FORWARD
0
Excavation/Quarry/Misc/ Takeoff.
| Qty | Unit
Avrg Trench = .900D*.450W | 0 | m
L/M Of Asphalt Reinstate | 0 | m
M2 Of Asphalt Reinstate | 0 | m2
L/M Of CBR Reinstate | 0 | m
L/M of Inground Pipe (Average Depth) | 0 | m
L/M of Inground Pipe (Deeper Than Average Depth) |  | m
Avergage of trtenches 'Shared'…. Shared trench Factor | 0 | m
SEWER / SW / TW - InGrnd |  | m | #DIV/0!
WAT / FIRE - InGrnd |  | m | #DIV/0!
SPK - InGrnd |  | m | #DIV/0!
| D | W | L | Spoil/Compact Factor; | Shared Trench Factor | Total m3 - EXCAVATED | Total M3 - Bed, Pipe, Cover reduction | Total M3 - Backfill Req (Less Bed&Pipe) | Total M3 - Spoil - REMOVE | TCS Load - Haulage & dump rate only
L/M of Inground Pipe (Average Depth) | 1.2 | 0.6 | 0 | 1.3 | 0 | 0
L/M of Inground Pipe (Deeper Than Average Depth) | 1.2 | 0.5 | 0 | 1.3 | 0 | 0
L/M of Bed, Pipe, Cover material reduction (Average Depth) | 0.35 | 0.6 | 0 | 0 | 0 |  | 0
L/M of Bed, Pipe, Cover material reduction (Deeper Than Average Depth) | 0.2 | 0.5 | 0 | 0 | 0 |  | 0
L/M of BACKFILL required (Average Depth) | 1.2 | 0.6 | 0 | 1.3 | 0 |  |  | 0
L/M of BACKFILL required (Deeper Than Average Depth) | 1.2 | 0.5 | 0 | 1.3 | 0 |  |  | 0
[9 empty] | QTY | Rate | Total
[6 empty] | 0 | 0 | 0 | 0 | 40 | 0
MANHOLE Concrete | m3/TB | Qty | Total m3 | Contingency | Total m3 | Total Cost
| 0.1 |  | 0 | 1.2 | 0 | 0
Quarry & Concrete Product
1.18
Description | Unit/LM | Unit | Rate | Rate/LM |  |  | QTY | Shared Trench Factor | Total Req. | Total | Contingency | TOTAL | Drainage Use | Fire/WAT Use | SPK Use
5-7mm Stone | 0.203 | Ton | 62 | 12.586 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
5-7mm Stone | 0.14 | m3 | 62 | 16.926
10-12mm Stone | 0.45 | Ton | 62 | 27.9 |  |  | 0 |  |  | 0
80-110mm Stone | 0 | Ton | 25 | 0 |  |  | 0 |  |  | 0
Medium River / Bed Sand | 0.225 | Ton | 40 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0!
Medium River / Bed Sand | 0.14 | m3 | 40 | 8.4
CBR15 Road Base | 0.36 | Ton | 27 | 9.72 |  |  | 0 |  |  | 0
CBR45 | 0.36 | Ton | 30 | 10.8 |  |  | 0 |  |  | 0
LEANMIX | 0.3 | m3 | 0 | 0 |  |  | 0 |  |  | 0
|  |  | TCS | Q2
Description |  | Unit | Rate | Rate
5-7mm Stone |  | T | 62 | 31
10-12mm Stone |  | T | 62 | 39
80-110mm Stone |  | T | 25 | 29
Medium River / Bed Sand |  | T | 40 | 26
CBR15 Road Base |  | T | 48 | 27
CBR45 |  | T | 50 | 30
LEANMIX_20mm-12:1 |  | M3 | 168 | 0
Concrete_32/20/100 |  | M3 | 400 | 0
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allow for Class 4
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allow for Class 4

## SW_Pit Takeoff
2022-12-23
Total Qty
600 Grte/frm Height |  | 0.055
600*900 Grte/frm Height |  | 0.08
1.2*1.2 Grte/frm Height |  | 0.14
1200*9*6 ASPRO Height |  | 0.175
600 infl Height |  | 0.055
600 V Grate Height |  | 0.15
600 Pit Base Height |  | 0.6
600 Pit Riser Height |  | 0.15
600 Pit Riser Height |  | 0.3
600 Pit Riser Height |  | 0.6
600 Pit Riser Height |  | 0.9
900*900 Pit Base Height |  | 0.9
600*900 Pit Riser Height |  | 0.15
600*900 Pit Riser Height |  | 0.3
600*900 Pit Riser Height |  | 0.6
600*900 Pit Riser Height |  | 0.9
1050 Chmbr Base Height |  | 1.2 | 1200
1050 Chmbr Riser Height |  | 0.15
1050 Chmbr Riser Height |  | 0.3
1050 Chmbr Riser Height |  | 0.6
1050 Chmbr Riser Height |  | 0.9
1050 Chmbr Riser Height |  | 1.2
| 1200*1200*200 | 0.2 | [24 empty] | 0.2for1.2
[12 empty] | Manual calc | [12 empty] | V3 |  | Manual calc | [13 empty] | V3 |  | Manual calc
Pit Count | PIT No. | Grate RL | Type | Grate Size | Chamber | Outlet IL | Depth |  |  | Riser Height Req. w/ base |  | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser | Pit riser difference | Pit Count | PIT No. | Grate RL | Type | Grate Size | Chamber | Outlet IL | Depth |  | Riser Height Req. w/base | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser | Pit riser difference | Pit Count | PIT No. | Grate RL | Type | Grate Size | Chamber | Outlet IL | Depth |  |  | Riser Height Req. w/ base | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser | Pit riser difference
1 | [6 empty] | 0 |  |  | -0.5 | [5 empty] | -0.5 | 21 | [6 empty] | 0.986 | 1 | 0.631 |  |  | 1 |  | 0.031 | 40 | 46 | [7 empty] | -0.75 | -1.34 |  |  |  |  | -1.34
2 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | 22 | [6 empty] | 0.949 | -0.949 | 0.594 |  |  | 1 |  | -0.006 | 42 | 47 | [7 empty] | -0.75 | -1.34 |  |  |  |  | -1.34
3 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | 23 | [6 empty] | 0 |  | -0.98 |  |  |  |  | -0.98 | 43 | [8 empty] | -0.75 | -0.98 |  |  |  |  | -0.98
4 | [6 empty] | 0 |  |  | -1.155 | [5 empty] | -1.155 | 24 | [7 empty] | 2.1 | -0.98 |  |  |  |  | -0.98 | 44 | [8 empty] | -0.75 | -0.98 |  |  |  |  | -0.98
5 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | 25 | [7 empty] | 0.86 | -0.98 |  |  |  |  | -0.98 | 45 | [8 empty] | -0.75
6 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | 26 | [7 empty] | 2.26 | -0.98 |  |  |  |  | -0.98 | 46 | [8 empty] | -0.75
7 | [6 empty] | 0 |  |  | -0.98 | [5 empty] | -0.98 | 27 | [7 empty] | 1.96 | -0.98 |  |  |  |  | -0.98 | 47 | [8 empty] | -0.75
8 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | 28 | [7 empty] | 2.1 | -0.98 |  |  |  |  | -0.98 | 48 | [8 empty] | -0.75
9 | [6 empty] | 0 |  |  | -1.155 | [5 empty] | -1.155 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
10 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
11 | [6 empty] | 0 |  |  | -0.655 | [5 empty] | -0.655 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
12 | [6 empty] | 0 |  |  | -0.505 | [5 empty] | -0.505 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
13 | [6 empty] | 0.767 |  |  | 0.262 | [5 empty] | 0.262 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
14 | [6 empty] | 0.882 |  |  | 0.377 | [5 empty] | 0.377 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
15 | [6 empty] | 1.291 |  |  | 0.636 | [5 empty] | 0.636 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
16 | [6 empty] | 0.969 |  |  | 0.464 | [5 empty] | 0.464 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
17 | [6 empty] | 0 |  |  | -0.98 | [5 empty] | -0.98 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
18 | [6 empty] | 0 |  |  | -0.98 | [5 empty] | -0.98 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
19 | [6 empty] | 2.51 |  |  | 1.53 | [5 empty] | 1.53 | [8 empty] | 2.1 | -0.98 |  |  |  |  | -0.98
20 | [6 empty] | 0.615 |  |  | -0.04 | [5 empty] | -0.04 | [8 empty] | 2.1 | -0.945 |  |  |  |  | -0.945
[10 empty] | Pit Bases |  | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser | [10 empty] | Pits | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser | [11 empty] | Pits | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser
300x300 ploy
[7 empty] | 450x450 poly | [15 empty] | 900High | 900*600 |  |  | 0 | 0 | 0 | 0 | [8 empty] | 900High | 900*600
[7 empty] | 450*450 |  |  |  | 450High | [12 empty] | 1050 |  |  | 0 | 0 | 1 | 0 | [9 empty] | 1050 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 600*600 |  |  |  | 600High | [12 empty] | 1200 |  |  | 0 | 0 | 0 | 0 | [9 empty] | 1200
[7 empty] | 900*900 |  |  |  | 900High
[7 empty] | 1050 dia |  |  |  | 900 high
[7 empty] | 1200x1200 |  |  |  | 1200 High
[6 empty] | 1st Order | 1500x1500 |  |  |  | 1200 High | [11 empty] | 1st Order | 600*600 | [14 empty] | 1st Order | 600*600
[7 empty] | 2100 |  |  |  | 900 high | [12 empty] | 900*600 | [15 empty] | 900*600
[7 empty] | 2100 |  |  |  | 600 High | [12 empty] | 1050 | [15 empty] | 1050
[7 empty] | 2100 |  |  |  | 300 High
0.2R 1.2*1.2
[10 empty] | Pit Bases |  | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser
[6 empty] | TOTAL | 900*600 |  |  |  | 600High
[7 empty] | 900*600 |  |  |  | 900High | 0 | 0 | 0 | 0
[7 empty] | 1050Dia |  |  |  |  | 0 | 0 | 1 | 0
[7 empty] | 1200Dia |  |  |  |  | 0 | 0 | 0 | 0
[7 empty] | 1200 Pit | In lieu of 1050&1200Ch |  |  | 1200High |  |  | 1 | 0
Grates/Covers
[6 empty] | TOTAL | 450x450 |  | 0 | heel safe grate cover |  | CL D, Hinged, Galv, Bolt Down.
[7 empty] | 600x600 |  | 0 | heel safe grate cover |  | CL D, Hinged, Galv, Bolt Down.
[7 empty] | 600X600 |  | 0 | Grate &Frame |  | CL D, Cast Iron
[7 empty] | 600x900 |  |  | heel safe grate cover |  | CL D, Hinged, Galv, Bolt Down.
[7 empty] | 600x900 |  | 0 | Grate &Frame |  | CL D, Hinged, Galv, Bolt Down.
[7 empty] | 900X900 |  | 0 | Grate &Frame |  | CL D, Hinged, Galv, Bolt Down.
[7 empty] | 900X600 |  | 0 | 900x600 cast Iron lid and concret around |  | CL D, Cast Iron
[7 empty] | 1050*6*9 |  | 0 | Aspro |  | 150Thick, 900*600 Opening
[7 empty] | 1200x900 |  |  | Grate & Frame |  | CL D, Hinged, Galv, Bolt Down.
[7 empty] | 1200*1200 overflow pit |  |  | Grate & Frame |  | CL D, Hinged, Galv, Bolt Down.
900x900 Class D hinged grate and frame with a concrete surroun
[10 empty] | 2.4m lintel |  | 3.6m SAG centre inlet, Kerb in line
Headwall (250mm pipe )
headwall(600mm pipe )
Twin Pipe Headwall ( 300mm /225mm pipe )
[10 empty] | Head Wall |  | Precast - 450RCP Inlet
[10 empty] | Pit Bases |  | 0.15 Riser | 0.3 Riser | 0.6 Riser | 0.9 Riser
[6 empty] | 1st PIT Order | 600*600 |  |  |  | 600High
[7 empty] | 900*900 |  |  |  | 900High
[7 empty] | 900*600 |  |  |  | 600High
[7 empty] | 900*600 |  |  |  | 900High
[7 empty] | 1050 |  |  |  | 0High
Grates/Covers
[6 empty] | 1St GRATE Order | 600*600 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down.
[7 empty] | 600*600 |  |  | Grate & Frame |  | CL B, Galv, Bolt Down.
[7 empty] | 600*600 |  |  | Cover & Frm - INFILL |  | CL B, Galv, Bolt Down.
[7 empty] | 600*600 |  |  | V-Grate w/conc surround |  | CL B, Galv
[7 empty] | 900*600 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down.
[7 empty] | 900*600 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down - HEEL GUARD
[7 empty] | 900*900 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down - HEEL GUARD
[7 empty] | 1050*6*9 |  |  | Aspro |  | 150Thick, 900*600 Opening
Grates/Covers
[6 empty] | 2nd GRATE Order | 600*600 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down.
[7 empty] | 600*600 |  |  | Grate & Frame |  | CL B, Galv, Bolt Down.
[7 empty] | 600*600 |  |  | Cover & Frm - INFILL |  | CL B, Galv, Bolt Down.
[7 empty] | 600*600 |  |  | V-Grate w/conc surround |  | CL B, Galv
[7 empty] | 900*600 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down.
[7 empty] | 900*600 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down - HEEL GUARD
[7 empty] | 900*900 |  |  | Grate & Frame |  | CL D, Galv, Bolt Down - HEEL GUARD
[7 empty] | 1050*6*9 |  |  | Aspro |  | 150Thick, 900*600 Opening

## SW_insitu Takeoff
PIT/MANHOLE TAKEOFF
DESCRIPTION | Design Depth | Grate/Finish | Aspro | Total Chamber Height | Chamber Concrete volume/m3 | Base Concrete volume/m3 | Total Concrete volume/m3 |  | Dia | Area of circle
[7 empty] | 0 |  | 2.1 | 3.4636 | m2
[9 empty] | 2.6 | 5.3093 | m2
[10 empty] | 0 | m2
[10 empty] | 0 | m2
[9 empty] | 32 | MPA | 290 | $/m3
0
[7 empty] | 0 | m3 | 0

## Program
Project Program |  |  | MONTH 1 | [27 empty] | MONTH 2 | [27 empty] | MONTH 3 | [27 empty] | MONTH 4 | [27 empty] | MONTH 5
|  |  | Week 1 / SEPT | [6 empty] | Week 2 / SEPT | [6 empty] | Week 3 / SEPT | [6 empty] | Week 4 / SEPT | [6 empty] | Week 5 / OCT | [6 empty] | Week 6 / OCT | [6 empty] | Week 7 / OCT | [6 empty] | Week 8 / OCT | [6 empty] | Week 9 / NOV | [6 empty] | Week 10 / NOV | [6 empty] | Week 11 / NOV | [6 empty] | Week 12 / NOV | [6 empty] | Week 13 / NOV-DEC | [6 empty] | Week 14 / DEC | [6 empty] | Week 15 / DEC | [6 empty] | Week 16 / NOV | [6 empty] | Week 17 / NOV-DEC
|  |  | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su
|  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Contract Execution, Contract Insurances and Exchanges
Design Assessment, Coordination, Shop Drawings etc_For Construction
Site Inductions
Mobilsation | BUILDERS Proj DURATION:
TEMPS
Materials Store, Area establishment, signage and controls
Road 5 | 670LM - 2 Tees - Serving 20 Lots
Road 6 | 100LM - Serving 5 Lots
Road 7 | 500LM - Serving 19 Lots
Live Connection #1
Live Connection #2
Contract Completion
Commissioning
As-Built
O+M Manuals
Pratical Completion
Site Demobilisation
Staff Count
| TRADESMAN_LEADING HAND |  | Week 17 / NOV-DEC Su 31: 0
CREW - Fire & WAT | bar: Week 1 / SEPT M 4 to Week 1 / SEPT Sa 9; Week 2 / SEPT M 11 to Week 2 / SEPT Sa 16; Week 3 / SEPT M 18 to Week 3 / SEPT Sa 23; Week 4 / SEPT M 25 to Week 4 / SEPT Sa 30; Week 5 / OCT M 2 to Week 5 / OCT Sa 7; Week 6 / OCT M 9 to Week 6 / OCT Sa 14; Week 7 / OCT M 16 to Week 7 / OCT Sa 21; Week 8 / OCT M 23 to Week 8 / OCT Sa 28; Week 9 / NOV M 30 to Week 9 / NOV Sa 4; Week 10 / NOV M 6 to Week 10 / NOV Sa 11; Week 11 / NOV M 13 to Week 11 / NOV Sa 18; Week 12 / NOV M 20 to Week 12 / NOV Sa 25; Week 13 / NOV-DEC M 27 to Week 13 / NOV-DEC Sa 2; Week 14 / DEC M 4 to Week 14 / DEC Sa 9; Week 15 / DEC M 11 to Week 15 / DEC Sa 16; Week 16 / NOV M 18 to Week 16 / NOV Sa 23; Week 17 / NOV-DEC M 25 to Week 17 / NOV-DEC Sa 30
CREW - Drainage | bar: Week 1 / SEPT M 4 to Week 1 / SEPT Sa 9; Week 2 / SEPT M 11 to Week 2 / SEPT Sa 16; Week 3 / SEPT M 18 to Week 3 / SEPT Sa 23; Week 4 / SEPT M 25 to Week 4 / SEPT Sa 30; Week 5 / OCT M 2 to Week 5 / OCT Sa 7; Week 6 / OCT M 9 to Week 6 / OCT Sa 14; Week 7 / OCT M 16 to Week 7 / OCT Sa 21; Week 8 / OCT M 23 to Week 8 / OCT Sa 28; Week 9 / NOV M 30 to Week 9 / NOV Sa 4; Week 10 / NOV M 6 to Week 10 / NOV Sa 11; Week 11 / NOV M 13 to Week 11 / NOV Sa 18; Week 12 / NOV M 20 to Week 12 / NOV Sa 25; Week 13 / NOV-DEC M 27 to Week 13 / NOV-DEC Sa 2; Week 14 / DEC M 4 to Week 14 / DEC Sa 9; Week 15 / DEC M 11 to Week 15 / DEC Sa 16; Week 16 / NOV M 18 to Week 16 / NOV Sa 23; Week 17 / NOV-DEC M 25 to Week 17 / NOV-DEC Sa 30
CREW #3 | bar: Week 1 / SEPT M 4 to Week 1 / SEPT Sa 9; Week 2 / SEPT M 11 to Week 2 / SEPT Sa 16; Week 3 / SEPT M 18 to Week 3 / SEPT Sa 23; Week 4 / SEPT M 25 to Week 4 / SEPT Sa 30; Week 5 / OCT M 2 to Week 5 / OCT Sa 7; Week 6 / OCT M 9 to Week 6 / OCT Sa 14; Week 7 / OCT M 16 to Week 7 / OCT Sa 21; Week 8 / OCT M 23 to Week 8 / OCT Sa 28; Week 9 / NOV M 30 to Week 9 / NOV Sa 4; Week 10 / NOV M 6 to Week 10 / NOV Sa 11; Week 11 / NOV M 13 to Week 11 / NOV Sa 18; Week 12 / NOV M 20 to Week 12 / NOV Sa 25; Week 13 / NOV-DEC M 27 to Week 13 / NOV-DEC Sa 2; Week 14 / DEC M 4 to Week 14 / DEC Sa 9; Week 15 / DEC M 11 to Week 15 / DEC Sa 16; Week 16 / NOV M 18 to Week 16 / NOV Sa 23; Week 17 / NOV-DEC M 25 to Week 17 / NOV-DEC Sa 30
T/A & Apprentice | bar: Week 1 / SEPT M 4 to Week 1 / SEPT Sa 9; Week 2 / SEPT M 11 to Week 2 / SEPT Sa 16; Week 3 / SEPT M 18 to Week 3 / SEPT Sa 23; Week 4 / SEPT M 25 to Week 4 / SEPT Sa 30; Week 5 / OCT M 2 to Week 5 / OCT Sa 7; Week 6 / OCT M 9 to Week 6 / OCT Sa 14; Week 7 / OCT M 16 to Week 7 / OCT Sa 21; Week 8 / OCT M 23 to Week 8 / OCT Sa 28; Week 9 / NOV M 30 to Week 9 / NOV Sa 4; Week 10 / NOV M 6 to Week 10 / NOV Sa 11; Week 11 / NOV M 13 to Week 11 / NOV Sa 18; Week 12 / NOV M 20 to Week 12 / NOV Sa 25; Week 13 / NOV-DEC M 27 to Week 13 / NOV-DEC Sa 2; Week 14 / DEC M 4 to Week 14 / DEC Sa 9; Week 15 / DEC M 11 to Week 15 / DEC Sa 16; Week 16 / NOV M 18 to Week 16 / NOV Sa 23; Week 17 / NOV-DEC M 25 to Week 17 / NOV-DEC Sa 30
TRADESMAN.1 | bar: Week 1 / SEPT M 4 to Week 1 / SEPT Sa 9; Week 2 / SEPT M 11 to Week 2 / SEPT Sa 16; Week 3 / SEPT M 18 to Week 3 / SEPT Sa 23; Week 4 / SEPT M 25 to Week 4 / SEPT Sa 30; Week 5 / OCT M 2 to Week 5 / OCT Sa 7; Week 6 / OCT M 9 to Week 6 / OCT Sa 14; Week 7 / OCT M 16 to Week 7 / OCT Sa 21; Week 8 / OCT M 23 to Week 8 / OCT Sa 28; Week 9 / NOV M 30 to Week 9 / NOV Sa 4; Week 10 / NOV M 6 to Week 10 / NOV Sa 11; Week 11 / NOV M 13 to Week 11 / NOV Sa 18; Week 12 / NOV M 20 to Week 12 / NOV Sa 25; Week 13 / NOV-DEC M 27 to Week 13 / NOV-DEC Sa 2; Week 14 / DEC M 4 to Week 14 / DEC Sa 9; Week 15 / DEC M 11 to Week 15 / DEC Sa 16; Week 16 / NOV M 18 to Week 16 / NOV Sa 23; Week 17 / NOV-DEC M 25 to Week 17 / NOV-DEC Sa 30
TRADESMAN.2 | bar: Week 1 / SEPT M 4 to Week 1 / SEPT Sa 9; Week 2 / SEPT M 11 to Week 2 / SEPT Sa 16; Week 3 / SEPT M 18 to Week 3 / SEPT Sa 23; Week 4 / SEPT M 25 to Week 4 / SEPT Sa 30; Week 5 / OCT M 2 to Week 5 / OCT Sa 7; Week 6 / OCT M 9 to Week 6 / OCT Sa 14; Week 7 / OCT M 16 to Week 7 / OCT Sa 21; Week 8 / OCT M 23 to Week 8 / OCT Sa 28; Week 9 / NOV M 30 to Week 9 / NOV Sa 4; Week 10 / NOV M 6 to Week 10 / NOV Sa 11; Week 11 / NOV M 13 to Week 11 / NOV Sa 18; Week 12 / NOV M 20 to Week 12 / NOV Sa 25; Week 13 / NOV-DEC M 27 to Week 13 / NOV-DEC Sa 2; Week 14 / DEC M 4 to Week 14 / DEC Sa 9; Week 15 / DEC M 11 to Week 15 / DEC Sa 16; Week 16 / NOV M 18 to Week 16 / NOV Sa 23; Week 17 / NOV-DEC M 25 to Week 17 / NOV-DEC Sa 30
| Qty Staff On Site |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Days - LEAD HAND - PRELIM | 0
Hyd allow **
Civil SW allow **
| Total Days - CREW - FIRE_WAT | 0
| Total - CREW "Drainage" | 0
HYD - CREW "Drainage"
Civil SW - CREW "Drainage"
Total Days CREW 3
| Total Days - TA | 0
| Total Days - Tradesman.1 | 0
Hyd - Tradesman.1
Civil SW - Tradesman.1
Total Days - Tradesman.2
Hyd - Tradesman.2
Civil SW - Tradesman.2

## Staff Rates
Project:
Tricore -
Stage 1 Version 1
Item
BASED ON:
| 6 - Day Week, 10Hr Day |  |  |  | 2023 Staff Cost increase | Project total cost | Difference
| Working Days/Month | 24 |  |  | Current
| No-Work Days/Month | 4 |  |  | 2.5% | 0 | 0
| Avrg Hours / Day | 8.75 |  |  | 5% | 0 | 0
| Avrg Days / Week | 6 |  |  | 7.5% | 0 | 0
| Avrg Hours / Month | 210 |  |  | 10% | 0 | 0
| STAFF |  |  |  |  | Hourly Rate + 2.5% | Hourly Rate + 5% | Hourly Rate + 7.5% | Hourly Rate + 10%
|  | Unit | REQ | Cost ex GST | Total ex GST
| TRADESMAN_LEADING HAND | HR | 1 | 94 | 94 | 96.35 | 98.7 | 101.05 | 103.4
|  | DAY | 1 | 822.5 | 822.5 | 843.0625 | 863.625 | 884.1875 | 904.75
| TRADESMAN_LEADING HAND | WEEK | 1 | 4935 | 4935 | 5058.375 | 5181.75 | 5305.125 | 5428.5
|  | MONTH | 1 | 19740 | 19740 | 20233.5 | 20727 | 21220.5 | 21714
| QTY Staff in Crew | 1
| Crew #1 | HR | 1 | 254 | 254 | 260.35 | 266.7 | 273.05 | 279.4
|  | DAY | 1 | 2222.5 | 2222.5 | 2278.0625 | 2333.625 | 2389.1875 | 2444.75
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 13335 | 13335 | 13668.375 | 14001.75 | 14335.125 | 14668.5
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 53340 | 53340 | 54673.5 | 56007 | 57340.5 | 58674
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #2 | HR | 1 | 254 | 254 | 260.35 | 266.7 | 273.05 | 279.4
|  | DAY | 1 | 2222.5 | 2222.5 | 2278.0625 | 2333.625 | 2389.1875 | 2444.75
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 13335 | 13335 | 13668.375 | 14001.75 | 14335.125 | 14668.5
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 53340 | 53340 | 54673.5 | 56007 | 57340.5 | 58674
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #3 | HR | 1 | 254 | 254 | 260.35 | 266.7 | 273.05 | 279.4
|  | DAY | 1 | 2222.5 | 2222.5 | 2278.0625 | 2333.625 | 2389.1875 | 2444.75
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 13335 | 13335 | 13668.375 | 14001.75 | 14335.125 | 14668.5
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 53340 | 53340 | 54673.5 | 56007 | 57340.5 | 58674
T/A & Apprentice
| QTY Staff in Crew | 3
| TRADESMAN_PLUMBER_OPERATOR | HR | 1 | 92 | 92 | 94.3 | 96.6 | 98.9 | 101.2
|  | DAY | 1 | 805 | 805 | 825.125 | 845.25 | 865.375 | 885.5
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 4830 | 4830 | 4950.75 | 5071.5 | 5192.25 | 5313
|  | MONTH | 1 | 19320 | 19320 | 19803 | 20286 | 20769 | 21252
| QTY Staff in Crew | 1
| T/A & Apprentice | HR | 1 | 70 | 70 | 71.75 | 73.5 | 75.25 | 77
|  | DAY | 1 | 612.5 | 612.5 | 627.8125 | 643.125 | 658.4375 | 673.75
| T/A & Apprentice | WEEK | 1 | 3675 | 3675 | 3766.875 | 3858.75 | 3950.625 | 4042.5
|  | MONTH | 1 | 14700 | 14700 | 15067.5 | 15435 | 15802.5 | 16170
| QTY Staff in Crew | 1

## Equip&HIRE
|  | TCS PROJECT USE |  | CAT Rental (ROK) |  | COATES (ROK) |  | ONSITE
DESCRIPTION | QTY | WEEKLY (5 day) | COMMENTS | WEEKLY (5 day) | COMMENTS | WEEKLY (5 day) | COMMENTS | DAILY | WEEKLY (5 day) | COMMENTS
Skid Steer Loader_Tracked | 0 | 0 |  | 0 |  | 0 |  | 0 | 262
Skid Steer Loader_Wheeled | 0 | 300 | 0 | 250 |  | 192 |  | 0 | 0
4.5-6Ton_Excavator | 0 | 200 |  | 0 |  | 0 |  | 0 | 0
8Ton_Excavator | 0 | 250 | 0 | 0 |  | 0 |  | 0 | 0
10-12Ton_Excavator | 0 | 310 | 0 | 310 | 13T | 301 | 12T | 0 | 300 | 13T
14-16Ton_Excavator | 0 | 440 | 0 | 370 | 17T | 375 | 14T | 0 | 295 | 14T
20-24Ton_Excavator | 0 | 450 | 0 | 480 | 25T | 417 | 20T | 0 | 444 | 20T
Ripper_10-12T | 0 | 26 |  | 0 |  | 25.7 |  | 0 | 0
Ripper_14-16T | 0 | 26 |  | 0 |  | 25.7 |  | 0 | 21
Ripper_20-24T | 0 | 30 |  | 0 |  | 30.1 |  | 0 | 23
Breaker_10-12T | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
Auger Drive_10-12T | 0 | 115 | 0 | 0 |  | 0 |  | 0 | 0
300Dia Auger Drill | 0 | 50 |  | 0 |  | 0 |  | 0 | 0
2-4T_Tipper Truck | 0 | 180 | 0 | 0 |  | 180 | 2-3T | 0 | 130 | 2-3T
6-12T_Tipper Truck | 0 | 400 | 0 | 0 |  | 238 | 6T | 0 | 0
<10T_Articulated Site Tipper | 0 | 341 | 0 | 0 |  | 243 | 9T | 0 | 0
Upright Rammer_Wacker | 0 | 50 | 0 | 0 |  | 48 |  | 0 | 46
Trench Roller_Dbl Drum_Remote | 0 | 180 | 0 | 0 |  | 121 |  | 0 | 98 | Rller - padfot?
<26Ft_Scissor Lift - Diesel | 0 | 150 | 0 | 0 |  | 89 |  | 0 | 112
<26Ft_Scissor Lift - Elec | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
<34Ft_Boom Lift - Diesel | 0 | 150 | 0 | 0 |  | 96 |  | 0 | 140
<34Ft_Boom Lift - Elec | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Porta Loo_No Tank | 0 | 5 | 0 | 0 |  | 5 |  | 0 | 7.5
3.6*3m Demantable Office | 0 | 0 | 0 | 0 |  | 15 | 42D Min. | 0 | 13
20Ft Shipping Container | 0 | 5 | 0 | 0 |  | 4 | 42D Min. | 0 | 0
Quick Cut Demo Saw | 0 | 0 | 0 | 0 |  | 100 |  | 0 | 50
Sngl Ph_6KVA Genset | 0 | 50 | 0 | 0 |  | 45 |  | 0 | 35
Diesel Air Compressor_Trailer | 0 | 0 | 0 | 0 |  | 73 |  | 0 | 68
Air Breaker - Heavy | 0 | 0 | 0 | 0 |  | 34 |  | 0 | 0
Air Hose <10m | 0 | 0 | 0 | 0 |  | 9 |  | 0 | 1.2
Elec Breaker/Jachammer | 0 | 0 | 0 | 0 |  | 45 |  | 0 | 0
Flexdrive Motor Unit | 0 | 0 | 0 | 0 |  | 25 |  | 0 | 27
Flexdrive_Pump Shaft | 0 | 0 | 0 | 0 |  | 30 |  | 0 | 22
Temporary Power Board | 0 | 25 | 0 | 0 |  | 30 |  | 0 | 17
Dual CabUte | 0 | 125 | 0 | 0 |  | 0 |  | 0 | 0
10m3_Skip Bin | 0 | 40 | 0 | 0 |  | 0 |  | 0 | 0
Vac Truck / HR | 0 | 200 | 0 | 0 |  | 0 |  | 0 | 0
| 0 | 0 |  | 0 |  | 0 |  | 0 | 0
| 0 | 0 |  | 0 |  | 0 |  | 0 | 0
TRANSPORT_Ex BRIS - Return | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
TRANSPORT_Ex ROK - Return | 0 | 0 |  | 0 |  | 480 | 22T | 0 | 0 | 0

## Civil Rate BOQ
Adress |  |  | Contract
ROADWORKS AND CIVIL SERVICES
BILL OF QUANTITIES |  |  | Date
SUMMARY
1 | TOTAL PART A - PRELIMS, SITE ESTABLISHMENT, E&S Controls & PREPARATIONS |  |  |  | 0
2 | TOTAL PART B - EARTHWORKS |  |  |  | 0
3 | TOTAL PART C - ROADWORKS |  |  |  | 0
4 | TOTAL PART D - STORMWATER DRAINAGE |  |  |  | 25129.8652
5 | TOTAL PART E - POTABLE WATER RETICULATION |  |  |  | 0
6 | TOTAL PART F - SEWERAGE RETICULATION (RIGS) |  |  |  | 0
7 | TOTAL PART G - STORMWATER TREATMENT |  |  |  | 0
8 | TOTAL PART H - ELECTRICAL & COMMUNICATIONS |  |  |  | 0
9 | TOTAL PART I - INTERNAL PLUMBING |  |  |  | 0
9 | SUB-TOTAL: |  |  |  | 25129.8652
14 | COMBINED QLEAVE LEVY AND WORKPLACE HEALTH AND SAFETY FEE |  |  |  | (By Principal) |  |  | 4188.3109
ITEM DESCRIPTION |  | QTY UNIT |  |  | Rate |  | Amount
PART A - SITE ESTABLISHMENT AND PREPARATION
1. Site establishment including mobilisation of plant and personnel. |  |  |  | Item | 6081.91 |  | 0
1. Site DeMob & Clean |  |  |  | Item | 3100 |  | 0
2. Supply and erect approved 1200mm x 900mm project Notice |  |  |  | Item | 364.91 |  | 0
board to Local Authority requirements.
3. Provision for traffic, including installation of temporary warning |  |  |  | Item | 1450 |  | 0
devices and/or traffic controllers and /or traffic controllers and
maintenance of access for site traffic, in accordance with approved
Traffic Management Plan (to be organised by contractor)
4. Allowance for service location and potholing as required to |  |  |  | Item | 1715.1 |  | 0
confirm existing services and protect infrastructure throughout
construction.
5. Supply all materials, construct, maintain and remove on |  |  |  | Item | 5850 |  | 0
completion of works the erosion and sediment control measures as
detailed. Note that the Contractor must engage their own CPESC for
ongoing management of ESC Control measures on site.
6.Clearing and grubbing, including removal of trees and grasses, |  |  |  | Item | 650 |  | 0
existing fences, rubbish and debris from all work areas, including
mulching of trees & vegetation or removal from site as directed.
7. Provision of Level 4 Arborist for attendance at pre-start meeting |  |  |  | Item | 6252.2
and during cleaning operations.
8. Implementation of approved Vegetation Management Plan |  |  |  | Item | 4378.97 |  | 0
procedures, including supply and establishent of temporary fencing
for protection of identified trees, vegetation to be preserved &
management of mulch stockpiles.
9. Provision for obtaining EPA resuce permit and for payment to |  |  |  | Item |  |  | By Client
accredited wildlife spotter / catched for attendance during clearing
and grubbing operations, in accordance with approved Fauna
Management Plan requirements.
10.Condition of adjacent buildings and structures, carried out by |  |  |  | Item | 2432.76 |  | 0
accredited personnel prior to construction. - DELAP REPORT
SURVEY |  |  |  | Item | 11200 |  | 0
Construciton Management Plan |  |  |  | Item | 1020 |  | 0
Geotech Report |  |  |  | Item | 1888 |  | 0
Skip Bin & Rubbish |  |  |  | Item | 650 |  | 0
TOTAL PART A: | [6 empty] | 0
(Carried forward to Summary)
PART B - EARTHWORKS
1. Strip, stockpile and replace topsoil to allotments, verge and
verge and batters including final trim and soil amendment (100mm
nominal depth).
(a) Strip to stockpiles. |  |  |  | cu.m.
(d) Respread topsoil from stockpiles |  |  |  | cu.m.
(c) Removal of excess topsoil offsite. |  |  |  | cu.m.
3. Earthworks in all materials including compaction, trimming and
testing (by RPEQ Geotechnical Engineer) as specified:
(a) On leads from site excavations to structural filling. (Nett cut) |  |  |  | cu.m. | 14.52 |  | 0
(b) Import of acceptable fill material to site (to LCC Requirements) |  |  |  | cu.m. | 22.56 |  | 0
inclusive of compaction factor (compacted fill in place).
(c) Trench Spoil (including stormwater, sewer, water & |  |  |  | cu.m. | 13.74 |  | 0
electrical) to structural fill (Provisional)
(d) Excavation of unsuitable material below ground surface or |  | 0 |  | cu.m. | 33.92 |  | 0
road subgrade , including removal to nonstructural areas and
replacement with compacted,approved site material. (Provisional)
Strip Topsoil |  |  |  | cu.m. | 9.6 |  | 0
Remove Topsoil |  |  |  | cu.m. | 6 |  | 0
Cut-Fill |  |  |  | cu.m. | 15.8 |  | 0
Remove Trees_onsite |  |  |  | Item | 600 |  | 0
Remove Spoil From site |  |  |  | cu.m. | 31 |  | 0
4 Extra/over Item 3 for excavation of general earthworks in rock by |  |  |  | cu.m. | 25 |  | 0
excavator larger than 148kW (Provisional).
5. Level 1 testing carried out by a NATA-accredited |  |  |  | Lump Sum | 3100 |  | 0
testing authority, including certification by an approved
geotechnical engineer and Registered Professional
Engineer Queensland (RPEQ), carried out in
accordance with AS3798, including relative
compaction testing carried out in accordance with
AS1289 Series 5.
6. Global stability analysis and certification, carried out on the |  |  |  | Item | 3649.14 |  | 0
completed earthworks and retaining walls by the Contractor's
geotechnical engineer and Registered Professional Engineer
Queensland (RPEQ).
7. Allowance for site inspections by Principal's geotechnical |  |  |  | PC Item
consultant, only if ordered by Superintendent. (Provisional)
8. Grass seeding to the following areas: |  |  |  | ha | 1946.21 |  | 0
(a) Allotments
(b) Extra/over - Supply and apply Vital Chemical spray or |  |  |  | ha | 5589.01 |  | 0
equivalent approved product (Provisional)
9. Provide detailed design, supply all materials and construct the
following precast concrete sleeper retaining wall system complete,
including all components, additional excavation as required,
drainage layer, connection of aggregate drains to stormwater system,
approved backfilling, temporary safety fencing during construction,
provision of structural design and supervision certificate by
Registered Professional Engineer, Queensland and supply of testing
results to Superintendent certifying compliance (Work by specialist
retaining wall subcontractor):
(Note: Retaining wall quantities scheduled are based on square
metres of exposed face area).
(a) Single tier sleeper walls 1600mm maximum exposed hieght |  |  |  | sq.m | 382.54 |  | 0
(b) Single tier sleeper walls 1600 - 2400mm maximum exposed |  |  |  | sq.m | 485.89 |  | 0
height.
(c) Fence Brackets |  |  |  | Lump Sum
10. Provide detailed design, supply all materials and construct the
following blockwork retaining wall system complete, including
all components, additional excavation as required, drainage layer,
connection of aggregate drains to stormwater system, approved
backfilling, temporary safety fencing during construction, provision
of structural design and supervision certificate by Registered
Professional Engineer, Queensland and supply of testing results
to Superintendent certifying compliance (Work by specialist
retaining wall sub-contractor):
(Note: Retaining wall quantities scheduled are based on square
metres of exposed face area).
(a) Single tier block walls up to 2000mm maximum exposed height |  |  |  | sq.m | 783.81 |  | 0
(b) Single tier block walls 2000 - 3000mm exposed height |  |  |  | sq.m | 1174.92 |  | 0
(c) Extra/over select waterproofing application to external face |  |  |  | Item | 3649.14 |  | 0
of blockwork wall to 1% AEP Flood Level (14.6m AHD).
(d) Fence Brackets |  |  |  | Lump Sum |  |  | Rate Only
11. Allowance for 3rd party RPEQ review of the retaining wall |  |  |  | Item | 2189.49
designs and provide review certificate.
12. Provision of "as constructed" survey by Principal's icensed |  |  |  | Item |  |  | By others
surveyor of finished allotment profiles, retaining walls, roadway profiles, stormwater
profiles, stormwater drainage and bio-basin areas, sewerage and
water reticulation to Council requirements.
9. Provide detailed design, supply all materials and construct the
following precast concrete sleeper retaining wall system complete,
including all components, additional excavation as required,
drainage layer, connection of aggregate drains to stormwater system,
approved backfilling, temporary safety fencing during construction,
provision of structural design and supervision certificate by
Registered Professional Engineer, Queensland and supply of testing
results to Superintendent certifying compliance (Work by specialist
retaining wall subcontractor):
(Note: Retaining wall quantities scheduled are based on square
metres of exposed face area).
(a) Single tier sleeper walls 1600mm maximum exposed hieght |  |  |  | sq.m | 382.54 |  | 0
(b) Single tier sleeper walls 1600 - 2400mm maximum exposed |  |  |  | sq.m | 485.89 |  | 0
height.
(c) Fence Brackets |  |  |  | Lump Sum
TOTAL PART B: | [6 empty] | 0
(Carried forward to Summary)
PART C - ROADWORKS / Pavement
1. Supply all materials, excavate for, and construct sub-soils |  |  |  | lin.m. | 46 |  | 0
drains including cleanout points, outlet and backfilling.
2. Trim pavement subgrade including compaction, proofrolling and |  |  |  | sq.m. | 6.93 |  | 0
testing.
4. inal trim pavement base including compaction, proofrolling |  |  |  | sq.m. | 7.8 |  | 0
and testing.
5. Supply, spread and compact the following gravel pavement
including testing:
(a) Type 2.1 base course 150mm (CBR80) |  |  |  | cu.m. | 203.14 |  | 0
(b) Type 2.3 Sub-Base Course 150mm (CBR45) |  |  |  | cu.m. | 192.49 |  | 0
(c) Type 2.5 Lower Sub-base Course (CBR15) |  |  |  | cu.m.
(d) Class 3 imported subgrade replacement material (CBR15) |  |  |  | cu.m. | 177.62 |  | 0
including additional excavation and disposal of excavated of excavated materials if ordered 300mm (Provisional)
materials if ordered 300mm (Provisional)
6. Supply all materials and construct the following cast-insitu
concrete edge sections, complete including 75mm minimum
gravel bedding and all tapers and transitions:
(a) Mountable Kerb 'M3' |  |  |  | lin.m. | 53.3 |  | 0
(b) Edge Restraint 'ER2 |  |  |  | lin.m. | 81.32 |  | 0
7. Supply all materials and construct reinforced concrete driveways
as detailed including bedding, jointing, kerb transitions, blinding
layer and finish including vehicular crossover at kerb in accordance
with Logan City Council Standards:
(a) Driveway for Lot 7 detail refer drawing BE210215-01-C350 for |  |  |  | sq.m. | 155 |  | 0
details
(b) Modified driveway for Lots 15, 16 and Basin detail refer drawing |  |  |  | sq.m. | 159.05 |  | 0
BE210215-01-C451 for details.
Crossover |  |  |  | No. | 4300 |  | 0
Bedding Sand |  |  |  | cu.m. | 170 |  | 0
Testing |  |  |  | No. | 3400 |  | 0
Road Patch |  |  |  | No. | 2000 |  | 0
Kerb Patch |  |  |  | No. | 1301 |  | 0
8. Supply materials and install approved full-height metal roofwater
kerb adapters during kerb and channel construction (minimum 2
per Lot) and associated stormwater pipe construction including:
(a) Approved full-height metal roofwater kerb adaptors during kerb |  |  |  | No. | 69.93 |  | 0
and channel construction .
(b) Roof water pipe under concrete footpath (100mm) |  |  |  | lin.m. | 94.27 |  | 0
(c) Roof water pipe under concrete footpath (150mm) to all |  |  |  | lin.m. | 143.13 |  | 0
nominated pits.
9. Supply all materials and construct the following standard
reinforced concrete pathway, including excavation and restoration
of surfaces.
(a) 1200mm nominal width (Refer Standard Drawing IPWEAQ RS-065) |  |  |  | sq.m. | 122.03 |  | 0
IPWEAQ RS-065)
(b) Kerb ramps (Refer Standard Drawing IPWEAQ RS-065) |  |  |  | No. | 721.22 |  | 0
10. Supply all materials and construct bin collector pad including |  |  |  | No. | 677.25 |  | 0
excavation, restoration of surfaces as detailed on the approved
plans.
11. Supply all materials and construct the following asphalt
surfacing, including prime coat, seal and testing for:
(a) AC10 - 35mm compacted thickness. |  |  |  | sq.m. | 36.14 |  | 0
12. Supply materials for and action linemarking as per the |  |  |  | Item | 1824.57 |  | 0
approved plans.
13. Supply and install all signs including:
(a) Street sign |  |  |  | No. | 344.48 |  | 0
(b) R1-2A Giveway sign |  |  |  | No. | 474.39 |  | 0
(c) D4-5 Obstruction marker |  |  |  | No. | 656.85 |  | 0
(d) Timber bollards with reflective tape to road ends |  |  |  | Item | 3709.96 |  | 0
(Refer Landscape Architect Documentation)
Allow for demolishing and replacing existing crossover |  |  |  | No. |  |  | 0
14. Supply all materials, excavate for, bed, lay, joint and backfill |  |  |  | lin.m. | 72.7 |  | 0
100mm dia. UPVC PN9 water service road crossing conduits |  |  |  | lin.m. | 40 |  | 0
complete including marker discs on kerb and testing of backfill
compaction.
15. Turfing to Road Verge - Full width of verge |  |  |  | sq.m | 11 |  | 0
16. Decommission and remove of existing VXO and driveways |  |  |  | Item | 7711.86 |  | 0
on Chambers Flat Road and reinstate the verge with turf & kerb
and channel to existing conditions.
TOTAL PART C: | [6 empty] | 0
(Carried forward to Summary)
PART D - STORMWATER DRAINAGE
1. Supply and install all materials, clearing and grubbing, excavate
for, bed, lay, joint and backfill the following drainage lines and box
culverts, including jointing materials, approved bedding,backfill,
approved backfill under roads, testing of backfill compaction,
disposal of surplus materials off site and restoration of surfaces:
a) Steel-reinforced concrete stormwater drainage pipes:
(i) 375mm dia. Class 2 (RRJ) |  |  |  | lin.m. | 188.15 |  | 0
(ii) 375mm Class 4 RCP |  | 10.04 |  | lin.m. | 269.38 |  | 2704.5752
(b) SN8 PVC stormwater drainage pipes
(i)150mm Class SN8 UPVC |  | 10 |  | lin.m. | 148.21 |  | 1482.1
(ii) PIPE Ribbed RRJ 225MM |  |  |  | lin.m. | 160.93 |  | 0
(iii) 300mm Class SN8 PVC |  |  |  | lin.m. | 170 |  | 0
(iii) PIPE Ribbed RRJ 375MM |  |  |  | lin.m. |  |  | 0
PIPE Ribbed RRJ 375MM |  | 199.73 |  | lin.m. |  |  | 0
PIPE Ribbed RRJ 450MM |  | 135.16 |  | lin.m. |  |  | 0
PIPE Ribbed RRJ 525MM |  | 32.59 |  | lin.m. |  |  | 0
PIPE Ribbed RRJ 600MM |  | 49.64 |  | lin.m. |  |  | 0
PIPE Ribbed RRJ 750MM |  |  |  | lin.m. |  |  | 0
373 PP SN8 |  | 9.43 |  | lin.m. |  |  | 0
2. Extra/over Item 1 for removal of unsuitable foundation |  |  |  | cu.m.
material to stormwater lines and replacement with
approved material (Provisional)
3. Extra over for CBR15 backfill where pipes are located under roads |  |  |  | Item | 1571.96 |  | 0
or trafficable areas
4. Extra/over Item 1 for excavation of rock in stormwater trenches
as follows (Provisional):
(a) By excavator larger than 148kW. |  |  |  | cu.m. | 25 |  | 0
(b) By jackhammer. |  |  |  | cu.m. | 180 |  | 0
5. Supply all materials and construct reinforced concrete
headwalls to suit the following sized drainage lines, including
pedestrain safety fence & dumped rock surround as per detail:
(a) Twin 375mm Dia. |  |  |  | No. | 3649.15 |  | 0
6. Supply all materials, excavate for, and construct the following
concrete stormwater inlet structures including reinforcement if
requried (all depths) complete:
(a) Single gully on grade or sag - small lintel. |  | 1 |  | No. | 4522.76 |  | 4522.76
(b)600 x 600mm, Type 2A, I.A.W IPWEAQ DS-050 |  | 2 |  | No. | 1868.6 |  | 3737.2
(c) 600 x 600mm, Type 2A, I.A.W IPWEAQ DS-050. Dome |  |  |  | No. | 2498.39 |  | 0
top, including concrete apron - bio basin | [6 empty] | 0
(d) 900x900 Field Inlet - Type 1 - Concrete Apron |  |  |  | No. | 2455.13 |  | 0
(e) 600x900 Field Inlet Pit with Class D Grated Lid |  |  |  | No. | 2049.56 |  | 0
Concrete/GRC - Class D - 900SQ Pit w/base - |  | 12 |  | No. |  |  | 0
0
0
0
0
7.Roofwater Property Connections
a) 150mm dia directly from chamber |  |  |  | No. | 148.71 |  | 0
8. HEADWALLS
a) 225 dia precast concrete complete |  |  |  | No. | 1083.95 |  | 0
b) 375 dia precast concrete complete |  |  |  | No. | 1836.05 |  | 0
Trench Gate |  |  |  | m | 550 |  | 0
9. Supply all materials, excavate for and construct the
following concrete stormwater manholes, including
lids, (all depths) complete:
(a) 1050mm dia. < 2m depth |  | 1 |  | No. | 5120.37 |  | 5120.37
b) 1200mm dia. < 2m depth |  | 1 |  | No. | 5485.28 |  | 5485.28
c) 1500 dia |  |  |  | No. | 5913.11 |  | 0
Geo Testing |  |  |  | No. | 600 |  | 0
Neighbouring Property additional Labour |  |  |  | No. | 1200 |  | 0
Neighbouring Property & Balfour additional rectification |  |  |  | No. | 722 |  | 0
Balfour St asphalt |  |  |  | No. | 2200 |  | 0
Balfour st vacuum truck |  |  |  | No. | 1500 |  | 0
Balfour st MH Additional hire, shore, plate etc |  |  |  | No. | 2144 |  | 0
10. Supply all materials, excavate for and construct swale, including |  |  |  | Item | 6627.44 |  | 0
turfing. Refer drawing BE210215-01-C470 & C471 for details.
11. BIO-RETENTION / DETENTION BASIN
a) Excavation for bio-retention to fill onsite |  |  |  | m3 | 15.84 |  | 0
b) Impermeable proprietary liner fabric |  |  |  | Item | 1983.84 |  | 0
c) Subsoil Drainage, including collector pipe and clean out points |  |  |  | m | 38 |  | 0
d) Drainage layer |  |  |  | m3 | 237.75 |  | 0
e) Transition laye |  |  |  | m3 | 303.76 |  | 0
f) Filter Material, including testing |  |  |  | m3 | 224.73 |  | 0
g) Turf to filter area including geotextile |  |  |  | m2 | 17.61 |  | 0
h) Lock rail with steel posts I.A.W IPWEAQ RS-049 |  |  |  | Item | 4408.54 |  | 0
i) Bio retention batter planting including subgrade |  |  |  | Item | 16097.45 |  | 0
cultivation, topsoil spread, coir netting, and planting
complete. Refer Landscape Documentation prepared
by Saunders Havill Group
12. MISCELLANEOUS
a) Stone Pitching |  |  |  | m2 | 151.03 |  | 0
13. Carry out CCTV video survey and condition report on all
stormwater drainage pipework after completion, in
standard Council-prescribed format by approved
consultant, for submission to Council by the
Superintendent at the following stages of the works:
(a) At Practical Completion of works ("On-Maintenance"). |  | 1 |  | Item | 1038.79 |  | 1038.79
(b) At time of "Off Maintenance" Inspection |  | 1 |  | Item | 1038.79 |  | 1038.79
Allow for 150mm Wide Trench with Heel Guard Grage |  | 25.51 |  | m |  |  | 0
Allow for 450mm wide spoon drain |  | 162.78 |  | m |  |  | 0
Allow 200mm - 300 mm rock picking |  | 16.8 |  | m3 |  |  | 0
28 meter lever spreader as below
Allow for 500 mm lever spreader |  | 3.73 |  | m |  |  | 0
Allow for 200 mm lever spreader |  | 20.46 |  | m |  |  | 0
Allow for 150 mm lever spreade |  | 6.21 |  | m |  |  | 0
65 mm knock outs @ 2m space |  | 16 |  | ea |  |  | 0
DetentionTank
Allow for 10mx 1.4 high detention wall |  | 2 |  | ea |  |  | 0
Allow for 29.20m x 1.4m high detention wall |  | 2 |  | ea |  |  | 0
Allow for 10m x29.20 detention Base |  | 292 |  | m2 |  |  | 0
Allow for 1.3m weir wall |  | 2 |  | ea |  |  | 0
Allow for 450x150mm RECTANGULAR ORIFACE |  | 1 |  | ea |  |  | 0
Allow for 750x150mm RECTANGULAR ORIFACE |  | 1 |  | ea |  |  | 0
Allow for 0.80m weir |  | 1 |  | ea |  |  | 0
Allow for Spel Treatment area |  | 1 |  | ea |  |  | 0
0
Allow for Type A Precast lip in lin on Grade Gull Inlet |  | 1 |  | ea |  |  | 0
Allow fpr 100 mm sub soil drainage |  | 345 |  | m |  |  | 0
TOTAL PART D: | [6 empty] | 25129.8652
(Carried forward to Summary)
PART E - POTABLE WATER RETICULATION
1. Supply all materials, clearing and grubbing, excavate in all
materials, bed, lay, joint, backfill and all NATA testing for the
following diameter water mains, including all fittings, bends,
concrete thrustblocks, approved backfill under roads, testing of
backfill compaction, pressure testing, disposal of surplus
materials off site and restoration of surfaces:
(a) 100mm dia. PVC-M PN16 Series 2 (RRJ). |  |  |  | lin.m. | 132.15 |  | 0
(b) 100mm dia. DICL PN35 Series 2 (RRJ). |  |  |  | lin.m. | 209.15 |  | 0
(c) 100mm dia. DICL Crossing underneath Stormwater |  |  |  | Item | 10515.48 |  | 0
(d) DN25 PE 100 |  | 16.85 |  | lin.m. |  |  | 0
pipework complete with concrete thrust restraints &
associated fittings in accordance with approved detail
on drawing BE210215-01-C510.
2. Extra/over Item 1 for excavation of rock in stormwater
trenches as follows (Provisional):
a) By excavator larger than 148kW. |  |  |  | cu.m. | 25 |  | 0
b) By jackhammer. |  |  |  | cu.m. | 180 |  | 0
3. Supply all materials and install approved hydrants to
the following diameter water mains complete,
including hydrant tee, bend, riser, hydrant box
concrete surround and kerb/pavement marking:
(a) 100mm dia. On Line |  |  |  | No. | 1005.89 |  | 0
(b) Temporary Duck Foot Hydrant |  |  |  | No. | 879.53 |  | 0
4. Supply all materials and install approved sluice valves
to the following diameter water mains complete,
including jointing, margin setts, boxes, associated
concrete thrust restraint and kerb/pavement marking:
(a) 100mm dia. end of line including puddle flange and |  |  |  | No. | 1884.31 |  | 0
concrete thrust restraint.
5. Supply all materials and install the following internally
lined and externally coated DICL fittings including bed,
lay, joint, backfill and thrust blocks:
(a) Tee:
(i) 100mm x 100mm. |  |  |  | No. | 382.19 |  | 0
(b) Bends:
(i) 100mm dia. 11.25 degree Bend |  |  |  | No. | 329.88 |  | 0
(ii)100mm x 22.5 degrees |  |  |  | No. | 568.47 |  | 0
(iii)100mm x 45 degrees |  |  |  | No. | 568.47 |  | 0
(iv) 100mm dia. 90 degree Bend |  |  |  | No. | 329.88 |  | 0
6. Supply all materials and construct the following 25mm
OD MDPE Series 1 SDR11 PE100 PN16 water
service pipework complete including ball valves,
additional footpath excavation, sand bedding,
backfilling and property service marker discs:
(a) To each allotment on same side of street. |  |  |  | No. | 720.84 |  | 0
(b) To each allotment on opposite side of street. |  |  |  | No. | 720.84 |  | 0
(c) Extra Over Supply and Install Water Meters box complet |  |  |  | No. | 121.64 |  | 0
7. Sterilisation of all water mains including supply of |  |  |  | Item | 547.37 |  | 0
chlorine, water for chlorination and bacteriological
sampling and testing.
8. Locate existing 100mm dia. water main and arrange |  |  |  | No.
connection of new water mains, complete including
application forms and payment of all applicable fees
and charges. (Provisional)
Live water Con & Prop Service |  |  |  | No. | 22240.61 |  | 0
Supply Meter_007 - DN100 Fire |  |  |  | No. | 7800 |  | 0
25Con & Meter |  |  |  | No. | 3100 |  | 0
Live work 1 , allow for expense of installing new fire hydrant |  |  |  | No . |  |  | 0
Live work 2 , allow for connecting to the existing main , |  |  |  | No . |  |  | 0
proposed DN25 Water service and 20mm meter
Live work 3 make connection live in Manhole |  |  |  | No . |  |  | 0
TOTAL PART E: | [6 empty] | 0
(Carried forward to Summary)
PART F - SEWERAGE RETICULATION
1. Supply and install sewer pipes including clearing and
grubbing, excavation, bends and fittings and
backfilling of trenches, including approved backfill,
approved trench filling, testing of backfill compaction,
vacuum testing by NATA-approved laboratory,
disposal of surplus materials off site and restoration of
surfaces for sewer lines in the following depth ranges:
(a) 150mm dia. PVC SN8 pipe: |  |  |  | lin.m. | 135.08 |  | 0
(i) <1.5m depth. |  |  |  | lin.m. | 142.32 |  | 0
(i) 1.5 - 2.0m depth. |  |  |  | lin.m. | 151.02 |  | 0
(ii) 2.0 - 2.5m depth. |  |  |  | lin.m. | 174.92 |  | 0
(iii) 2.5 - 3.0m depth. |  |  |  | lin.m. | 214.75 |  | 0
(iv) 3.0 - 3.5m depth. |  |  |  | lin.m. |  |  | 0
(c) DN110 PE 100 |  |  |  | lin.m. | 132 |  | 0
(d) DN160 PE100 |  |  |  | lin.m. | 190 |  | 0
2. Extra/over Item 1 for excavation of rock in stormwater
trenches as follows (Provisional):
(a) By excavator larger than 148kW. |  |  |  | cu.m. | 25 |  | 0
(b) By jackhammer. |  |  |  | cu.m. | 180 |  | 0
3. Supply all materials and construct the following
precast sewer maintenance holes in accordance with
SEQ standards, complete including bedding,
benching, vacuum testing by NATA-approved
laboratory and sub-soil drainage, but excluding frames
and covers:
(a) SEQ Type 'P2' - DN 1050mm: |  |  |  | No. | 6947.87 |  | 0
(i) <1.5m depth. |  |  |  | No. | 6208 |  | 0
(ii) 1.5 - 2.0m depth. |  |  |  | No. | 8089.57 |  | 0
(iii) 2.0 - 2.5m depth. |  |  |  | No. | 8696.91 |  | 0
(iv) 2.5 - 3.0m depth. |  |  |  | No. | 10296.79 |  | 0
(v) 3.0 - 3.6m depth.
Maintenance Shaft |  |  |  | No. | 2250 |  | 0
4. Supply all materials and install the following ductile
iron maintenance hole covers, frames and surrounds
complete, in accordance with SEQ requirements:
(a) Class 'B' cover and frame (in roadways) |  |  |  | No. | 262.74 |  | 0
(b) Class 'D' cover and frame (in roadways) |  |  |  | No. | 742.9 |  | 0
5. Supply all materials, excavate for, bed, lay, joint,
backfill and test the following house connection
branches to sewer lines complete, including fibreglass
reinforced oblique junction fittings, bends, inspection
tees, concrete surround and location markers:
(a) 100mm dia. UPVC Class SN6:
(i) Type A |  |  |  | No. | 791.48 |  | 0
(ii) Type B |  |  |  | No. | 1047.42 |  | 0
(iii) Type D |  |  |  | No. | 1406.22 |  | 0
(iv) Type C |  |  |  | No. |  |  | 0
6. MAINTENANCE SHAFTS
Construct maintenance shafts including excavation,
backfilling, rendering, benching, drops and step irons,
excluding covers |  |  |  | No. | 2305.69 |  | 0
Rodding End
Cap Seal Exisiting |  |  |  | No. | 320 |  | 0
7. Supply all materials and construct the following
maintenance hole drops complete, including coupling,
hydrophylic rubber seal and short pipe as detailed:
(a) 150mm dia. pipe:
(i) Type V drop - benching only. |  |  |  | No. | 177.26 |  | 0
(ii) Type Y |  |  |  | No. | 1148.12 |  | 0
(iii) Type W |  |  |  | No. | 542.7 |  | 0
8. Supply all materials and construct temporary end cap |  |  |  | No. | 182.46 |  | 0
to UPVC Class SN8 sewer lines to be extended in
future contracts, including approved location markers.
9. Decomission and remove existing sewer main and |  |  |  | Item | 6081.91 |  | 0
structure between new structures 01/01 & 04/01
including excavation, disposal of pipe and structure
offsite, backfill, compaction and testing, after
successful live connections of the new sewer.
10. Complete live works break-in of existing sewer pipe |  |  |  | No. | 729.83 |  | 0
crown upon successful completion of On-Maintenance
Inspection. Refer to drawing BE210215-01-C620 for
additional details. (Provisional)
11. Carry out CCTV video survey and condition report on
all sewerage reticulation pipework, in standard Council
prescribed format by approved consultant, for
submission to Council by the Superintendent at the
following stages of the works:
(a) At Practical Completion of works ("On Maintenance"). |  |  |  | Item | 1507.95 |  | 0
(b) At time of "Off-Maintenance" Inspection |  |  |  | Item | 1507.95 |  | 0
CCTV Of exisitng to confirm OK for use |  |  |  | Item | 1180 |  | 0
VAC TEST |  |  |  | Item | 850 |  | 0
GEO TEST |  |  |  | Item | 1200 |  | 0
Conc Test |  |  |  | Item | 680 |  | 0
12. Excavation
a) Extra over for excavation in rock |  |  |  | m3 | 250 |  | 0
b) Extra over for excavation and disposal of unsuitable |  | Rate Only |  | m3 | 150
material and supply of additional bedding to trench or
structure foundation
13. BEDDING
a) Extra over for Type 4 bedding |  | Rate Only |  | m | 6.16
14. MISCELLANEOUS
a) Live sewer works delivered under the LCC Developer |  |  |  | Item | 3955.54 |  | 0
delivered live works process, excluding Council and
Consultant fees
TOTAL PART F: | [6 empty] | 0
(Carried forward to Summary)
PART G - STORMWATER TREATMENT
Phase 1: Sediment Basin | [5 empty] | Allowed for in Part A - Item 5
1. Excavation in all materials within bio-basins to nominal
1000mm below ultimate top of media level to establish
temporary sediment control basin, including lead
excavated material to site fill areas as directed.
2. Maintenance of sediment control basins, including | [5 empty] | Allowed for in Part A - Item 5
pump-out and manual flocculation following rainfall
events throughout construction.
3. Testing of sediment basin water quality by NATA | [5 empty] | Allowed for in Part A - Item 5
accredited laboratory prior to commencement of
dewatering.
Phase 2: Building Work Phase
4. Decommissioning and cleanout of sediment basin | [5 empty] | Allowed for in Part A - Item 5
following completion of civil infrastructure works,
including trim floor of basin to level of ultimate base of
drainage layer:
5. Supply all materials and construct reinforced concrete
overflow weirs to basins, complete as detailed,
ncluding all reinforcement and jointing.
(a) Overflow weir (4m wide) - reno mattress scheduled elsewhere. |  |  |  | Item | 2989.23 |  | 0
(b) High flow weir (3.5m wide) - reno mattress scheduled |  |  |  | Item | 2989.23 |  | 0
elsewhere.
6. Supply all materials and construct coarse forebay inlet |  |  |  | sq.m | 431.72 |  | 0
area, including all concrete and steal reinforcement,
nib wall and energy dissipator as detailed on the
drawings, generally in accordance with the detailed
design drawings.
7. Supply all materials and install flood hazard sign at |  |  |  | Item | 486.55 |  | 0
basin entrance.
8. Supply all materials and construct compacted gravel |  |  |  | sq.m. | 31.93 |  | 0
driveway & 1m access track in accordance with
drawings.
9. Supply all materials and construct 175mm thick |  |  |  | sq.m. | 229.48 |  | 0
concrete access driveway. Refer basin driveway
access detail on drawing BE210215-01-C451.
10. Supply all materials and construct 300mm thick rock |  |  |  | sq.m. | 95.68 |  | 0
scour protection with 200mm nominal dia. Rock
adjacent to sediment forebay.
11. Supply all materials and construct 230mm thick Reno |  |  |  | sq.m. | 77.99 |  | 0
rock mattress 80-150mm dia. Rock. Refer to drawing
BE210215-01-462 for details.
12. Supply all materials, excavate for and construct the
following bio-basin inlet structures including rock scour
protection surrounds & filter cloth, as detailed:
(a) 900 x 600 pit with hinged gate |  |  |  | No. | 2351.73 |  | 0
(b) 900 x 900 pit with hinged gate with 425mm diameter |  |  |  | No. | 2820.04 |  | 0
orifice plate.
13. Supply and install all materials, clearing and grubbing,
excavate for, bed, lay, joint and backfill the following
drainage lines , including jointing materials, approved
bedding, backfill, approved backfill under roads,
testing of backfill compaction, disposal of surplus
materials off site and restoration of surfaces:
(a) 450mm dia. Class 2 (RRJ). (including concrete collar) |  |  |  | lin.m. | 206.07 |  | 0
14. Supply all materials, excavate for and construct
headwalls to suit the following inlet/outlet structures:
(a) 450mm dia. |  |  |  | Item | 729.83 |  | 0
15. Supply all materials, excavate for and install 150mm |  |  |  | lin.m. | 134.34 |  | 0
dia. solid HDPE collector pipe as outlet line from
drainage layer to basin outlet pit, as detailed.
16. Supply all materials, excavate for and install 100mm |  |  |  | lin.m. | 26.4 |  | 0
dia. slotted HDPE collector pipe in drainage layer to
collector pipes, as detailed including branches and
clean-out drain as detailed.
17. Supply all materials and construct bio-basin drainage |  |  |  | cu.m | 225.91 |  | 0
layer, as detailed (2-5mm screenings), nominal
150mm depth.
18. Supply all materials and install coarse sand transition |  |  |  | cu.m | 231.03 |  | 0
layer, nominal 100mm depth, as detailed.
19. Supply all materials and install approved filter media |  |  |  | cu.m. | 154.18 |  | 0
as detailed (sandy loam material), to nominal 600mm
depth as directed.
20. Supply all materials and install approved geofabric |  |  |  | Item | 727.4 |  | 0
liner as media surround to floor and walls of ultimate
bio basin, as detailed.
21. Supply and place temporary approved cover-turf to top |  |  |  | Item | 2188.88 |  | 0
of bio basin areas, including sacrificial geofabric layer.
22. Supply and install slip rail gate as per council |  |  |  | No. | 3040.95 |  | 0
standards and details.
23. Install all required fencing and landscaping treatments |  |  |  | No. | NO DETAILS
around bio-retention basin as detailed on Landscape
Architect's plans.
Phase 3: Vegetation Planting Phase
(Provisional - Upon Completion of 80% of houses/building works)
24. At completion of building works phase, remove |  |  |  | Item | 2298.96 |  | 0
temporary cover from top of basins:
25. Supply all materials and extend approved filter media |  |  |  | sq.m. | 34.84 |  | 0
(sandy loam material), to finished basin surface level
as directed (nominal 100mm depth):
26. Supply materials and carry out vegetation |  |  |  | Item | NO DETAILS
stabilisation/landscaping to basin areas as detailed:
TOTAL PART G: | [6 empty] | 0
(Carried forward to Summary)
PART H - ELECTRICAL & COMMUNICATIONS (PROVISIONAL)
(N.B All work to be carried out by Energex and Telstra accredited
contractors)
1. Excavate for the following road crossing conduits for
all depths, including supply and place approved
bedding and surround and approved backfill
(Provisional).
(a) Electrical and communications joint-use trench. |  |  |  | lin.m | 59.53 |  | 0
(b) Single-Use Trench |  |  |  | lin.m | 38.74 |  | 0
2. Supply all materials, lay and joint the following road
crossing conduits including draw rope, marker discs,
warning tape and plastic cover strip: (Provisional)
(a) Electrical Conduits (Orange PVC)
(i) 40mm dia. Heavy duty (street light conduit). |  |  |  | lin.m | 7.1 |  | 0
(ii) 100mm dia. Light duty |  |  |  | lin.m | 14.64 |  | 0
(iii) 125mm dia. Light duty |  |  |  | lin.m | 17.7 |  | 0
(b) Electrical Communication Circuit Conduits (White
PVC)
(i) 100mm dia. Medium duty |  |  |  | lin.m | 14.64 |  | 0
(c) Telstra / NBN Conduits (white PVC)
(i) 50mm Dia light duty. |  |  |  | lin.m | 8.31 |  | 0
(ii) 100mm dia. Light duty. |  |  |  | lin.m | 13.01 |  | 0
(d) Private Commmunications / C.A.T.V Conduits (White
PVC)
(i) 100mm dia. Light duty. |  |  |  | lin.m | 13.01 |  | 0
TOTAL PART H: | [6 empty] | 0
(Carried forward to Summary) | [6 empty] | 0
PART E - INTERNAL PLUMBING
1. Supply all materials, clearing and grubbing, excavate in all
materials, bed, lay, joint, backfill and all NATA testing for the
following diameter water mains, including all fittings, bends,
concrete thrustblocks, approved backfill under roads, testing of
backfill compaction, pressure testing, disposal of surplus
materials off site and restoration of surfaces:
(a) 100mm dia. PVC-M PN16 Series 2 (RRJ). |  |  |  | lin.m. | 130.11 |  | 0
(b) 100mm dia. DICL PN35 Series 2 (RRJ). |  |  |  | lin.m. | 209.15 |  | 0
(c) 100mm dia. DICL Crossing underneath Stormwater |  |  |  | Item | 10515.48 |  | 0
(d) DN25 PE 100 |  |  |  | lin.m. |  |  | 0
pipework complete with concrete thrust restraints &
associated fittings in accordance with approved detail
on drawing BE210215-01-C510.
2. Extra/over Item 1 for excavation of rock in stormwater
trenches as follows (Provisional):
a) By excavator larger than 148kW. |  |  |  | cu.m. | 25 |  | 0
b) By jackhammer. |  |  |  | cu.m. | 180 |  | 0
3. Supply all materials and install approved hydrants to
the following diameter water mains complete,
including hydrant tee, bend, riser, hydrant box
concrete surround and kerb/pavement marking:
(a) 100mm dia. On Line |  |  |  | No. | 1005.89 |  | 0
(b) Temporary Duck Foot Hydrant |  |  |  | No. | 879.53 |  | 0
4. Supply all materials and install approved sluice valves
to the following diameter water mains complete,
including jointing, margin setts, boxes, associated
concrete thrust restraint and kerb/pavement marking:
(a) 100mm dia. end of line including puddle flange and |  |  |  | No. | 1884.31 |  | 0
concrete thrust restraint.
5. Supply all materials and install the following internally
lined and externally coated DICL fittings including bed,
lay, joint, backfill and thrust blocks:
(a) Tee:
(i) 100mm x 100mm. |  |  |  | No. | 382.19 |  | 0
(b) Bends:
(i) 100mm dia. 11.25 degree Bend |  |  |  | No. | 329.88 |  | 0
(ii)100mm x 22.5 degrees |  |  |  | No. | 568.47 |  | 0
(iii)100mm x 45 degrees |  |  |  | No. | 568.47 |  | 0
(iv) 100mm dia. 90 degree Bend |  |  |  | No. | 329.88 |  | 0
6. Supply all materials and construct the following 25mm
OD MDPE Series 1 SDR11 PE100 PN16 water
service pipework complete including ball valves,
additional footpath excavation, sand bedding,
backfilling and property service marker discs:
(a) To each allotment on same side of street. |  |  |  | No. | 720.84 |  | 0
(b) To each allotment on opposite side of street. |  |  |  | No. | 720.84 |  | 0
(c) Extra Over Supply and Install Water Meters box complet |  |  |  | No. | 121.64 |  | 0
7. Sterilisation of all water mains including supply of |  |  |  | Item | 547.37 |  | 0
chlorine, water for chlorination and bacteriological
sampling and testing.
8. Locate existing 100mm dia. water main and arrange |  |  |  | No.
connection of new water mains, complete including
application forms and payment of all applicable fees
and charges. (Provisional)
Council Fees |  |  |  | No. | 380 |  | 0
Inspection, test cert |  |  |  | No. | 2311 |  | 0
Sewer Divert |  |  |  | No. | 1987 |  | 0
TOTAL PART E: | [6 empty] | 0
(Carried forward to Summary)
SCOPE OF WORKS
Our proposal is based on the civil design package provided by Burchills Consulting Engineers. In no way should it be
deemed that we have included something detailed or noted in other drawings or documents either supplied or not. We note
hat landscape drawings were not provided as part of the tender package.
CLARIFICATIONS SPECIFIC TO THE SCOPE
Preliminary
• No allowance has been made for payment of such fees as portable long service levy, workplace health and safety ee, local authority applications and/or inspection fees or bonds.
Clearing and demolition
• No allowance has been made for additional works, delays or costs associated with, treatment, management,
demolition, protection, removal or reinstatement of Trees/Flaura/Root systems incl Arborist costs or NALL permits.
• No allowance has been made for creation, implementation or management of Vegetation Management plans.
• No allowance has been made to remove tree stumps on boundaries where damage to existing fences or structures could occur.
• No allowance has been made for vacuum excavation of tree stumps in or close to existing underground services, fences or tree protection zones or at the direction of an arborist.
• We have made no allowance for encountering asbestos or potential asbestos containing materials above or below he ground.
• No allowance has been made to demolish and reconstruct existing structures unless detailed.
Earthworks
• No allowance has been made for encountering, removing and treatment of PASS (Potential Acid Sulphate Soils) or unsuitable material below the natural surface.
COMMERCIAL
GST
Unless specifically noted, all prices or rates provided in the tender schedule are excluding GST.
Insurances
We have allowed for public and products liability to $20million and WorkCover or where not applicable, personal accident
insurance. We have assumed that our scope will fall under the principal contractors contract works insurance.
GENERAL
Working hours
Tender provided is based on permitted hours of work for that local council, and is generally Monday to Friday – 6:30am to
6:30pm excluding public holidays. Should work be required outside these hours, this will incur additional costs. Reduced
allowable working hours as a result of permit conditions may also incur additional costs
Program of works
Our construction duration is approx. 16 weeks from date of possession of site. If successful we can provide a detailed
program of works. Lead time on permits for this project are 8-10 Weeks.
Extensions of time
Wet weather, unforeseen circumstances, encountering rock or unsuitable material, design changes, interruption by other
trades, public holidays and Christmas closure periods will require extensions of time. To remove any doubt; rain and the
effects of rain will trigger an extension of time. This may include days proceeding a rain event, where no productive work can
be undertaken. Safety issues will be considered, as will the ability to undertake works in accordance with engineering
requirements.
Damage caused by others
No allowance has been made for the repair of damage to works caused by others, including damage caused by building
trades and/or client’s subcontractors during construction and/or maintenance periods.
Existing services
Unless specifically noted by a scheduled item, no allowances are made for protection, and/or support of, and/or relocation of
existing services.
Survey Control
Survey control data, control points and electronic data shall be provided prior to commencement. We have assumed
boundary pegs placed by a cadastral surveyor will be in place prior to our mobilisation to site.
Note on L210: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is it too high for retaining wall as .82 height max )